## Summary table
AREA | IOAC RECOMMENDATION (REFERENCE) | REFERENCE | STATUS
Structure | To share the WHE Programme roll-out plan with WHO staff in the country offices | EB140/8 | Fully implemented
Structure | IM DOA: To provide pre-deployment orientation on WHO systems, procedures, DOA and its relationship to the CO, with DOA being issued concurrent with the IM activation. | Monitoring Framework 3/21, A73/10, A70/8. | Fully implemented
Structure | To adapt the IMS principles and approaches to WHO’s mission and structure, iteratively improving and systematizing WHO’s approach over time. To use IMS for acute emergencies and focus on surge of staff and partners in humanitarian crisis settings. | A72/6, A70/8, EB140/8. | Target achieved, progress continuing
Structure | WHE surge: To strengthen technical expertise across the organization and develop a policy for surge capacity (especially as regards health operations leads, senior epidemiologists and infectious disease specialists) that authorizes the release of technical expertise within the organization at all levels, leveraging in-house expertise and partners on the ground. To clarify and adapt reporting lines and performance management of staff deployed as surge capacity. | A73/10, Interim Report 2020, EB146/16, A72/6, EB144/8. | In progress
HR | Ensure a baseline of staffing capacity is present in country offices (including HCC and IMO posts and senior staff, e.g. deputy WR when WR assumes IM role), with a particular focus on priority countries (e.g. fragile states). Ensuring WR engagement in decisions re. WHE CO staffing and that all necessary functions should have the needed capacity (e.g. administration, HR, finance, emergency response, operational partnerships and procurement). The recruitment process should not be held back by the transformation agenda and staffing capacity should be at least 75% of the total planned positions. | Monitoring Framework 3/21, A73/10, EB146/16, A72/6, EB144/8, EB142/8, A70/8, EB140/8. | In progress
HR | CO Capacity Building: To invest in and support national staff, including the training of WRs for emergency response. To enable and encourage WRs to effectively engage with in-country donors. | Monitoring Framework 3/21, A70/8, EB140/8. | Fully implemented
HR | Rosters: To increase the supply of a diverse pool of competent staff to lead emergencies, further develop IM rosters and create deputy IM posts that are preferably filled by under-represented suitably skilled groups. To expand the recruitment pool rather than limiting to internal WHO staff and to explore flexible contractual arrangements and roster arrangements for emergencies. Endeavour to find candidates with the skill sets that match specific country needs, to developing an internal roster system for potential health cluster coordinators and information management officers, and to upgrade the training, orientation and empowerment of health cluster coordinators. | Monitoring Framework 3/21, A73/10, EB146/16, A71/5, EB142/8, A70/8. | Fully implemented
HR | Career progression: To establish a promotion system that rewards high-performing staff and motivates others. The IOAC considers that special consideration should be given to the recruitment and career progression of staff working at extreme hardship duty stations. | Monitoring Framework 3/21, A73/10, EB146/16, A72/6. | In progress
HR | Recruitment strategy and planning: The capacity for HR planning, recruitment and management should be evaluated in order to deliver improvements. A longer-term recruitment strategy should be developed which can attract, orient and support the best candidates. | A73/10, EB142/8, A70/8. | In progress
HR | 3 levels staffing balance: To identify trade-offs within a more limited staffing footprint, and reconsider the balance of HQ, RO, and field staff, without jeopardizing the operational capacity for emergency management. To recruit greater numbers of national staff with fewer international positions in COs . | EB146/16, A70.8, EB140/8. | In progress
HR | Staffing gaps and rates: The IOAC recommends that WHO identify staffing gaps and provide flexibility to minimize the disruption during the transitional period. Aim to improve on the recruitment rate: HQ 70%, RO 50%, CO 35% position filled as of Dec 2016. | Monitoring Framework 3/21, EB146/16, A70/8, EB140/8. | In progress
HR | To increase HR capacity and staff trained in emergency response at the country level. | EB146/16, A72/6. | In progress
HR | To complete the recruitment to fill the dedicated full time HCC and IMO posts at country level and ensure satisfactory information management and coordination. | Monitoring Framework 3/21, A72/6, EB144/8. | In progress
HR | Hardship: WHO to develop incentives and appropriate leave policies specifically for staff working in emergencies, taking into consideration increased workload and also need for support and protection from workplace harassment. The need to review the degree of hardship in offices is also recognised (e.g. those in cross-border posts) and to implement a staff rotation policy for hardship duty stations. | Monitoring Framework 3/21, A73/10, EB146/16, A70/8, EB140/8 | In progress
HR | To conduct an HR benchmarking exercise focused on incentives, and appropriate R&R in emergency settings against those of peer UN agencies and development organizations working in emergencies that have good systems in place for talent acquisition and management. | A73/10, EB146/16, A71/5, EB142/8, EB140/8, A70/8. | In progress
HR | The IOAC stresses that ensuring that the WHE Programme operations are transparent and free of collusion, fraud and corruption, is of paramount importance. The IOAC also notes that the investigation into the allegations of corruption in Yemen has yet to be completed, while the reputation of the Programme staff cited in those allegations remains seriously compromised. | A73/10. | In progress
HR | To conduct annual or biennial staff culture survey and support the DG’s plan to undertake a similar survey on a regular basis and pulse surveys at regular intervals. To develop an action plan for implementing improvements against the outcomes of the survey, and that performance on this plan be reported within the IOAC reporting framework by WHE Programme leadership. | A72/6. | In progress
HR | The IOAC welcomes the organization’s efforts to improve diversity and recommends using the WHE Programme as a pilot for the organization in this regard. Work should take into account the socioeconomic and gender-related implications of preparing for, responding to, and recovering from public health emergencies and their interventions, by establishing a small dedicated team of social scientists and gender equality experts within the WHE Programme, guided by an external advisory group or expert network. | Monitoring Framework 3/21, A73/10, A72/6. | Target achieved, progress continuing
HR | To develop a system of performance management that includes 360-degree feedback and introduces the element of assessing how outcomes have been achieved. | EB146/16, A72/6. | In progress
Staff Protection | WHO to invest in its own security function across the field, COs, ROs and HQ to make it robust, appropriately and flexibly funded, accessible, responsive and able to deliver in hostile and insecure environments. | A73/10, EB146/16, A72/6, A70/8. | In progress
Staff Protection | WHO to implement security procedures and strategy in field settings for acute emergencies, outbreaks and protracted crises. WHO should be prepared to support staff and protect them when working in areas with limited infrastructure and increased security risk. Systematic risk assessments combined with preventative measures should be used to mitigate risk. | EB146/16, EB144/8, A71/5, EB142/8, A70/8, EB140/8. | In progress
Staff Protection | The IOAC recognizes the provision by medical services of psychological support to the staff working in the DRC on the Ebola crisis and recommends that this practice should be institutionalized for other emergencies. MS are encouraged to guide the WHO Secretariat to improve the well-being and satisfaction of staff across the globe. | EB146/16, A72/6. | In progress
Staff protection | To clarify and simplify the various elements of the grievance and redress system to increase staff trust in the mechanisms, and make them more responsive. The WHE Programme senior management should ensure that effective staff welfare and protection measures are in place in the field and at all levels of the organization, and make them accessible and responsive. | EB146/16, A72/6. | Fully implemented
Coordination/ Management | The ERF should further clarify the roles and specific responsibilities of each office embedded in the WHE programme and reinforce institutional measures required for rigorous compliance therewith, providing a single line of authority in case of disagreement. Both the RDs and the WHE ED share accountability for infectious hazard events and other health emergencies with potential to spread internationally. They share responsibility for day-to-day management of those events. The roles, responsibilities and accountabilities of each player and updated processes for all-hazards emergency risk management should be enshrined in the ERF. | A73/10, A71/5. | In progress
Coordination/ Management | To improve the agility and flexibility of the WHE Programme through an appropriate level of autonomy and authority based on the principle of a single structure, single budget, single staff workplan and common results framework across WHO headquarters and all regional offices. Managerial responsibility of the WHE Programme rests with its Executive Director, who reports directly to the Director-General. Regional Emergency Directors should have delegated authority for emergency management in their respective regions and report directly to the Regional Directors and the WHE Programme Executive Director. The IOAC emphasizes the importance of close collaboration and coordination between the WHE Programme Executive Director and the Regional Directors for major emergencies management and recruitment of key senior staff such as the Regional Emergency Directors to ensure coherent work as “One Programme”. | A73/10, EB146/16, A72/6. | In progress
Coordination/ Management | Centralization: The IOAC recommends that transitional steps be taken to ensure that the centralized corporate structure does not dilute the particular and immediate needs of emergency operations and risk mitigation. To provide for this, there is a need to put in place dedicated teams within the centralized functional divisions to support emergencies, with a dual reporting line to the WHE Programme and respective division heads. Key performance indicators will need to be established to track these critical enabling functions, such as communications, resource mobilization, procurement, security and HR, to ensure that their effectiveness is maintained and improved. Further, a time-limited working group dedicated to addressing major issues for streamlining administrative and operational systems in an emergency response should be created. | A73/10, Interim Report 2020, EB146/16, A72/6, A70/8. | In progress
Coordination/ Management | Incident Management: To build a critical mass of qualified WRs and IMs through rosters and training and linkage. To hold the WR accountable for the performance of the IM and to engage IMs on longer-term contracts. IM should have a direct line to the WHE/EXD to ensure appropriate technical and operational oversight and should also be given greater authority, particularly in relation to recruitment, procurement and finance. For that reason, IMs should have the appropriate profile and experience in order to lead effectively, and in addition, be properly empowered and supported to carry out their role. This support should entail being released from other duties and assignments for an extended period, as required. Additionally, WRs should also be further empowered and supported in their roles. | Monitoring Framework 3/21, A70/8, EB140/8. | Fully implemented
Coordination/ Management | IHR should be reviewed by MS in the light of the COVID-19 pandemic to ensure that the attribution of authority and roles outlined under the Regulations are in alignment with MS’ understanding and expectations. This may entail revisiting the roles and responsibilities of the WHO secretariat and the duties of MS. | A73/10, Interim report 2020. | In progress
Leadership | WHO to document its work under the 'Whole of Syria' approach – an operational approach to a complex humanitarian and health crisis – to inform future responses. | EB146/16. | In progress
Leadership | WHO’s Emergency Response Framework (ERF) should be consistently followed by staff at all levels of the Organization. | A73/10, A71/5. | In progress
Leadership | To improve coordination among the departments of the WHE, across the three levels and to accelerate implementation of the WHE at country level. The IOAC emphasizes that WHO’s work in outbreaks and emergencies must be reflected in every aspect of the organization as a core part of its mandate and best practice leveraged across the organisation. Administrative support staff should be deployed at the beginning of an emergency activation in order to assist the team with its heavy field deployment demands and to navigate the business systems. During a response, a dedicated emergency administrative support officer should also sit in the CO to provide added capacity and facilitate support to the Programme. | A73/10, Interim Report, A70/8, EB140/8. | In progress
Leadership | The IOAC emphasizes that the quality assurance of laboratory testing and timely analysis of genetic sequencing data are critical to fully characterize the evolution of the EVD outbreak in order to inform diagnostic, vaccine and treatment approaches and recommends closer collaboration between INRB and WHO. However, WHO should leverage experiences from the DRC and Uganda to fast track approvals for the administration of investigational vaccines and therapeutics and their deployment. WHO should enhance mentorship, training and supervision to ensure capacity to make this happen. | Monitoring Framework 3/21, A72/6, EB144/8. | In progress
Leadership | Further improvement is required in terms of accountability to, and coordination with, the WHE Programme, the External Relations Division and the rest of the organization at all three levels, to maximize available resources and ensure consistent messaging for major emergencies. This would involve improvement in both internal and external communications about the WHE Programme, especially with regard to the strategic vision, structure, function and deliverables of the WHE Programme. | Monitoring Framework 3/21, A73/10, EB142/8, A70/8. | In progress
Business Processes | To apply a fast track recruitment (in advance of funding if required) and shorten the recruitment process. | Monitoring Framework 3/21, A70/8. | Target achieved, progress continuing
Business Processes | WHO should conduct a benchmarking analysis for and promote a 'no regrets' approach in the supply chain process. It should consider either: outsourcing the function to another provider within the UN system, such as UNICEF’s Supply Division, to enable the WHE programme to procure and effectively manage and deliver its emergency stocks; or making an investment case for the entire organization, establishing a central division of supply chain management, with clear objectives and accountabilities across the organization, upon which the WHE can build if additional capacity for emergencies is required. | Monitoring Framework 3/21, A73/10, A71/5, EB142/8. | In progress
Business Processes | To streamline SOPs for emergency procurement: increase the expenditure limits in the delegation of authority, apply standard waivers in accordance with the DOA, systematize pre-qualified suppliers, simplify local contracts and payment processes, and fast track due diligence process as per the provision in the Framework of Engagement with Non-State Actors. | A70/8. | Fully implemented
Business Processes | Expertise of the WHE Programme operations support and logistics team and the emergency management field experience should be leveraged within the transformation agenda and the effectiveness of operations should be maintained. | A72/6. | Fully implemented
Business Processes | To implement emergency measures under FENSA across the regions. | EB146/16, EB142/8. | In progress
Business Processes | To caution when operating the new business rules within the existing systems. Business processes must support the WHE Programme based on a no-regrets approach. | EB140/8. | Target achieved, progress continuing
Business Processes | To carry out further efforts to streamline the process and accelerate engagement to support critical emergency responses. | A72/6. | Target achieved, progress continuing
Risk assessment | To monitor the a. effectiveness of both ERF and EIOS, and b. track the ERF is properly implemented against the specific timeframes in 24hr, 72hr, 60days. | A70/8, EB140/8. | In progress
Risk assessment | To assess the effectiveness of the EMS and update the current systems. | A73/10, EB142/8, A70/8. | In progress
Risk assessment | To inform the governments concerned of grading decisions immediately prior to their announcement. | A70/8. | Fully implemented
IHR | CO IHR: Streamlining the IHR reporting process for COs and strengthening national capacity to report on IHR, including supporting countries to develop impact-oriented NAPs which prioritize short-term goals with timelines for implementation. | Monitoring Framework 3/21, EB146/16, A72/6, EB144/8, A71/5. | In progress
IHR | IHR CO: To reinforce the pool of expertise across the organization and to allocate a core budget for supporting countries with transition activities following major events, with a view to building IHR core capacities in a more sustainable way. The secretariat should review existing tools and mechanisms in the light of COVID-19 and the lessons learned. In that regard, national leadership, a whole of government approach, subnational level capacity, and community empowerment and resilience should all be considered. | Monitoring Framework 3/21, A73/10, EB144/8. | In progress
IHR | IHR CO: WHO is mandated to assist countries in making rational decisions, deploying effective measures to prevent public health emergencies and complying with the IHR requirements. | A71/5. | In progress
IHR | IHR CO: To support countries in maintaining the level of preparedness and avoiding burnout after Ebola readiness efforts. | A72/6. | Fully implemented
IHR | Funding preparedness: The IOAC cautions that investment in preparedness has been insufficient and the impact of WHO’s action on strengthening IHR core capacities is unclear. | A73/10, EB146/16. | In progress
IHR | JEE: IOAC cautions that the impact of JEEs and NAPHS on strengthening IHR core capacities is still unclear. The adequacy of tools to support country preparedness should be reviewed based on the lessons learned during the COVID-19 pandemic preparedness and response efforts, and improved under the guidance of the IHR Review Committee. The JEE tool should be suitable for its purpose, including its ability to assess: (i) capacity at the community level to alert and take early action, and (ii) the way in which strengthening community engagement is being built into core IHR capacity. | A73/10, EB146/16, EB140/8. | In progress
IHR | Countries should be supported with implementing corrective measures for critical areas of work identified in JEEs and after-action reviews. RO should support countries to share best practice and experience with JEE and NAP, and relevant community-based groups be systematically included in JEE processes to ensure that community-based surveillance and community early response systems are included in all evaluations. | Monitoring Framework 3/21, EB144/8, A70/8. | In progress
IHR | The IOAC notes it may be opportune for MS to reassess WHO Secretariat’s role in providing travel advice during a pandemic. | Interim report 2020. | In progress
IHR | The IOAC considers it opportune to introduce a graded PHEIC system with clear criteria and practical implications for countries , under the guidance and based on the recommendations of the IHR Review Committee, to facilitate preparedness, preventive action, and dedication of resources at the early stage of outbreaks, which could avert any escalation. The PHEIC grading must be tied to a set of binding actions under the IHR provisions . | A73/10. | In progress
IHR | Post COVID-19, it would be useful to independently assess the organization’s performance during this response and identify lessons for the future. The scope of such an assessment should be determined by MS, and should cover both MS and WHO secretariat’s actions in response to the COVID-19 pandemic. The IOAC encourages MS to consider whether: a stepped level of alerts and galvanization of response measures should be added to the IHR; to enhance the openness and transparency of the Emergency Committee process; and to review whether the IHR-nominated focal points in governments are able to adequately raise the alarm to ministers within their governments when a PHEIC is declared. The IOAC would caution that conducting such a review during the heat of the response could disrupt WHO’s ability to respond effectively. | A73/10, Interim report 2020. | In progress
Partnership | Demonstrate WHO’s leadership in the IASC for health and lead the committee during outbreaks. | Monitoring Framework 3/21, A73/10, A71/5, EB140/8. | Target achieved, progress continuing
Partnership | Partnership and engagement with host governments, humanitarian actors and NGOs on the ground should be leveraged to deliver collective progress. This should include an alignment of technical standards, financial arrangements, staff training, and development of joint protocols and standard operating procedures (SOPs) to improve collective capacity in terms of preparedness and response to large-scale health emergencies. This should also involve the dissemination of best practice and global standards for EMTs via national medical response teams. | Monitoring Framework 3/21, Interim report 2020, A72/6, EB144/8, A70/8. | In progress
Partnership | IOAC observes that WHO’s performance in the health cluster and interaction with partners in the field relies heavily on the individual ability of health cluster coordinators. Systematic measures and institutional support for health cluster coordinators are needed to ensure that WHO provides strong coordination and technical and operational support to partners on the ground through the health cluster system. | Monitoring Framework 3/21, A73/10. | In progress
Partnership | Close collaboration of health cluster coordinators with incident managers to enable closer engagement and effective coordination. | A72/6. | Fully implemented
Partnership | GOARN: Roles and responsibilities of WHE and partners in GOARN should be clarified, with the aim of establishing institutional arrangements for GOARD deployment. WHE should work closely with MS, GOARN partners and stakeholders to ensure a rapid roll-out of the Go.Data tool. | Monitoring Framework 3/21, EB146/16, A72/6, A70/8, EB140/8. | Target achieved, progress continuing
Partnership | WHO should promote the establishment of an appropriate multilateral governance mechanism for ensuring equitable access to therapeutics and vaccines for all countries and effective delivery and stewardship, drawing upon previous experience of epidemics and pandemics. Further, the organization should be actively involved in global efforts to promote equitable access to COVID-19 vaccines and treatments, and IOAC further recommends the continued active involvement of WHO in this process. | A73/10, Interim report 2020. | In progress
Partnership | The WHE Programme and the Science Division work with other divisions across the organization to implement the R&D Blueprint’s joint workplan with funding requirements, a common monitoring framework and a system of dual reporting to the WHE ED and the Chief Scientist. IOAC believes the programme should explore greater use of WHO collaborating centres around the world, expert networks, such as technical advisory bodies, and public health institutes, to generate technical recommendations and supplement capacity in fast-moving crisis. | Monitoring Framework 3/21, A73/10, Interim report 2020. | In progress
Partnership | Sufficient and consistent support for information management should be provided to the health cluster coordinator. | Monitoring Framework 3/21, A70/8. | In progress
Finance | CO Fundraising: Increasing in-country donor engagement by WRs to improve local fundraising. To increase CO's authority to fundraise during emergency response, partnering with rather than depending on RO or HQ.. | A73/10, EB146/16, A71/5, EB142/8, A70/8, EB140/8. | In progress
Finance | MS should be invited to consider an increase in assessed contributions in the form of long-term sustainable financing. The IOAC further advises WHO to: improve donor engagement; develop a credible, strategic, data-driven, and compelling narrative; improve understanding of donor requirements; engage with the right donor counterparts; prioritize unrestricted resources; and tailor fundraising strategies to specific donor and funding requirements. | Monitoring Framework 3/21, A73/10, Interim Report, A70/8, EB140/8. | In progress
Finance | WHO/WHE core budget: WHO is encouraged to increase allocation of the core flexible funding for the WHE Programme, in particular supporting countries with preparedness activities, for which it has proved difficult to raise funds. Further, there is a need to identify additional revenue sources for the core budget of the WHE Programme, and strengthened budgeting at country level. | Monitoring Framework 3/21, A73/10, EB146/16, A72/6, A70/8. | In progress
Finance | To clarify the relationships and division of labour between the CFE and other humanitarian funding streams that receive donor support in health emergencies. Redesigning the CFE replenishment mechanism, giving consideration to whether the CFE should be partly funded by the WHO core budget or whether alternative sources of funding, including from the private sector and foundations, should also be explored. | A73/10. | In progress
Finance | To boost humanitarian donors’ confidence. | A73/10, EB140/8. | In progress
Finance | Investment case: WHO share a draft of the corporate investment case paper with Member States to ensure that the final document is successful in robustly advocating the economic argument/case for investment to governments including ministers of finance and other donors. | EB142/8. | Fully implemented
Finance | Donors were urged to contribute in order to bring the EVD outbreak in DRC under control and contain the spread to surrounding countries. | A72/6. | Fully implemented
Finance | The IOAC believes that the CFE would be most effective if it was fully functioning as a revolving fund, but recognizes that it is not functioning as one currently, and recommends WHO to come forward with clear plans for its sustainability for the future. | Monitoring Framework 3/21, A70/8. | In progress
Finance | Financing surge capacity: To secure resources to maintain and increase core technical expertise capacity within the WHE Programme at HQ and enable the programme to leverage in-house experts through internal surge capacity. MS and WHO secretariat revisit the size and surge capacity of the WHE to ensure sufficient capacity, resilience and flexibility within and beyond the IMS to respond adequately to such multidimensional and large-scale emergencies, alongside the increasing number of graded emergencies that it routinely manages. | A73/10, Interim Report 2020, A72/6, EB144/8. | In progress
Finance | Corrective actions, including emergency measures under the Framework of Engagement with Non-State Actors, must be fully implemented at all three organizational levels, to support field responses. | A72/6, A71/5. | In progress

## Table with full description
AREA | IOAC RECOMMENDATION (REFERENCE) | REFERENCE | STATUS | PROGRESS AGAINST RECOMMENDATIONS AS OF APRIL 2021
Structure | To share the WHE Programme roll-out plan with WHO staff in the country offices | EB140/8 | Fully implemented | Implemented as part of the 2016 roll-out of the programme.
Structure | IM DOA: To provide pre-deployment orientation on WHO systems, procedures, DOA and its relationship to the CO, with DOA being issued concurrent with the IM activation. | Monitoring Framework 3/21, A73/10, A70/8. | Fully implemented | The DOA in emergencies was standardized across the regions in 2017. However, the application of such authority has been inconsistent due to a risk-averse organizational culture and lack of understanding by the staff involved in the process. Further, feedback from staff and partner organizations indicated that major constraints remained that affected the agility and effectiveness of emergency operations. Further guidance on DOA implementation in the Global Management System (GMS) was released in line with the WHO transformation agenda to streamline the process and harmonize approval levels across major offices. Following the WHO transformation, new delegation of authorities for RDs, WHE ED, ADGs, WRs, Directors and Unit Heads have been developed of the WHO transformation, revised DOAs are being developed for the 3 levels. This include a higher level of delegation below the RDs and the ADGs to facilitate operations. New organigrams at HQ and the regions have been issued to also reduce the number of reporting lines. KPIs for the centralized functions are being developed and a monitoring framework is expected to be finalized by the middle of April 2021. Each centralized function will be expected to maintain effective tracking for the key processes that have undergone centralization, for reporting on at least a 6-monthly period. The DOA for Emergencies is published in eManual XVII.2.3. It sepcifies "The delegation is valid as per the criteria to activate the SOPs for Emergencies (as listed in section XVII.2.2 of the WHO e-Manual), starting from the date of the grading decision, and ending when the grading decision is removed or ends. For Protracted Grade 1 and 2, the SOPs for Emergencies only apply during the first 12 months following the grading decision, unless otherwise extended by the EXD. The DOA for Special Emergency Procedures during a "disaster situation" is contained in the overall DOA issued to each WR. Under the DOA, special administrative policies and procedures may be used by the head of the WHO office or responsible officer, including the IM (WHO E-Manual XVII.2.3DOA) Pre deployment, IMS learning and SOPs have been developed. Surge capacity are expected to complete the learning opportunities as part of their placement on the rosters or, at the time of their deployment, if they are not part of the rosters. Since 2016, face-to-face training workshops have been conducted regularly with major ROs, mainly targeting the administrative staff and programme managers. SOPs for Emergencies is also an integral part of WR orientation every year. A standard set of training materials for SOPs for emergencies have been developed, including online training module at OpenWHO.org as a part of pre-deployment training. With the evolvement of COVID-19, further development of online packages is under way.
Structure | To adapt the IMS principles and approaches to WHO’s mission and structure, iteratively improving and systematizing WHO’s approach over time. To use IMS for acute emergencies and focus on surge of staff and partners in humanitarian crisis settings. | A72/6, A70/8, EB140/8. | Target achieved, progress continuing | In line with the ERF, all high graded emergencies have been managed through WHO’s IMS to fulfil its six critical functions (Leadership, Coordination, Information and Planning, Health Operations, Operations Support & Logistics, Finance & Administration). At country level, setting up an IMS was achieved within 72 hours in 63% (100%) of events in 2017 (2018). WHO continuously reviews the implementation of IMS principles as laid down in both the ERF and the emergency SOPs. Operational reviews are regularly conducted and inform areas that require adaptation and/or improvement. WHO is incorporating recent lessons learned into the third edition of the ERF . External partners and networks - e.g. from GOARN, GHC, or the Standby Partnership arrangement - have been used where feasible and appropriate to strengthen and/or complement IMS. The relationship between Cluster and IMS has been examined by several reviews to streamline the coordination mechanism in humanitarian settings where both health cluster and incident management work side by side. The evaluation recommendations how the Health Cluster best engages with the response pillars will be incorporated in the next revision of the ERF.
Structure | WHE surge: To strengthen technical expertise across the organization and develop a policy for surge capacity (especially as regards health operations leads, senior epidemiologists and infectious disease specialists) that authorizes the release of technical expertise within the organization at all levels, leveraging in-house expertise and partners on the ground. To clarify and adapt reporting lines and performance management of staff deployed as surge capacity. | A73/10, Interim Report 2020, EB146/16, A72/6, EB144/8. | In progress | The IOAC was informed that a global surge policy is in the final stage of revision and will be presented to the Global Policy Group for decision. Staff are expected to attend on-arrival briefing which includes briefing with supervisor on reporting lines and objectives that form part of the performance evaluation process. There is an ongoing initiative to ensure performance evaluations are shared with HR Emergency team for roster management. " In terms of reporting lines, it is imperative that the joint accountability and close collaboration of the RDs and the WHE ED be ensured, with dual reporting lines to them for REDs and relevant staff across three levels.
HR | Ensure a baseline of staffing capacity is present in country offices (including HCC and IMO posts and senior staff, e.g. deputy WR when WR assumes IM role), with a particular focus on priority countries (e.g. fragile states). Ensuring WR engagement in decisions re. WHE CO staffing and that all necessary functions should have the needed capacity (e.g. administration, HR, finance, emergency response, operational partnerships and procurement). The recruitment process should not be held back by the transformation agenda and staffing capacity should be at least 75% of the total planned positions. | Monitoring Framework 3/21, A73/10, EB146/16, A72/6, EB144/8, EB142/8, A70/8, EB140/8. | In progress | The IOAC observes that WHO CO capacity for emergencies has been strengthened in the priority countries. However, a survey of WRs found that they believe the workforce at country level to be spread thin and that the COVID-19 pandemic has shown that the country business model needs to be revised. Re. HCCs, as of 1 March 2021, 26 out of 31 (83%) health clusters/sectors have a dedicated Health Cluster Coordinator at national level, which did not meet the 2020 PB target indicator of 100%. Five clusters (16%) have part-time/double hatting national level coordinators. Stagnation in the number of dedicated HCCs persists due to previously cited bottlenecks including insufficient funding to implement the WHE Country Business Plans and delayed recruitment process. As of December 2019, 73% of planned positions at country level were occupied. Further, The WHE Programme’s dedicated human resources team managed to issue consultancy contracts within 24 hours for emergencies, and temporary staff contracts in seven days for emergencies. Under the transformation agenda, the WHE Programme HR function was centralized and SOPs are being redeveloped. Although there is a team designated to support emergencies in the HR Department, the WHE Programme perceives that HR processes have become lengthier and more cumbersome, with additional layers of review for recruitment. The IOAC has found that little progress has been made in the staffing of health cluster positions over the last four years.
HR | CO Capacity Building: To invest in and support national staff, including the training of WRs for emergency response. To enable and encourage WRs to effectively engage with in-country donors. | Monitoring Framework 3/21, A70/8, EB140/8. | Fully implemented | As 2020 began, with the outbreak of COVID-19 in China, WHE’s Learning and Capacity Building Unit initiated its health response training package and launched the first course – An introduction to the Novel Corona Virus (now renamed COVID-19). Since then four other courses have been launched: eProtect (occupational health and safety course for responders); Infection Prevention and Control; Severe Acute Respiratory Infections and National Preparedness planning for UN country teams. By March 2021, more than 500,000 people from 190 countries were accessing COVID-19 courses on the platform. It is important to note that the OpenWHO platform was established following the West Africa Ebola outbreak when WHO led the training response and is therefore a concrete example of WHO transformation of its health emergencies work. Secondly, the seed money for the platform was provided by Pandemic Influenza Preparedness Framework, and the team designed the platform to operate in a pandemic such as the one we are currently experiencing. The use of innovative technologies and approaches also means that the WHE Learning and Capacity Building team was able to fully shift into distance work and telework within 4 hours, with not only continuity of production, but a massive and continuing expansion. Re. Investing in national staff: The recently revised policy on NPOs who apply for international professional positions will contribute to the professional growth and career of national staff. Re. training of WRs for emergency response: In 2018 WHE developed a Learning Strategy and created a Learning and Capacity Development Team which has prioritized the development of flagship training based on the Incident Management System (IMS). The first training and table-top exercise conducted by the LCD team was in December 2018 for the WHO Heads of COs in WHO HQ. Over the period 2016 – 2020: A total of 236 staff have received face to face training on emergencies in pre-deployment training and Leadership in Emergencies training. A further 1450 WHO staff have completed on-line training on IMS, Tier 1 and Tier 2 hosted on OpenWHO. In 2019 the online IMS training was made mandatory for deploying staff and colleagues from partner organizations amounting into a total of 25 000 enrolment in the courses in 6 UN languages and Portuguese. Since its formation in October 2018 LCD provided training in Leadership in emergencies and IMS training workshops to 75 staff across all regions. The LCD is currently engaging with colleagues in AFRO, EMRO, EURO and WPRO to extend IMS and Leadership in Emergencies Training in these regions. Training will largely be delivered remotely online. This will involve the enrolment of a further 50 colleagues from Eastern Mediterranean and further cohorts from the African region. It is anticipated that this programme will be rolled out across all regions in 2020 and 2021. The programme including the face to face components will be transformed online through virtual interactive classes, virtual learning labs, webinars and virtual simulation exercises by the end of 2021 to address the challenges posed by the COVID-19 pandemic, as well as to scale up the number of users worldwide. Re. WR engagement with in-country donors: From 2020, under the new Global RM Strategy there is focus on RM and external relations capacity building in country. WRs receive training in donor engagement and RM on appointment as part of their induction course.
HR | Rosters: To increase the supply of a diverse pool of competent staff to lead emergencies, further develop IM rosters and create deputy IM posts that are preferably filled by under-represented suitably skilled groups. To expand the recruitment pool rather than limiting to internal WHO staff and to explore flexible contractual arrangements and roster arrangements for emergencies. Endeavour to find candidates with the skill sets that match specific country needs, to developing an internal roster system for potential health cluster coordinators and information management officers, and to upgrade the training, orientation and empowerment of health cluster coordinators. | Monitoring Framework 3/21, A73/10, EB146/16, A71/5, EB142/8, A70/8. | Fully implemented | Re. internal capacity to lead emergencies - completed: Regions are now identifying and deploying competent staff to lead emergencies for extended periods. Internal and external rosters of IMs are in place. Re, external capacity to lead emergencies - ongoing: External, partner rosters in place to support requests for external surge capacity. In addition for specialized functions, technical leads recommend external expertise for recruitment. Roster arrangements have been developed for emergencies. To support the Global Health Emergencies Workforce, the Learning Unit is supporting WHE in AFRO to create a regional pool of pre-identified and screened health response personnel from Member States, ensure they undergo a standard core learning package and be available for work within their countries as well as deploy internationally. This work will provide valuable lessons for the operationalization of the DGH’s Global Health Emergency Workforce. The GHC continues to work closely with WHE HQ-HR to develop the WHE HCC rosters and with the Standby Partnerships team to deploy suitable candidates to fill outstanding HCC gaps. At the time of reporting, country clusters currently ‘at risk’ are Burundi, Cameroon, CAR, Colombia, Ethiopia, Whole of Syria, Turkey and Zimbabwe due to double-hatting or imminent transition of HCCs. HCC roster candidates are selected through WHO's virtual interview process with candidates assessed against a set of technical and competency based questions set by the Global Health Cluster reflecting the essential requirements for Health Cluster Coordination core functions. Candidates selected for the roster must complete the Health Cluster Coordination E-learning course before committing to an HCC contract. The GHC provides pre-deployment technical briefings. Once deployed, HCC performance management is overseen by first and second level supervisors (respectively Head of CO & Regional Emergency Program Manager) as per WHO HR policy. The GHC provides remote support to all HCCs through regular thematic webinars and individual support to enhance knowledge and application of sector policy and guidance. GHC support missions are undertaken at the request of CO or RO to address HCC performance issues.
HR | Career progression: To establish a promotion system that rewards high-performing staff and motivates others. The IOAC considers that special consideration should be given to the recruitment and career progression of staff working at extreme hardship duty stations. | Monitoring Framework 3/21, A73/10, EB146/16, A72/6. | In progress | A promotion system for rewarding and motivating staff has not yet been implemented. The policy on Recognizing Excellence recognizes staff members who have made an exceptional achievement and they are awarded certificates, medals and pins together with three days special leave. The policy does not make provision to 'promote' staff members and this has to be taken forward in the context of the UN system HLCM. WHE is working with HRD to pilot incentives to encourage staff to take positions in hardship duty stations, including one grade increase and conversion from temporary to fixed-term positions. Within the overall context of WHO Transformation Implementation, WHE will work closely with the Business Operations Pillar (largely composed of the previous GMG) in this area.
HR | Recruitment strategy and planning: The capacity for HR planning, recruitment and management should be evaluated in order to deliver improvements. A longer-term recruitment strategy should be developed which can attract, orient and support the best candidates. | A73/10, EB142/8, A70/8. | In progress | Each Incident Management Support Team at HQ, RO and CO is capacitated with technical and administrative support required for these actions. The three-levels of the organization work together to ensure this support is available where gaps are identified during an emergency.
HR | 3 levels staffing balance: To identify trade-offs within a more limited staffing footprint, and reconsider the balance of HQ, RO, and field staff, without jeopardizing the operational capacity for emergency management. To recruit greater numbers of national staff with fewer international positions in COs . | EB146/16, A70.8, EB140/8. | In progress | WHE has strengthened significantly and prioritized RO and CO as part of the roll-out of the programme, ensuring that flexible funding is primarily transferred out of HQ. Additional work has been done as part of the WHO Transformation to identify functions which could be further decentralized, however delays have been faced due to the COVID-19 response. This progress should be reviewed and addressed through the upcoming mobility policy and the new country model initiative within the broader transformation agenda.
HR | Staffing gaps and rates: The IOAC recommends that WHO identify staffing gaps and provide flexibility to minimize the disruption during the transitional period. Aim to improve on the recruitment rate: HQ 70%, RO 50%, CO 35% position filled as of Dec 2016. | Monitoring Framework 3/21, EB146/16, A70/8, EB140/8. | In progress | Current staffing gaps should be determined, however, as of Dec 2019, positions filled stood at HQ 76%, RO 67%, CO 73%. The onset of the COVID-19 pandemic has led to fast-paced recruitments of additional functions which were needed. Further progression in the recruitment of a stable workforce has been slowed due to the lack of funding and focus put on current emergency response of key staff involved in recruitment - there are currently 1206 core positions filled in the WHE, distributed as follow: 53% country offices, 24% regional offices and 23% WHO Headquarters. The model is also being reviewed in the context of the COVID-19 response to ensure fit for purpose for the future.
HR | To increase HR capacity and staff trained in emergency response at the country level. | EB146/16, A72/6. | In progress | EURO: Completed. All CBM positions are in place. In addition to Turkey and Ukraine, EURO has CBM positions also in other 13 vulnerable countries, for a total of 33 positions. EURO has updated/corrected the CBM positions. WPRO: There is only one Priority 2 country which is the Pacific Island Countries (PIC) while there are 8 countries listed under Priority 3 countries (these are countries with WHO CO presence such as Cambodia, China, Lao PDR, Malaysia, Mongolia, Papua New Guinea, Philippines and Vietnam). Since the transition to WHE, WPRO has adapted the Country Business Model concept applicable for the Western Pacific Region context based on the following considerations: (1) Addressing the expectations of Members States building on past experience and lessons learnt; (2) Aligning with past staffing levels; and (3) Differing country capacities and context.From the initial 44 health security and emergencies positions in countries in 2017, additional 6 new positions under WHE were created in 2018 (3 in PIC and 1 each in PHL, PNG and SLB). These additional positions are considered core positions and funded by WHE flexible funding. There were also few projected-funded positions that were created in 2019 in PIC and LAO for a limited-time duration. EMRO: In process. While HR is indeed giving high priority to its WCOs the CBM is not fully applied in all countries. More feedback could be provided by WHE on implementation of the CBM to enable HR conduct a more precise assessment. SEARO: In process: Some countries have been able to roll out the CBM (e.g. Bangladesh / Cox's Bazar has funding to achieve this), however, this has not been possible across the region due to unpredictable and insufficient WHE AC flexible funding. AFRO - Completed. In the context of CBM implementation, countries in AFRO were put in 4 categories, 1 and 2 being for the most fragile countries. These countries were prioritized in the recruitment of 10 WHE senior staff such as Health Cluster Coordinators and WHE Team Leads.
HR | To complete the recruitment to fill the dedicated full time HCC and IMO posts at country level and ensure satisfactory information management and coordination. | Monitoring Framework 3/21, A72/6, EB144/8. | In progress | Since the inception of the WHE program, substantial investment has been made to secure dedicated full time HCC and IMO capacity to enhance health cluster performance. Securing IMOs continues to be challenging. As of 1 March 2021, only 17 out 31 (52%) health clusters/sectors have a dedicated IMO, a slight increase since the previous reporting period (53%). Most clusters continue to have dedicated IMOs hired on short term contacts linked to event-based funding or deployed through Standby Partners. Nine clusters (29%) have part time/double hatting IMOs and 2 clusters have no IMO. Whilst progress on recruitment and retention of HCCs and IMO has been positively acknowledged by internal and external stakeholders it should also be noted that progress on both HCCs and IMOs has plateaued over the last 2 years. Whilst this is partly due to anticipated staff turnover, structural aspects also play a significant role including (1) changes in the country business plan model with appears less enabling of funding HCC and IMO functions resulting in increased hiring against short-term contracts linked to event based funding or use of short-term standby partner capacity (2) protracted recruitment.
HR | Hardship: WHO to develop incentives and appropriate leave policies specifically for staff working in emergencies, taking into consideration increased workload and also need for support and protection from workplace harassment. The need to review the degree of hardship in offices is also recognised (e.g. those in cross-border posts) and to implement a staff rotation policy for hardship duty stations. | Monitoring Framework 3/21, A73/10, EB146/16, A70/8, EB140/8 | In progress | WHO is currently working with ICSC on a package of entitlements. Corporate compensatory leave policies have been developed for staff on duty travel and those working in their duty stations on emergencies for extended periods of time. In addition, some duty stations also introduce compressed work schedules and time off for national staff. To protect agains workplace harassment, Staff Health and Wellbeing (SHW) is regularly offering briefings to staff being deployed to regions and countries, including in emergency response settings. More than 90% of WHE staff completed the mandatory training covering WHO’s policy for prevention of and response to sexual harassment, sexual exploitation and abuse. The consequences of non-compliance are followed based on WHO Mandatory Training Policy within annual performance management cycle. This policy is also included in the draft WHE Global Surge Policy and is integrated into the revised ERF. All REDs and IMs were briefed in 2020 to ensure that PSEA function is reflected in ongoing and future operations. When alerted about specific cases, SHW take action to help address the situation, in collaboration with the relevant parties at HQ or at the regional and country level.
HR | To conduct an HR benchmarking exercise focused on incentives, and appropriate R&R in emergency settings against those of peer UN agencies and development organizations working in emergencies that have good systems in place for talent acquisition and management. | A73/10, EB146/16, A71/5, EB142/8, EB140/8, A70/8. | In progress | Talent acquisition, retention and performance management are still a cause for concern and need to be strengthened. HR incentives and R&R are monitored at the country level and recommendations made in accordance with ICSC guidelines. In addition, adjustments are made during specific response events, following consultation amongst the agencies. Feedback suggested that the term 'HR benchmarking' is quite vague and touches all the different HR functions ranging from recruitment and selection to retirement. In TAD, no benchmarking exercise has been conducted until now in areas of staff learning and development and performance management. However, it is worth highlighting that the JIU has produced a report on "Policies and platforms in support of learning: towards more coherence, coordination and convergence" after a survey they carried out across the UN System. They have made recommendations based on their findings and the report will be submitted to the Global Learning and Development Committee (GLDC).
HR | The IOAC stresses that ensuring that the WHE Programme operations are transparent and free of collusion, fraud and corruption, is of paramount importance. The IOAC also notes that the investigation into the allegations of corruption in Yemen has yet to be completed, while the reputation of the Programme staff cited in those allegations remains seriously compromised. | A73/10. | In progress
HR | To conduct annual or biennial staff culture survey and support the DG’s plan to undertake a similar survey on a regular basis and pulse surveys at regular intervals. To develop an action plan for implementing improvements against the outcomes of the survey, and that performance on this plan be reported within the IOAC reporting framework by WHE Programme leadership. | A72/6. | In progress | Culture/Pulse check surveys were conducted. Culture survey results are here: https://intranet.who.int/sites/transformation/culture/surveys/ Link to the pulse check survey results: https://intranet.who.int/sites/transformation/pulse.shtml Action plan - not started.
HR | The IOAC welcomes the organization’s efforts to improve diversity and recommends using the WHE Programme as a pilot for the organization in this regard. Work should take into account the socioeconomic and gender-related implications of preparing for, responding to, and recovering from public health emergencies and their interventions, by establishing a small dedicated team of social scientists and gender equality experts within the WHE Programme, guided by an external advisory group or expert network. | Monitoring Framework 3/21, A73/10, A72/6. | Target achieved, progress continuing | The IOAC is pleased to see the improvement in human resources diversity of the WHE Programme but concerned that little progress has since been made with the organizational policy and systems. WHE has launched a Gender Working Group to strengthen gender-inclusive/sensitive/responsive preparedness and response measures both in terms of MS capacities and within the WHE Programme. The Working Group activities include reviews of existing guidance, tools and frameworks to enhance gender-inclusivity and strategic partner engagement to advance gender mainstreaming in all measures for emergency preparedness and response.
HR | To develop a system of performance management that includes 360-degree feedback and introduces the element of assessing how outcomes have been achieved. | EB146/16, A72/6. | In progress | WHO is in the process of launching an RFP to replace the present performance evaluation system and will be looking into the introduction of a 360 degree feedback and a mobile applications functionalities.
Staff Protection | WHO to invest in its own security function across the field, COs, ROs and HQ to make it robust, appropriately and flexibly funded, accessible, responsive and able to deliver in hostile and insecure environments. | A73/10, EB146/16, A72/6, A70/8. | In progress | Inclusion of security requirements in budgets and cost estimates for emergency responses is being ensured with the engagement of security services from the onset and planning phase of all emergency response activities. Security costs are primarily covered through UNDSS, which are funded through POC (corporate funding) within SP4 budget. Response-specific security costs are included in appeals and funded through VC. The recruitment of security staff at HQ and in WHO is conducted in synergy with existing resources, especially with UNDSS, and the WHO transformation guidelines. The development of a Corporate Security Strategy is planned to be initiated during the scheduled WHO Security Network Workshop this year and to be finalized following the assumption of a full time Head of Global Security (also towards the end of this year). However, during its field visits, the IOAC noted serious gaps in WHO security capacity and management as well as in staff protection measures. It is unclear how WHO security functions in terms of line reporting, accountability and coordination across field, country and regional offices and WHO headquarters.
Staff Protection | WHO to implement security procedures and strategy in field settings for acute emergencies, outbreaks and protracted crises. WHO should be prepared to support staff and protect them when working in areas with limited infrastructure and increased security risk. Systematic risk assessments combined with preventative measures should be used to mitigate risk. | EB146/16, EB144/8, A71/5, EB142/8, A70/8, EB140/8. | In progress | The current framework of accountability is found in the existing WHO Staff Security Policy included in the WHO Manual. This is to be updated and enhanced at the scheduled WHO Security Network Workshop in synchrony with the development of the Corporate Security Strategy. Security Risk Management at all levels are done in collaboration with the UNSMS. To ensure availability, applicability and responsiveness, the WHO Security Focal Point and the unit engages where necessary from the field level (Area and Security Cells and Management Teams) to the HQ Level through the Inter-Agency Security Management Network An interagency working group for MEDEVAC linked to COVID-19 has been established. The task force is led by UNDOS, with support from WHO and other UN agencies. Under the leadership of the COVID-19 Global MEDEVAC Task Force, WHO established a joint operations center in WHO HQs, leveraging the combined resources of organization, UNDOS, and WFP, to provide 24/7 access to air medical support for UN staff and their eligible dependents. As of 22 February 2021, the joint operations center has completed more than 225 medical evacuation cases from over 50 countries. At the request of the task force, WHO also established a regional COVID-19 medevac treatment facility for UN staff and their dependents in Accra, Ghana. With support from WFP and a WHO contracted clinical care provider (CADG/AMI), the facility opened in early June 2020 with 68 beds and the capacity to deliver the full spectrum of care and support required for high-dependency and intensive hospital care. There is an ongoing discussion on a joint approach with UNDSS and partners should there be a need to set up a specific staff security system in area with weak National security capacity.
Staff Protection | The IOAC recognizes the provision by medical services of psychological support to the staff working in the DRC on the Ebola crisis and recommends that this practice should be institutionalized for other emergencies. MS are encouraged to guide the WHO Secretariat to improve the well-being and satisfaction of staff across the globe. | EB146/16, A72/6. | In progress
Staff protection | To clarify and simplify the various elements of the grievance and redress system to increase staff trust in the mechanisms, and make them more responsive. The WHE Programme senior management should ensure that effective staff welfare and protection measures are in place in the field and at all levels of the organization, and make them accessible and responsive. | EB146/16, A72/6. | Fully implemented | The organization has reformed its internal justice system to allow for the resolution of formal grievances/appeals under strict timelines. Further, the organization has increased resources for the informal resolution of disputes which has been effective in addressing matters before they escalate. The organization has also invested in regular trainings for staff at all levels, including through orientation training of new staff, so that dispute resolution mechanisms are widely known.
Coordination/ Management | The ERF should further clarify the roles and specific responsibilities of each office embedded in the WHE programme and reinforce institutional measures required for rigorous compliance therewith, providing a single line of authority in case of disagreement. Both the RDs and the WHE ED share accountability for infectious hazard events and other health emergencies with potential to spread internationally. They share responsibility for day-to-day management of those events. The roles, responsibilities and accountabilities of each player and updated processes for all-hazards emergency risk management should be enshrined in the ERF. | A73/10, A71/5. | In progress | All risk assessment and grading processes are three level decisions recorded in EMS2. At the grading call, the three levels will discuss the most appropriate operational setup, including roles and responsibilities of CO, RO and HQ. The traditional roles assigned by ERF - G1 led by CO, G2 led by RO, G3 led by HQ - have been gradually replaced by a more dynamic model where key functions are assigned to major offices according to capacity and needs. This model has been discussed as part of the ERF review and will be incorporated in more detail in ERF3. Following on from a review process which started in 2019, the ERF has been revised in light of recent experiences with acute event response, and recommendations from the IOAC. The review process included inputs from all major WHO offices and provided critical feedback on all aspects of the ERF – ranging from minor clarifications in the text to substantial additions of new topics. The process was delayed due to COVID, but resumed in late 2020. The revised ERF contains updates to the following areas, which will be discussed with the GPG ahead of WHA 2021: • Risk assessment • Grading • Accountability clarified • IMS functions reviewed and updated • Performance standards updated • Emergency procedures updated in line with proposed changes • New section on Prevention of Sexual Exploitation, Abuse and Harassment • New section on Risk management and compliance • New section on responding to vaccine preventable outbreaks • Updated and expanded section on protracted emergency response. • Checklist for accessing the CFE
Coordination/ Management | To improve the agility and flexibility of the WHE Programme through an appropriate level of autonomy and authority based on the principle of a single structure, single budget, single staff workplan and common results framework across WHO headquarters and all regional offices. Managerial responsibility of the WHE Programme rests with its Executive Director, who reports directly to the Director-General. Regional Emergency Directors should have delegated authority for emergency management in their respective regions and report directly to the Regional Directors and the WHE Programme Executive Director. The IOAC emphasizes the importance of close collaboration and coordination between the WHE Programme Executive Director and the Regional Directors for major emergencies management and recruitment of key senior staff such as the Regional Emergency Directors to ensure coherent work as “One Programme”. | A73/10, EB146/16, A72/6. | In progress | The IOAC cautions WHO to find the right balance between autonomy and integration of the WHE Programme and make the required institutional arrangements to safeguard the WHE Programme’s managerial authority and autonomy against politicization.
Coordination/ Management | Centralization: The IOAC recommends that transitional steps be taken to ensure that the centralized corporate structure does not dilute the particular and immediate needs of emergency operations and risk mitigation. To provide for this, there is a need to put in place dedicated teams within the centralized functional divisions to support emergencies, with a dual reporting line to the WHE Programme and respective division heads. Key performance indicators will need to be established to track these critical enabling functions, such as communications, resource mobilization, procurement, security and HR, to ensure that their effectiveness is maintained and improved. Further, a time-limited working group dedicated to addressing major issues for streamlining administrative and operational systems in an emergency response should be created. | A73/10, Interim Report 2020, EB146/16, A72/6, A70/8. | In progress | The transformation agenda acknowledged the urgent need to improve the administrative system and business processes that underlie WHO’s emergency work. It has sought to find solutions at a corporate level by centralizing critical enabling functions, such as communications, resource mobilization, human resources, procurement and security, as well as by consolidating structures across the Organization. The IOAC cautions that such centralization could dilute the WHE Programme’s distinctive functions and agile business processes. The IOAC observes that the incident management support team is overstretched due to the huge demand generated by the pandemic. The IOAC recommends that Member States and the WHO Secretariat revisit the size and surge capacity of the WHE Programme to ensure sufficient capacity, resilience and flexibility within and beyond the incident management system to respond adequately to such multidimensional and large-scale emergencies, alongside the increasing number of graded emergencies that it routinely manages. The working group mentioned is not started yet. This will be addressed as part of the Business Process Optimization of the new ERP project which is planned to take place over the next two years.
Coordination/ Management | Incident Management: To build a critical mass of qualified WRs and IMs through rosters and training and linkage. To hold the WR accountable for the performance of the IM and to engage IMs on longer-term contracts. IM should have a direct line to the WHE/EXD to ensure appropriate technical and operational oversight and should also be given greater authority, particularly in relation to recruitment, procurement and finance. For that reason, IMs should have the appropriate profile and experience in order to lead effectively, and in addition, be properly empowered and supported to carry out their role. This support should entail being released from other duties and assignments for an extended period, as required. Additionally, WRs should also be further empowered and supported in their roles. | Monitoring Framework 3/21, A70/8, EB140/8. | Fully implemented | Qualified WRs and WR candidates are members of a global roster, managed by the HR Department. Training is under development (August 2020) to guide candidates about the skills and competencies required to be a successful WR, before they apply to the global roster. Further learning and development opportunities are made available to roster members when they meet for global or Regional WR meetings. The global roster is updated every quarter. WHE has launched a new IMS Leadership training programme to identify and train staff with demonstrated or potential leadership abilities in order to perform key leadership roles under IMS. The first-ever IMS Leadership Training has taken place in April 2019 in Dakar, Senegal, with 28 participants that included IMs and IMS Operations Leads. A second training has been completed in EMRO in November 2019. A Phase II Leadership in Emergencies training which concentrates on developing individual leadership, negotiation and teamwork skills. This face-to-face training was delivered online using Open WHO and Zoom technology. It was piloted with 28 learners drawn from the Eastern-Mediterranean, Americas and Western Pacific Region and HQ Contractually, senior staff are released from other duties and assigned for extended periods to support events. As per established process under the ERF, HWO/WR supervises the IM directly, unless alternate arrangements are agreed by the WHE ED and RD. Regarding granting IM's greater authority, the DOA for emergencies outlined in eManual XVII.2.3 granted delegations to IMs in the area of recruitment, procurement and finance for acute emergencies, including development and management of workplan, approval of selection of temporary staff, consultants and deployment, approval of up to USD 500,000 for procurement of catalogue items, request reallocation of funding, etc.
Coordination/ Management | IHR should be reviewed by MS in the light of the COVID-19 pandemic to ensure that the attribution of authority and roles outlined under the Regulations are in alignment with MS’ understanding and expectations. This may entail revisiting the roles and responsibilities of the WHO secretariat and the duties of MS. | A73/10, Interim report 2020. | In progress | The WHO secretariat’s response to COVID-19 was faster than for either the MERS or SARS epidemics, but this did not prompt similarly rapid action by all MS. Evidence collected from the IOAC desk review indicates that the initial process of providing information about the new virus was conducted within the parameters established under the IHR.
Leadership | WHO to document its work under the 'Whole of Syria' approach – an operational approach to a complex humanitarian and health crisis – to inform future responses. | EB146/16. | In progress
Leadership | WHO’s Emergency Response Framework (ERF) should be consistently followed by staff at all levels of the Organization. | A73/10, A71/5. | In progress | Adherence to the ERF has been increasingly consistent in major emergencies and has enhanced coordination between the three levels of the Organization. ERF and the emergency SOPs are consistently applied across the Organization for the management of all acute events, regardless of hazard or cause. They form the basis of WHO's risk assessments and grading processes, implementation of response activities and evaluation of performance. Standard indicators are being collected in EMS2 and used to regularly review ERF. Training programs on ERF/IMT are being available on iLearn and OpenWHO; physical training courses have been held in major offices and many suboffices. Consistency and quality of ERF implementation is variable though, particularly when subject matter experts are expected to manage acute events because of the absence of a group/unit dedicated to acute event management and thus thoroughly familiar with this task. A standard set of training materials for SOPs for emergencies have been developed, including online training module at OpenWHO.org as a part of pre-deployment training. With the evolvement of COVID19, further development of online packages is under way. IOAC notes that while the Framework has proved effective in management of acute outbreaks, it requires further adaptation for protracted crises.
Leadership | To improve coordination among the departments of the WHE, across the three levels and to accelerate implementation of the WHE at country level. The IOAC emphasizes that WHO’s work in outbreaks and emergencies must be reflected in every aspect of the organization as a core part of its mandate and best practice leveraged across the organisation. Administrative support staff should be deployed at the beginning of an emergency activation in order to assist the team with its heavy field deployment demands and to navigate the business systems. During a response, a dedicated emergency administrative support officer should also sit in the CO to provide added capacity and facilitate support to the Programme. | A73/10, Interim Report, A70/8, EB140/8. | In progress | Coordination across WHO's three levels has improved. Nevertheless, the IOAC observes that the organizational culture and administrative system continue to resist change. The IOAC observes that graded emergencies are managed collectively and in a coordinated fashion across the three levels of the WHE Programme, regardless of the ERF classification. That is mainly due to the strong, cordial working relationships between the RDs and the WHE ED, and to a professional commitment by managers at all levels to being accountable to the populations they serve, MS, partners and donors. Significant improvement has been made in internal coordination mechanisms, management structures and decision-making processes. However, ambiguity remains in the ERF and in the implementation of shared accountability, roles and responsibilities, delegation of authorities and reporting lines between the DG, RDs, WHE ED, REDs, WRs, and IMs. The WHE Programme has strengthened COs and helped ROs to play a stronger role in coordinating regional platforms and in providing important insights into the geopolitical issues in the respective regions that impact WHO’s emergency response.
Leadership | The IOAC emphasizes that the quality assurance of laboratory testing and timely analysis of genetic sequencing data are critical to fully characterize the evolution of the EVD outbreak in order to inform diagnostic, vaccine and treatment approaches and recommends closer collaboration between INRB and WHO. However, WHO should leverage experiences from the DRC and Uganda to fast track approvals for the administration of investigational vaccines and therapeutics and their deployment. WHO should enhance mentorship, training and supervision to ensure capacity to make this happen. | Monitoring Framework 3/21, A72/6, EB144/8. | In progress | The GeneXpert technology was used in DRC to allow rapid diagnostic field capacity: >13,555 samples tested.
Leadership | Further improvement is required in terms of accountability to, and coordination with, the WHE Programme, the External Relations Division and the rest of the organization at all three levels, to maximize available resources and ensure consistent messaging for major emergencies. This would involve improvement in both internal and external communications about the WHE Programme, especially with regard to the strategic vision, structure, function and deliverables of the WHE Programme. | Monitoring Framework 3/21, A73/10, EB142/8, A70/8. | In progress | External communication mechanisms and processes: Following the centralization of the communications function, there continues to be in the dept of communications (DCO) a fully dedicated emergencies team which works closely with WHE technical teams and other communicators at all three levels of the organization Since January 2020 the team has been augmented by surge staff (as have other teams in DCO) to communicate on the COVID-19 pandemic while still covering major G3 emergencies (such as the Ebola outbreak in the DRC, Syria, and Yemen). For priority countries facing a G3 emergency, a communications strategy is developed by CO and RO communicators with support from the emergencies team. CO communications officers are the main points of contact with MoH counterparts, either urging the ministry to communicate on a developing health issue (e.g. cholera in Zimbabwe), or jointly producing communication materials (e.g. DRC Ebola outbreak). WHO communicates on emergencies through the WHO country and regional web pages, social media accounts, and by reaching out to media directly. WHO also amplifies MS products, especially on joint actions (e.g. Uganda Ebola preparedness). The principles of risk communication are integrated into all communication, and emergency communications media colleagues will reach out to MS to urge them to follow these principles, such as to flag when their health messages that could be misinterpreted, or to urge transparency when a MS is hesitant to announce an outbreak. In country, health promotion officers work with ministries to develop mechanisms and materials for communicating with communities affected by emergencies. WHO regularly conducts communications training, including the Emergency Communications Network training that includes WHO staff at all three levels of the organization, and ministry communicators. For example, the training in April 2018 included the communications focal point from MoH DRC who became the lead communicator during the Ebola outbreak. Many joint webinars on risk management approach to emergencies and disasters, including COVID-19 have been conducted through 2020 and 2021 in collaboration with UNDRR, the IPU, International Hospitals Federation, Cities Resilience Network and others with outreach to many thousands of participants across sectors and levels of government around the world. Communications within WHE across the three levels: Communications across the three levels has been steadily improving. WHE Directors have annual face to face meetings to review key strategic, programmatic and managerial issues of relevance for the Global Programme. Key themes have included delivering on GPW 13, monitoring and measuring impact, inspirational and accountable leadership and health systems in fragile, conflict and vulnerable settings. In addition, there are monthly teleconferences across the three levels with all the emergency directors. The output networks also have regular video/tele conference and network meetings. The HQ Senior Management Team meets weekly for information sharing, problem solving, decision making and accountability. The office of the WHE ED regularly shares relevant information and documents with all staff in HQ and the ROs. The WHE ED holds quarterly meetings with all HQ staff and regular meetings with an enhanced Senior Management Team which includes all unit heads in addition to the rest of the management team.
Business Processes | To apply a fast track recruitment (in advance of funding if required) and shorten the recruitment process. | Monitoring Framework 3/21, A70/8. | Target achieved, progress continuing | Fast Track Procedures for Emergencies SOP published on 26 November 2016.However, these have not been systematically applied, as it was felt that the short announcement period did not allow the programme enough time to source qualified candidates, and there was a preference for temporary arrangements which were felt to be more rapid.
Business Processes | WHO should conduct a benchmarking analysis for and promote a 'no regrets' approach in the supply chain process. It should consider either: outsourcing the function to another provider within the UN system, such as UNICEF’s Supply Division, to enable the WHE programme to procure and effectively manage and deliver its emergency stocks; or making an investment case for the entire organization, establishing a central division of supply chain management, with clear objectives and accountabilities across the organization, upon which the WHE can build if additional capacity for emergencies is required. | Monitoring Framework 3/21, A73/10, A71/5, EB142/8. | In progress | The IOAC is encouraged to see that the WHE is heavily engaged in redesigning supply chain business processes to support health emergency responses in the context of the transformation agenda. The IOAC notes that the WHE established the COVID-19 Supply Chain Inter-Agency Coordination Cell, composed of staff from WHO, OCHA and the WFP, to help respond to the COVID-19 pandemic. It is also noted that two benchmarking exercises were performed; one in 2017 and one in late 2018. Certain key recommendations from this have been taken forward. In particular, increasing the number of LTA's for supplies, increasing catalogue offerings, expanding operations in Dubai hub, expanding stockpiles and implementing a data system. All but the last have see improvements, with data being a more general issue that needs to be considered in light of future corporate ERP requirements. The expansion of the Dubai hub from 4,000 sq meters of temperature controlled storage facilities to now more than 17,000 square meters was primarily funded through approximately USD 3 million in Funding from the Kuwait grant. In addition, discussions are being held with the WFP to develop operational service level agreements to capitalise on the strength of their logistical capability including Camp/Life Support, Surface Transport, Communications, Air Transport, and EOCs. OSL is also exploring additional operational partnerships and service level agreements with other UN agencies and implementing partners. As part of the WHO Transformation agenda, the GMG and departments across WHO including the WHE are collaborating on building a fit-for-purpose supply chain that will support WHO programmes and initiatives as well as provide the necessary supply chain support for health emergencies. Further, OSL has developed a periodic dashboard outlining several key indicators of the supply chain operations for the DRC response.
Business Processes | To streamline SOPs for emergency procurement: increase the expenditure limits in the delegation of authority, apply standard waivers in accordance with the DOA, systematize pre-qualified suppliers, simplify local contracts and payment processes, and fast track due diligence process as per the provision in the Framework of Engagement with Non-State Actors. | A70/8. | Fully implemented | A policy specific to Procurement for Emergencies was issued in 2017 and has been regularly updated since (available from eManual XVII.9.3.4). Delegation of Authority: Upon grading of an Emergency 1, 2, 3 or notification of pre-graded event, WR, IM or Technical Leader for Response are automatically granted procurement authority up to US$ 200k per PO (US$ 500k for catalogue items) against WHE and OCR workplans. Waivers: - Adjudication Report not required for purchases below US$25k. - Competitive bidding is not required and CRC approval before the award of the contract is not required. - When the Purchase Requisition cannot be submitted in time in GSM, the WR or the IM is authorized to send a signed emergency adjudication report and an off-line purchase requisition to Team Lead, SUP/GPL. Prequalified suppliers: WHO has a specific process to approve pre-selected supplier (manufacturers or distributors) according to the WHO Quality Assurance Policy for the procurement of essential medicines and other health products. In addition and for the purpose of streamlining emergency procurement further, significant efforts have been made to develop Emergency Health Kits (based on LTAs signed with approved pre-selected suppliers). Payments: WR or IM is authorized to approve advance payments up to US$50,000 for Grade 3 emergencies, and up to US$20,000 for Grade 1 and 2 emergencies. Due diligence process: When the Procurement Initiator possesses the relevant technical expertise, and provided the goods required are not available from the catalogue, they may be allowed to purchase items from the product categories that normally require involvement from the Quality Assurance technical network (Medicines, biological products, medical devices, etc.).
Business Processes | Expertise of the WHE Programme operations support and logistics team and the emergency management field experience should be leveraged within the transformation agenda and the effectiveness of operations should be maintained. | A72/6. | Fully implemented | The WHE programme operations support and logistics has transformed rapidly in the wake of the COVID-19 response. These changes have seen an expansion of the core team, the temporary restructuring of the group to sub units that cover demand, supply, logistics, operations support to the three inter-agency procurement consortia (diagnostics, PPE and Biomed) as well as establishing a technical support network to advise on the design and construction of treatment centres. The group also accommodated a COVID-19 coordination cell, including 17 staff from WFP, 4 from UNICEF, 1 from OCHA and 5 from CHAI. So far this construct has delivered $US 277 Million of supplies to 179 countries with the WHO procured component accounting for over 50% of the total.
Business Processes | To implement emergency measures under FENSA across the regions. | EB146/16, EB142/8. | In progress | New FENSA emergency processes have been rolled-out and supported by the PNA unit and a focal point in WHE HQ. Training has been made in some ROs to familiarize with these processes and additional ones are expected. The revision of the Guide for Staff and the Guide for NSA will better articulate these requirements. An online training on emergency SOPs will also incorporate FENSA provisions.
Business Processes | To caution when operating the new business rules within the existing systems. Business processes must support the WHE Programme based on a no-regrets approach. | EB140/8. | Target achieved, progress continuing | The no-regrets policy is fully integrated in the ERF second version and in the eManual. Its use showed great improvement for rapid deployment of the WHE response to emergencies (e.g. plague in Madagascar, diphtheria in Bangladesh, Ebola in DRC and COVID-19 response). However, many audits showed that this policy is too permissive, therefore it will be amended to include controls on its use.
Business Processes | To carry out further efforts to streamline the process and accelerate engagement to support critical emergency responses. | A72/6. | Target achieved, progress continuing | The continuous improvement activities to streamline core services process have been ongoing since 2016. Feedback has been taken from a variety of sources, including operational review of major emergencies, subject matter experts, ongoing basis during critical emergencies. This has resulted in continuous updating of eManual XVII, including templates and tools. An enhanced operational toolkit is also under development to serve as one-stop shop of emergency-related templates.
Risk assessment | To monitor the a. effectiveness of both ERF and EIOS, and b. track the ERF is properly implemented against the specific timeframes in 24hr, 72hr, 60days. | A70/8, EB140/8. | In progress | WHO monitors the effectiveness of the ERF through the collection of performance indicators for all graded responses which are recorded in vSHOC (now EMS2) and regularly evaluated. For larger events, operational reviews are conducted, which include recommendations for improving ERF. These lessons learned form the basis of discussion during the face-to-face IMS training courses and were also the starting point for the current ERF review. Roll out of EIOS is still ongoing and no formal evaluation has been conducted to date. Access to EIOS has so far been granted to 17 governments/national entities and 12 regional/international organizations, networks and academia. Performance indicators are captured in EMS for all graded emergencies as feasible. E.g in 2017 (2018), IMSTs were established at country level within 72 hrs in 63% (100%) of all G2-3 emergencies. Strategic response plans were developed with partners within 30 days in 71%, 56% and 65% of graded emergencies in 2017, 2018 and 2019 respectively. Experience over the last few years has shown that some of the time-bound indicators cannot be meaningfully applied to all types of events, particularly for acute infectious disease events (as opposed to events in humanitarian settings). As part of the ERF revision the indicators were revised to make them more applicable to all settings and it is planned to include them in the upcoming ERF3.
Risk assessment | To assess the effectiveness of the EMS and update the current systems. | A73/10, EB142/8, A70/8. | In progress | EMS is going through transformation allowing the seamless management and capturing of information from signal detection, verification, risk assessment to response and information dissemination. The transformation is guided by best practices on the use of EMS and event management jointly developed between different departments in HQ and the Regional Offices. This will increase data quality, reduce redundancies in data capture and work flow and integrate with other tools and systems like the Event Information Site and the Epidemic Intelligence from Open Sources system. One of the latest improvements has been the integration of EMS data in WHO's Health Emergencies Public dashboard to show outbreaks WHO is currently monitoring. WHE to make the Emergency Dashboard available to both the donor community and public audiences.
Risk assessment | To inform the governments concerned of grading decisions immediately prior to their announcement. | A70/8. | Fully implemented | Between 1 January and 30 June 2020, 311 events in 213 countries and territories were investigated, followed up and their risks assessed. Of these, 92% were infectious disease events, 5% were natural disasters related, and the remaining 3% were related to chemical, radiological or nuclear, products or food safety events. Formalized risk assessments were conducted for a total of 22 events, including 16 events in 12 countries and 6 risk assessments for the global COVID-19 pandemic. The top three events besides COVID-19 were EVD, cholera, and yellow fever. The risk at national level was assessed as very high or high for 73% of the 22 events.
IHR | CO IHR: Streamlining the IHR reporting process for COs and strengthening national capacity to report on IHR, including supporting countries to develop impact-oriented NAPs which prioritize short-term goals with timelines for implementation. | Monitoring Framework 3/21, EB146/16, A72/6, EB144/8, A71/5. | In progress | Re. Streamlining IHR reporting: • Data consolidation between COVID-19 Partners Platform and the SPH Portal to facilitate the mobilzation of financial and technical resources to ensure donor and partner coordination to address countries gaps and needs in preparedness capacities. • The GISRS capacity in countries on surveillance and detection, risk assessment and vaccination has been building up systematically. The capacity built through influenza preparedness has been institutionized and used immediately in countries for early detection and response to the COVID-19 pandemic. • WHO has developed the Strategic Tool for Assessing Risk (STAR) to support MS in assessing the priority risks and hazards in a country. • WHO has been focussing on sub-national level capacity building and is working on M&E tools to be used at subnational and community levels. • WHO has built capacities at the Human Animal Interface, conducting One Health National Bridging Workshops jointly with OIE, and has developed and is implementing the WHO-OIE-FAO Tripartite Operational Tool for conducting Joint Risk Assessment at the interface. • A technical working group on “Advancing health emergency preparedness in cities and urban settings in COVID-19 and beyond” is ongoing (February to April 2021). It will produce a technical guidance for national and local governments, partners, communities and other stakeholders in mid-2021. Pillar 2 of the five-year global strategic plan to improve public health preparedness and response (2018-2023) highlights the need to support and further strengthen the National IHR Focal points, notably through:community-of-practice related activities; and training initiatives to support workforce development of NFPs and IHR stakeholders. The health laboratory sector is a key IHR component and building the capacity and monitoring the performance of this sector is a high priority for PHE. Also, a number of laboratory proficiency testing programmes for diseases of high public health importance have been organized and the global level and support for regional level programmes has also been provided. A large-scale global programme for diagnosis of COVID-19 at the subnational level will take place in the coming months covering over 3,000 laboratories. Further, the PoE and border health program is supporting countries in enhancing capacities for public health preparedness, readiness and response at points of entry- international travel and transport, in an effort to minimize international spread of disease. Re. NAPs: Since 2016, 67 NAPHS have been completed (31 in AFRO, 19 in EMRO, 1 in EURO, 8 in SEARO, 7 in WPRO and 1 in PAHO). A NAPHS toolkit was developed to support the planning of priority actions and to cost those actions using national standards. The toolkit includes a WHO guidance on Benchmarks for IHR capacities to guide the planning process. The NAPHS Framework to support the health security planning in countries based on country risk profiles and capacity assessments was revised and published. In addition, a Country Implementation Guide to operationalize the NAPHS framework is finalized and will soon be published. A WHO guidance has been drafted to support countries to develop an all- hazards response plan to country emergencies.
IHR | IHR CO: To reinforce the pool of expertise across the organization and to allocate a core budget for supporting countries with transition activities following major events, with a view to building IHR core capacities in a more sustainable way. The secretariat should review existing tools and mechanisms in the light of COVID-19 and the lessons learned. In that regard, national leadership, a whole of government approach, subnational level capacity, and community empowerment and resilience should all be considered. | Monitoring Framework 3/21, A73/10, EB144/8. | In progress | • To ensure coordination and streamlining in strategic planning and implementation of transition efforts across the organization, WHE is part of several working groups with colleagues working on health systems: recovery working group; joint working group for fragile, conflict affected and vulnerable settings; joint working group on UHC. • WHE and health systems colleagues have developed a way forward paper to support continued joint action between teams involved in supporting countries to enhance health security preparedness and those involved in supporting countries to strengthen integrated health services. The paper maps ongoing and evolving joint work in the context of COVID-19 and beyond within the frame of longer-term preparedness and the resilience of health systems of MS. • WHE is working closely with health system teams to strengthen health systems for health security for preparedness, UHC and SDGs. WHE is also working with health systems on PHE indicators and as well resilience. • WHO published a guidance on “Investing in and building longer-term health emergency preparedness during the COVID-19 pandemic” which maps COVID-19 preparedness and response actions to the building of sustainable International Health Regulations (2005) core capacities; locates relevant supporting WHO resources that are not specific to the pandemic; and advocates for the conscious and effective allocation of COVID-19 funds to also meet countries’ longer-term needs
IHR | IHR CO: WHO is mandated to assist countries in making rational decisions, deploying effective measures to prevent public health emergencies and complying with the IHR requirements. | A71/5. | In progress | WHO, supported by partners including GISRS and other public health agencies, develops and routinely updates risk assessment and risk management recommendations on zoonotic influenza outbreaks; updates recommendations on seasonal influenza vaccines; and develops operational guidance for countries in using existing resources (influenza capacity) for surveillance of COVID-19. Operational guidelines are developed by WHO for readiness and preparedness for all emergencies which outline effective, priority interventions aligned with international strategies and IHR requirements in all public health pillars to guide countries in implementing sound, effective measures systematically. • The Secretariat has continued to implement a structured approach for monitoring States Parties’ compliance regarding additional health measures, in accordance with Article 43 of the Regulations, and has maintained a database of such measures. • In accordance with Article 43 of the IHR (2005), the Secretariat will continue to monitor systematically additional health measures in relation to public health events. The Secretariat is also exploring approaches for reporting and presenting such information to States Parties, including the details of actions by States Parties under Article 43. In order to better inform States Parties about the effectiveness of additional health measures, the Secretariat is drafting evidence-based guidelines on the effectiveness of travel measures in reducing international spread of infectious diseases. WHO has commissioned a Cochrane systematic review of evidence on the effect of travel measures during COVID-19 response. The review showed low quality of existing evidence, which is insufficient to inform evidence-based recommendations, but provides a basis to identify needs for future research. WHO has also provided a letter of support for Canadian Institute for Health Research Institute to conduct extensive research in the field of additional health measures, the results of which are expected in 2021. WHO continues to explore options to expand research in this critical field. • The Secretariat published the Guidance for Conducting a Country COVID-19 Intra-Action Review (IAR) and accompanying tools to guide countries to conduct periodic review(s) of their national and subnational COVID-19 response, so that countries do not miss critical opportunities for learning and improvement to better respond to the COVID-19 outbreak in their countries, especially as the possibility of a protracted pandemic becomes increasingly probable. This includes possible lessons-learned for implementing the IHR on the national level, e.g. through senior-level allocation of the National IHR Focal Point, monitoring of functions relevant to the IHR such as legislation, governance, financing, cross-sectoral ownership, etc. • The National Civil-Military Health Collaboration Framework for Strengthening Health Emergency Preparedness (NCF) was finalized in 2020 and will be piloted in countries in 2021. • The joint WHO-IPU handbook on Parliaments’ Role in Strengthening Health Security planning is to be published in 2021 and mapping of legislation at the subnational level that facilitate multisectoral preparedness coordination will be piloted in 2021.
IHR | IHR CO: To support countries in maintaining the level of preparedness and avoiding burnout after Ebola readiness efforts. | A72/6. | Fully implemented | WHO provided guidance and support for integrated preparedness with the rollout of the REMAP tool for countries to identify cross cutting preparedness capacities for highest assessed threats. WHO has developed the Partners Platform, where governments, UN agencies and partners can plan and coordinate/collaborate together in real time. The REMAP tool has been adapted for COVID-19 and along with the Partners Platform tracking of actions aligned with IHR capacities, allows countries to prepare for multiple threats with cross cutting actions for better efficiencies.
IHR | Funding preparedness: The IOAC cautions that investment in preparedness has been insufficient and the impact of WHO’s action on strengthening IHR core capacities is unclear. | A73/10, EB146/16. | In progress
IHR | JEE: IOAC cautions that the impact of JEEs and NAPHS on strengthening IHR core capacities is still unclear. The adequacy of tools to support country preparedness should be reviewed based on the lessons learned during the COVID-19 pandemic preparedness and response efforts, and improved under the guidance of the IHR Review Committee. The JEE tool should be suitable for its purpose, including its ability to assess: (i) capacity at the community level to alert and take early action, and (ii) the way in which strengthening community engagement is being built into core IHR capacity. | A73/10, EB146/16, EB140/8. | In progress | The IOAC interim report on WHO’s response to COVID-19 noted that the majority of countries appeared ill-prepared, indicating no clear relation between the JEE score and the actual country preparedness and response in the event of a pandemic of this scale and magnitude.This suggests that existing metrics for public health preparedness and health care capacity do not reflect the full range of variables that affect a country’s response during a severe pandemic on a massive scale. To improve this, a review of the current JEE process and tool will take place to address elements including assessment of capacities at sub-national levels and additional areas highlighted as critical capacities for a severe pandemic, as highlighted by COVID 19. Also, WHE has developed a guidance document for Urban preparedness during COVID 19 and beyond, that would guide early action for local authorities.
IHR | Countries should be supported with implementing corrective measures for critical areas of work identified in JEEs and after-action reviews. RO should support countries to share best practice and experience with JEE and NAP, and relevant community-based groups be systematically included in JEE processes to ensure that community-based surveillance and community early response systems are included in all evaluations. | Monitoring Framework 3/21, EB144/8, A70/8. | In progress | As of 12 March 2021, 113 countries have volunteered for a JEE; 150 Simulation exercises have been implemented (including country level and regional and global exercises) and 65 After Action Reviews have been conducted. 33 IHR-PVS National Bridging Workshops have been organized in MS countries to encourage the contribution of the veterinary sector in the implementation of the IHR (2005) and define One Health roadmaps for improved coordination at the human-animal interface. In addition, 57 countries have reported the conduct of COVID-19 Intra-Action reviews and a series of COVID-19 specific simulation packages have been developed and made available to MS since February 2020. • WHO continues to encourage and support the implementation of corrective measures by MS following an AAR or JEE. • Reports of AARs and IARs are published and shared with technical teams and stakeholders. • WHE is developing a global strategic preparedness network to support countries bridge their specific gaps, in partnership with national public health institutes to strengthen sustainability of preparedness actions in countries. • WHE published COVID-19 tabletop exercise (SimEx) packages to support countries’ preparedness effort on the COVID-19 outbreak. Those packages include COVID-19 TTX for health facility and IPC, Point of Entry and Urban settings. • WHE supported countries to integrate seasonal influenza programs and pandemic influenza planning into their NAP. • WHO has provided direct support to countries and has documented progress of national implementation of IHR Monitoring & Evaluation recommendations and NAPs missions in Lao PDR, Sierra Leone, Sri Lanka and Tanzania. • WHO has developed and published a guidance document on conducting JEEs and developing and implementation of NAPHS in special context countries, including countries in conflict. • Case studies have been collected to capture best practices, lessons learned and knowledge on the implementation of IHR capacities for health security and emergency preparedness for all hazards. A call was issued for COVID-19 related case examples, lessons and best practices in preparedness from all countries. • Review of the current JEE process and tools to include assessment of capacities at sub-national level using lessons learnt from COVID-19 pandemic, IAR and case studies.
IHR | The IOAC notes it may be opportune for MS to reassess WHO Secretariat’s role in providing travel advice during a pandemic. | Interim report 2020. | In progress
IHR | The IOAC considers it opportune to introduce a graded PHEIC system with clear criteria and practical implications for countries , under the guidance and based on the recommendations of the IHR Review Committee, to facilitate preparedness, preventive action, and dedication of resources at the early stage of outbreaks, which could avert any escalation. The PHEIC grading must be tied to a set of binding actions under the IHR provisions . | A73/10. | In progress
IHR | Post COVID-19, it would be useful to independently assess the organization’s performance during this response and identify lessons for the future. The scope of such an assessment should be determined by MS, and should cover both MS and WHO secretariat’s actions in response to the COVID-19 pandemic. The IOAC encourages MS to consider whether: a stepped level of alerts and galvanization of response measures should be added to the IHR; to enhance the openness and transparency of the Emergency Committee process; and to review whether the IHR-nominated focal points in governments are able to adequately raise the alarm to ministers within their governments when a PHEIC is declared. The IOAC would caution that conducting such a review during the heat of the response could disrupt WHO’s ability to respond effectively. | A73/10, Interim report 2020. | In progress | The IOAC notes that the design of the PHEIC is very broad, covering everything from a limited regional outbreak such as Ebola in West Africa to a large global pandemic that touches every country. While recognizing the progress made, the IOAC cautions that investment in preparedness has been insufficient and the impact of WHO’s action on strengthening IHR core capacities is unclear. The IOAC emphasizes that supporting MS in building IHR core capacities is one of the WHE Programme’s prime functions and the secretariat should review existing tools and mechanisms in the light of COVID-19 and the lessons learned. In that connection, national leadership, a whole of government approach, subnational level capacity, and community empowerment and resilience should all be considered.
Partnership | Demonstrate WHO’s leadership in the IASC for health and lead the committee during outbreaks. | Monitoring Framework 3/21, A73/10, A71/5, EB140/8. | Target achieved, progress continuing | WHO has established its leadership in health in the IASC and plays its leadership role in outbreaks. Several new initiatives such as the WHE learning and capacity development initiative/unit, and the DG’s, global health emergency corps improved data analytics for preparedness, and the Global Preparedness Monitoring Board are expected to further enhance WHO leadership in global health emergencies. WHO has led health sector coordination through 30 Health Clusters (28 national, 2 regional), targeting the health and humanitarian needs of 68 million people, in partnership with over 900 national and international partners. In collaboration with national authorities, the Inter-Agency Standing Committee, the United Nations Office for the Coordination of Humanitarian Affairs and other global partner networks, WHO is actively strengthening context-specific coordination and multisector collaboration to achieve better health outcomes. In response to the COVID-19 pandemic response, the Strategic Preparedness and Response Plan developed by WHO has subsequently informed the COVID-19 Global Humanitarian Response Plan, a joint effort by IASC agencies with a humanitarian mandate to analyse and coordinate the response to the direct public health and indirect immediate humanitarian consequences of the pandemic on the population in countries already facing other crises. Implementation builds upon existing humanitarian mechanisms and process including the Health Cluster to meet COVID-19 specific needs through a multi-partner, multi-sectoral response to the pandemic. The GHC has produced Health Cluster Coordination Guidance for Heads of WHO COs as Cluster Lead Agency which aims to assist WHO Heads of Office to fully understand their responsibilities and accountability as Cluster Lead Agency and includes the IASC protocol on system wide activation for large scale outbreaks including WHOs role. The guidance has been disseminated to Heads of WHO Country Offices by the WHE Executive Director. The United Nations Crisis Management Team (UNCMT) was activated on 4 February 2020 to coordinate the entire United Nations system to support countries in responding to COVID-19. The IOAC notes that the UNCMT is being led by the WHO Secretariat for the first time and recognizes the establishment of a United Nations COVID-19 supply chain task force to scale up the supply of essential COVID-19 tools such as personal protective equipment, ventilators, and laboratory equipment. In 2020, the WHO collaboration with the UN system has grown significantly, with respect to: 1) Sendai Framework reporting against global targets and indicators, which in 2021 will including reporting on the impacts of COVID-19 on health and health services; and 2) the support of the UN system, in particular, UN DRR for developing UN policy, guidance and learning programs on integrating disease outbreaks in national disaster risk management strategies and UN sustainable development cooperation frameworks. The IOAC notes positive feedback and recognition from United Nations partners on the WHO’s leadership at both the global and field levels. The IOAC also recognizes the sustained efforts of the WHE Programme to engage with and build the depth and capacity of WHO partner networks. Further clarity on the governance structure of WHO partnerships, roles and responsibilities, and coordination mechanisms is however required.
Partnership | Partnership and engagement with host governments, humanitarian actors and NGOs on the ground should be leveraged to deliver collective progress. This should include an alignment of technical standards, financial arrangements, staff training, and development of joint protocols and standard operating procedures (SOPs) to improve collective capacity in terms of preparedness and response to large-scale health emergencies. This should also involve the dissemination of best practice and global standards for EMTs via national medical response teams. | Monitoring Framework 3/21, Interim report 2020, A72/6, EB144/8, A70/8. | In progress | The GHC strategy (2017-2019 & 2020-2023) prioritizes partners' commitment to prevent, prepare for, respond to and recover from public health and humanitarian emergencies including through greater outreach to multi-sectoral development actors who provide health enhancing capacity including WASH and RCCE. Several cluster partners have strengthened their collective operational readiness and response capacity for outbreaks (based on lessons learned from recent Ebola outbreaks) including investment in national actor capacity. In response to COVID-19, a GHC Task Team was established in 2020 to strengthen the coordination and effectiveness of the Health Cluster response to the COVID-19 pandemic. The COVID-19 Task Team's primary objectives are to: 1) Collate country-level technical, operational and coordination challenges; 2) Promote and support adaptation and use of COVID-19 guidance for low capacity and humanitarian settings; 3) Support multi-sectoral action; 4) Capture and share lessons learned and good practices; 5) Advocacy to address unmet needs and operational barriers. The GHC conducts regularly a Health Cluster Partners' Capacity Survey that aims to capture information on partners' technical, operational and coordination capacities. The result of this exercise helps to more effectively identify critical gaps in health response capacity and inform future partner engagement for the Health Cluster. Results have also been used to advocate for strengthening country multi-stakeholder interventions to address identified gaps and weaknesses (such as newborn health, MHPSS, SRH & GBV in emergencies and outbreak readiness and response capacity). GHC created a Knowledge Bank in 2017 that provides the most up-to-date and relevant documents for humanitarian coordination and response to health emergencies . Documents include technical guidelines and guidance, tools and templates, best practices, lessons learned - available via the GHC website. The Health Cluster has over 900 partners at country level of which 65% are national & local actors; 57 of the international partners also engage strategically at global level. This is a collective force guaranteeing the response to health emergencies is more timely, effective and predictable. WHO continues work to set global standards for EMTs through consultation at regional and global level on updates to the Classification and Minimum standards for Emergency Medical Teams (also known as the “Blue Book”) which will be finished this year. The initiation of the drafting process of the guidance document on the engagement of EMTs in conflict settings (known as the “Red Book”) has now concluded its consultation and drafting and will be available at the same time as the Blue Book as its accompaniment. Four out of six WHO regions have fully established their regional EMT governance platforms, which are the main forum at the regional level allowing for MS, EMTs and other stakeholders to shape, guide and drive the implementation of the EMT Initiative in their region.
Partnership | IOAC observes that WHO’s performance in the health cluster and interaction with partners in the field relies heavily on the individual ability of health cluster coordinators. Systematic measures and institutional support for health cluster coordinators are needed to ensure that WHO provides strong coordination and technical and operational support to partners on the ground through the health cluster system. | Monitoring Framework 3/21, A73/10. | In progress | Lessons learned on Country Health Cluster performance from three external reviews undertaken during the last reporting period (NE Nigeria, Mozambique, Turkey) have been incorporated into updated guidance documents such as the Health Cluster Guide (2nd edition) and ongoing revision of the WHO Emergency Response Framework, and applied operationally with appropriate adaptation of and interface between Health Cluster coordination architecture, the WHO Incident Management System and other outbreak coordination platforms. This has been most evident in through implementation of the Global Humanitarian Response Plan for COVID-19 which was premised on working within and strengthening existing national and humanitarian coordination architecture rather than develop parallel structures. As most Health Clusters had existing engagement with nationally led Emergency Operations Centers, this enabled rapid scale-up and integration of COVID-19 requirements within existing humanitarian operations. Similarly, lessons learned from the IASC Operational Peer Review of the Ebola response in Eastern DRC informed improvements in partner engagement with the IMST response pillars. During this reporting period, 59% of Health Clusters completed the annual IASC Cluster Coordination Performance Monitoring (CCPM) exercise (compared to 60% in 2019); the main areas identified for improvement include further development and systematic use of AAP mechanisms; encourage improved multi-sectoral data collection and joint analysis with health partners and other clusters/sectors; deeper examination of localization across all cluster work (particularly in the EMRO and AFRO regions) and strengthening advocacy work. An external evaluation of the 3-year GHC Project on ‘Delivering integrated Sexual and Reproductive Health Rights services in emergencies through the Health Cluster’ will be undertaken in April-June 2021 to review work undertaken in Bangladesh (Coxs Bazaar), DRC (Kasai region) and Yemen.
Partnership | Close collaboration of health cluster coordinators with incident managers to enable closer engagement and effective coordination. | A72/6. | Fully implemented | The relationship between Health Cluster Coordination and Incident Managers has been examined and addressed through the review of the ERF and GHC commissioned external evaluations of the Country Health Cluster performance and coordination architecture in NE Nigeria and Mozambique (completed between September 2019 and January 2020). Both evaluations explored aspects of WHOs role as Cluster Lead Agency and adaption of Health Cluster coordination to each evolving crisis, including the interface WHO IMS and other outbreak coordination platforms. The evaluation summary findings concluded that overall the Health Cluster scored 60%, or ‘average’ across all evaluation criteria, only slightly below a rating of ‘good’. The cluster is therefore fulfilling its core role of providing a well-functioning coordination platform for health response in both countries. The evaluation found that roles and responsibilities must be further clarified across WHE IMS and the Health Cluster, that overall, the WHE IMS structure was found to provide a positive environment. The GHC addressed the evaluation recommendations in the revised second edition of the Health Cluster Guide which clearly articulates the interface between the HCC and IM roles; how the Health Cluster engages with the response pillars defined within each event specific IMS. The Health Cluster Guide is the 'go-to' reference for all country Health Clusters, partners and other key stakeholders.
Partnership | GOARN: Roles and responsibilities of WHE and partners in GOARN should be clarified, with the aim of establishing institutional arrangements for GOARD deployment. WHE should work closely with MS, GOARN partners and stakeholders to ensure a rapid roll-out of the Go.Data tool. | Monitoring Framework 3/21, EB146/16, A72/6, A70/8, EB140/8. | Target achieved, progress continuing | As of March 2021, there are 265 partner organizations, agencies, and networks registered on the GOARN knowledge platform. SOPs delineate responsibilities at HQ for the management of the various event types (sudden natural, slow natural, sudden man-made, NBC accidental, NBC deliberate, high consequence pathogens) and for the transfer modalities between teams and departments when event phases change. The GOARN operational support team at HQ participates in the daily risk management and operational meetings and involves partners in outbreak investigation and control activities as feasible. GOARN Operational support team continues to conduct regular weekly operational calls with GOARN steering committee and partner institutions. Through GOARN alerts and GOARN Requests for assistance, partners are informed and engaged in response activities. In 2020, until 18 August, GOARN partners submitted close to 600 offers of support, of these over 100 deployments, including remote support deployments were conducted. WHO in collaboration with GOARN partner institutions have designed, developed and are rolling out (to support COVID-19 response) the outbreak investigation tool Go.Data which focuses on case and contact data, including contact tracing and visualisation of chains of transmission. Over 50 countries have requested support, and GOARN partners are implementing a strategy for wide-scale rollout of Go.Data including direct country support, technical briefings, webinar/online presentations, and comprehensive remote support. At the onset of the COVID-19 pandemic, the EMT network mobilized medical teams to the most affected countries as surge capacity. Additionally, in collaboration with GOARN, has sent clinical experts and coordinators to affected countries to support them to manage and respond to the rising cases in countries. GOARN is also undertaking research focused on Ebola and COVID-19 response. The network has also provided the coordination platform for IFRC, UNICEF, and WHO as the 3 main international agencies that are shaping the Risk Communications and Community Engagement (RCCE) for the COVID-19 response since the start of the outbreak. The GISRS (Global Influenza Surveillance and Response System - in > 125 countries) was leveraged in March and has become the platform for sentinel surveillance of COVID-19 providing critical understanding of community transmission to inform country's response. GOARN deployments of personnel with contractual arrangements directly with WHO are covered under the UN Security Management System, which ensures the safety of deployed personnel.
Partnership | WHO should promote the establishment of an appropriate multilateral governance mechanism for ensuring equitable access to therapeutics and vaccines for all countries and effective delivery and stewardship, drawing upon previous experience of epidemics and pandemics. Further, the organization should be actively involved in global efforts to promote equitable access to COVID-19 vaccines and treatments, and IOAC further recommends the continued active involvement of WHO in this process. | A73/10, Interim report 2020. | In progress
Partnership | The WHE Programme and the Science Division work with other divisions across the organization to implement the R&D Blueprint’s joint workplan with funding requirements, a common monitoring framework and a system of dual reporting to the WHE ED and the Chief Scientist. IOAC believes the programme should explore greater use of WHO collaborating centres around the world, expert networks, such as technical advisory bodies, and public health institutes, to generate technical recommendations and supplement capacity in fast-moving crisis. | Monitoring Framework 3/21, A73/10, Interim report 2020. | In progress | The R&D Blueprint is managed jointly by the WHE Programme and the Science Division, with centralized resource mobilization. Although no accountability framework is in place, the R&D Blueprint has performed well, in part as a result of the personal commitment of, and cordial relationship between, the Chief Scientist and the WHE ED. The IOAC recognizes the R&D blueprint as a means of coordinating the ongoing efforts of the global research community and that it has facilitated the process of multi-national vaccine and therapeutic drug trials by standardizing protocols and leveraging national capacities. The Research and Development Blueprint work is continuing. The list of priority diseases for the blueprint was revised in 2018 including disease X. The work of the Blueprint has allowed the introduction of 4 new therapeutics for case management and large-scale vaccination against Ebola in the Democratic Republic of the Congo (DRC) Eastern Equateur and North Kivu. More than 80,000 high-risk people have been vaccinated. In addition, modelling work by the WHO CC Imperial College has been used to support and guide the response. For the COVID-19 pandemic, the WHO Information Network for Epidemics (EPI-WIN) was established to fight misinformation, rumours and myths, as well as establishing trusted sources of information by establishing multi-partner amplification partnerships.
Partnership | Sufficient and consistent support for information management should be provided to the health cluster coordinator. | Monitoring Framework 3/21, A70/8. | In progress | HIM and GHC jointly co-chair the GHC Information Management Task Team, which is a group of focal points for agencies working in humanitarian information management. The IMTT has quarterly face-to-face (virtual) meetings, and works collectively to develop standards and tools (Public Health Information Services [PHIS] Standards + Toolkit) to facilitate information management within national Health Cluster. In the past 12 months, the IMTT has conducted an survey of national Health Clusters (Coordinators, Information Management Officers [IMOs] and others) to assess their greatest information management needs; and has provided guidance on estimating People in Need (PiN) of Health; has developed training materials on multiple aspects of emergency health information management; revised core health indicators; amongst others. Further, the GHC global IMO provides hands-on day-to-day support to national Health Cluster Coordinators through their Health Cluster IMOs. Efficient use of limited info management for the Health Cluster (e.g. when there is not a dedicated HC IMO) is promoted through the Integrated Information Management Unit (IIMU) concept. Information Management Training - The GHC Information Management Task Team has run 4 PHIS online training cycles between April 2020 and January 2021 with a total of 105 participants, from 58 organizations and representatives from all activated Health Clusters. The training consisted of 12 online thematic sessions, with additional post-training group projects revolving around the visualization and analysis of PHIS data in a training scenario.
Finance | CO Fundraising: Increasing in-country donor engagement by WRs to improve local fundraising. To increase CO's authority to fundraise during emergency response, partnering with rather than depending on RO or HQ.. | A73/10, EB146/16, A71/5, EB142/8, A70/8, EB140/8. | In progress | The IOAC observes that challenges persist in fundraising at country level. In recognition of funding decisions being informed, and increasingly decided by donors at country level, WHE has invested in strengthening RM capacity at country level. These investments include the recruitment of dedicated RM staff for priority graded country office operations – 10 priority positions were identified, and out of these 7 were filled. The WHE RM team also deployed dedicated RM staff to work with WRs for targeted responses to develop capacities for engagement of donors and through this, for resource mobilization. In 2021, AFRO has onboarded some 25 resource mobilization professionals, who will work at country level to better resource WHO’s work. WHO will continue to strengthen efforts for RM at country-level to tap into funding for emergencies e.g. ECHO funding and country-based pooled funds such as CERF funding. From 2020, under the new Global RM Strategy there is focus on RM and external relations capacity building in country, particularly where the identified opportunity is greatest and for certain humanitarian donors, where considerable momentum exists such as with ECHO for which WHO has become a strategic partner (as of Jan 2020). However, an IOAC survey with WRs found that there is a significant discrepancy between MS financial contributions and their expectations of the WHE Programme. The result is a constant struggle to mobilize resources, with staff forced to juggle competing priorities simultaneously. Further, CRM HQ works closely with regional colleagues, showcasing strong country teams in Strategic Dialogues with donors and is furthermore developing a Contributor Engagement Management System, with AFRO as the region featuring in the initial roll out. In addition, CRM in collaboration with the ROs have provided support to ensure adequate funding is secured for its emergency operations in different countries.
Finance | MS should be invited to consider an increase in assessed contributions in the form of long-term sustainable financing. The IOAC further advises WHO to: improve donor engagement; develop a credible, strategic, data-driven, and compelling narrative; improve understanding of donor requirements; engage with the right donor counterparts; prioritize unrestricted resources; and tailor fundraising strategies to specific donor and funding requirements. | Monitoring Framework 3/21, A73/10, Interim Report, A70/8, EB140/8. | In progress | The IOAC observes that there is a significant discrepancy between MS financial contributions and their expectations of the WHE Programme, resulting in a constant struggle to mobilize resources, with staff forced to juggle competing priorities simultaneously. The IOAC recommends that MS review WHO financing to ensure the WHE Programme is able to continue to play a key role in global health emergencies with appropriate capacities.. Longer-term sustainable financing is critical to stabilizing contracts that are short-term due to funding constraints - while multi-year partnerships have supported the stabilization of some contracts, not all contracts have been possible to stabilize. For some contracts including those for emergencies in the field, such as the North Kivu EVD outbreak, the nature of the funding (humanitarian) meant that a stabilization of contracts was impossible. Funding with a duration of anywhere from 6-12 months, does not allow for longer term contracts, especially when the funding is received at varying times during the response. This is a real and re-occurring problem for WHE when responding to health emergencies. For HQ, fundraising to cover salary costs remains a challenge – many donors will not want to cover HQ salary costs or only in limited form through their contributions for the programme, thus making WHE over reliant on what is raised as flexible funding for staff salaries. As regards OCR funding, WHO launched the COVID-19 Strategic Preparedness and Response Plan for 2020 in February 2020 with a total ask of $1.7 billion. At the close of 2020, WHO had mobilized $ 1.5 billion against the SPRP, through continued engagement of its donors including, but not limited to traditional humanitarian donors, while also seeking to engage new potential donors with a view to diversify the donor base. In 2020, 15 new donors came on board through support to the SPRP. On 24 February 2021, WHO launched the COVID-19 SPRP for 2021, which integrates the Organizations work on ACT-A and the HSC, too. By supporting the SPRP, donors will be supporting WHO’s work on ACT-A and HSC through the 10 pillars of work implemented by the Organization across its 3 levels.
Finance | WHO/WHE core budget: WHO is encouraged to increase allocation of the core flexible funding for the WHE Programme, in particular supporting countries with preparedness activities, for which it has proved difficult to raise funds. Further, there is a need to identify additional revenue sources for the core budget of the WHE Programme, and strengthened budgeting at country level. | Monitoring Framework 3/21, A73/10, EB146/16, A72/6, A70/8. | In progress | The WHE Programme budget has only risen 7% over the last four years. The IOAC considers this increase inadequate in view of the demands now being made on the WHE Programme’s responses to emergencies and humanitarian crises. Moreover, a budget of that size is insufficient to deal with a global pandemic like COVID-19 . A resource mobilization strategy was developed and presented to the EB at the 146th session held in February 2020. It provides information on the strategy for mobilizing the resources needed to deliver GPW 13, covers the period for 2019–2023 and rests on four pillars: • Established government partners: growing, diversifying or maintaining funding through regular and active engagement and policy alignment, taking a tailored approach; • Philanthropic partners: building on our most effective partnerships and seeking to grow funds from a wider range of philanthropies; • Funds, international development banks and multilaterals: maintaining funding from mature partnerships and developing funding streams from new sources and mechanisms; • Innovative financing and revenue-producing activities: exploring the potential in these areas. Individual donor profiles and engagement plans have been developed for top donor to the emergencies programme, detailing key partner institutions, budget cycles, key dates/events for engagement. The profiles also include a mapping of donor priorities against the 10 output strategies to guide more strategic engagement with donors for 2020. Strategic dialogues were held with several donors to WHO, and all included representation of the emergency programme thereby facilitating high level strategic discussions and positioning with donors. However, this work took place just prior to the onset of the COVID-19 response, and thus will have to be updated to reflect the new reality for donors. This is planned for 2nd half of 2021. In 2020, strategic dialogues were held with several donors to including Canada, France, Luxembourg, and Norway and all included representation of the WHE thereby facilitating high level strategic discussions and positioning with donors. A number of strategic dialogues are planned for 2021 including with Japan, to which WHE will also be participating at senior level. However, it should be noted that pre-COVID-19, several multi-year partnerships were in place including with Australia, BMGF, Germany, UK, USA (OFDA, USAID, CDC), New Zealand, the Netherlands, Russia. Since COVID-19, new multi-year partnerships have been developed including with China and Kuwait. In 2020, the COVID-19 response required the full attention of the EHE team, as well as the other units of CRM, and beyond. Resource mobilization for COVID-19 in 2021 is progressing, with significant amounts pledged already, but with concern over the high degree of earmarking by donors. This continues to restrict WHO’s ability to ensure equitable financing of its work, including financing in real time to where the capacities and needs are greatest. COVID-19 will undoubtedly continue to impact RM for other parts of the WHE in 2021, which may require adjustments to RM approaches and targets. Mobilizing flexible or thematic resources is a corporate priority and decisions about how such funds are allocated between the core budgets of different programmes are taken at a senior level across the organization.
Finance | To clarify the relationships and division of labour between the CFE and other humanitarian funding streams that receive donor support in health emergencies. Redesigning the CFE replenishment mechanism, giving consideration to whether the CFE should be partly funded by the WHO core budget or whether alternative sources of funding, including from the private sector and foundations, should also be explored. | A73/10. | In progress | There is wide recognition by MS that the CFE is critical in enabling WHO to address immediate needs in emergencies, thus preventing the further spread of an outbreak. However, the Fund struggled to reach the total capitalization set at US$ 100 million, and the replenishment mechanism has proved ineffective. The IOAC also observes that the CFE was disbursed for purposes other than those intended. The IOAC notes good progress with respect to donors’ trust in, and support of, WHO’s management of outbreaks. In particular, WHO’s enhanced capacity to rapidly deploy surge personnel to respond to the Ebola virus disease outbreak in the Democratic Republic of the Congo has significantly improved confidence. However, donors informed the IOAC that the ad hoc nature of CFE funding requests was problematic from their perspective, and that a broader donor base was needed, with more donors and a more diversified funding stream. The donor countries also noted a lack of coordination among the international financing mechanisms for emergencies, such as the Pandemic Emergency Financing Facility and the Central Emergency Response Fund.
Finance | To boost humanitarian donors’ confidence. | A73/10, EB140/8. | In progress | WHO has, since the establishment of WHE, made significant strides engaging humanitarian donors in support of WHO’s work in emergencies. CRM/EHE has developed dedicated donor profiles for WHE outlining the different donor institutions, which WHE collaborates with, or for which there is potential for collaboration based on mutual priorities. Special consideration has been given to identify and differentiate between partnerships and funding from Ministries of Health, and Ministries of Foreign Affairs, where the humanitarian funding often sits. In 2019 and 2020 WHE has established and engaged more strategically and frequently with the humanitarian attachés in Geneva and in capital as well. In 2020 in the context of the COVID-19 response, CRM and WHE have proactively, and at senior level, engaged on a regular basis with the so-called G12 group, which is a group of 14 GVA based Humanitarian Attachés. In depth briefings are held on a regular basis. The IOAC observes that the Department of Coordinated Resource Mobilization (CRM) has demonstrated its potential in WHO’s response to COVID-19. The IOAC observes great improvement in the financial support for appeals as the WHE Programme’s successful field performance has boosted humanitarian donors’ confidence in WHO. A number of humanitarian donors have or are considering including WHO/WHE as a strategic humanitarian partner – discussions around this have been ongoing in 2019, and continue in 2020, while ECHO confirmed that WHO in January 2020 was now officially included as one of eight strategic partners to ECHO. WHO is, thanks to WHE, increasingly viewed by donors as a critical partner on the ground in humanitarian settings – this is especially thanks to a number of strong and engaged WRs, who have set the bar high, and also a result of the health cluster coordination function, under which WHO has also proven itself an effective coordinator.
Finance | Investment case: WHO share a draft of the corporate investment case paper with Member States to ensure that the final document is successful in robustly advocating the economic argument/case for investment to governments including ministers of finance and other donors. | EB142/8. | Fully implemented | WHO Investment Case, GPW13, output strategies and factsheets. Humanitarian Response Plans such as the SRP for DRC, SPRP for COVID-19, Donor Alerts. The Investment Case is to be refreshed and WHE will be fully reflected; it is likely that the IPPR will comment on the macroeconomic investment case for pandemic preparedness, as well as make other specific recommendations
Finance | Donors were urged to contribute in order to bring the EVD outbreak in DRC under control and contain the spread to surrounding countries. | A72/6. | Fully implemented | As of May 2019 the WHO funding gap against its requirement in the third Strategic Response Plan (SRP) was 49%, and only a few donors had stepped up with significant funding. Whilst total funding received increased from SRP to SRP, the level of funding decreased from SRP 1 (fully funded) to SRP 2 (28% gap) and SRP 3 (49% gap). SRP 2 and SRP 3 left WHO with significant funding gaps, which were mainly filled by CFE. The SRP 4, released in July 2019, was however fully funded (USD 146 mil received) and supported by 17 donors.
Finance | The IOAC believes that the CFE would be most effective if it was fully functioning as a revolving fund, but recognizes that it is not functioning as one currently, and recommends WHO to come forward with clear plans for its sustainability for the future. | Monitoring Framework 3/21, A70/8. | In progress | Donors have demonstrated their confidence in WHO and the CFE by investing nearly US$137 million in the Fund since it was launched. The Contingency Fund for Emergencies (CFE) budget of US$ 100 million was 92% funded for 2018-2019 biennium. Standard procedures across all of WHO’s three levels – HQ, RO, CO – ensure the CFE’s effective operation and management, sustainability, and accountability to donors. Furthermore, the CFE’s income and expenditure are included in WHO’s Financial Reports, are submitted to the WHA annually, and are subject to internal and external auditing.The External Relations team continues to mobilize resources for the CFE. In 2019, US$54 million was raised from 16 Member States, while US$83 million was released to support 23 emergencies in 22 countries. Four new donors joined the list of contributors and the first multi-year agreement for the CFE was signed with New Zealand for a period of three years.Despite the increase in funds raised, the continued drawdown of the CFE in 2019, especially for the Ebola response, left the Fund depleted at times, and therefore not available to perform its core function. In 2020 approx. U$ 23 million was raised from 13 donors, while $44 million was released to support 14 events including six disease outbreaks, five complex emergencies, two natural disasters and one technological disaster. The main challenge has been the sustainable replenishment of the CFE. The CFE remains dependent on a few traditional donors for most of its funding. Furthermore, the CFE was envisaged by MS to be a revolving fund whereby contributions to WHO emergency operations at country level would be used to pay back CFE allocations. In practice, it has proven difficult to raise the level of resources required at the country level to sustainably replenish the CFE in this manner. This fact further underscores the challenge faced by the Organization in terms of sustainably funding its work. A road-map for how to better (re)position and replenish the CFE is being developed and will be carried out over the course of 2020 but has been somewhat delayed as RM capacities and efforts were redirected towards the COVID-19 response. The recently launched WHO corporate resource mobilization strategy places an emphasis on attracting more donors, deepening existing relationships, and seeking multi-year agreements to ensure predictability. The CFE fits squarely within this strategy. Furthermore, resource mobilization for the CFE must be part of the ongoing discussions around raising sufficient sustainable financing for WHO and strengthening WHO’s global health emergency preparedness and response capacity. In parallel, a broader, refreshed strategy aimed at strengthening the CFE in terms of its financial sustainability, operational fit and accountability to donors is currently being elaborated.
Finance | Financing surge capacity: To secure resources to maintain and increase core technical expertise capacity within the WHE Programme at HQ and enable the programme to leverage in-house experts through internal surge capacity. MS and WHO secretariat revisit the size and surge capacity of the WHE to ensure sufficient capacity, resilience and flexibility within and beyond the IMS to respond adequately to such multidimensional and large-scale emergencies, alongside the increasing number of graded emergencies that it routinely manages. | A73/10, Interim Report 2020, A72/6, EB144/8. | In progress
Finance | Corrective actions, including emergency measures under the Framework of Engagement with Non-State Actors, must be fully implemented at all three organizational levels, to support field responses. | A72/6, A71/5. | In progress | Emergency measures under the Framework of Engagement with Non-State Actors have been published in the WHO eManual, section XVII. However, the IOAC’s desk review on the Ebola response indicated that these measures are not being fully applied on the ground and the IOAC recommends that further efforts be carried out to streamline the process and accelerate engagement to support critical emergency responses.