## Milestones A69 30
Area of work | Milestone / target | Deadline as per A 69/30 | Status
Structure | WHO’s work in emergencies brought into a single programme, with a common structure across headquarters and all regional offices and the first set of priority countries. | 2016-07-01 | Completed. The programme has been established with a similar structure at the 3 levels with some regional specificities in those areas where there was a functional benefit. Adjustments were made following regional exercises further executed (e.g. functional reviews in EMRO and AFRO). The PAHO Health Emergencies Department (PHE) was created 15 September 2016, bringing together the department of Emergency Preparedness and Disaster Relief created in 1976 and the Unit of International Health Regulations/Epidemic Alert and Response, and Water Borne Diseases under a consolidated management structure. PHE reports directly to PAHO DIrector and functionally aligned its work in emergencies with WHO's new Health Emergencies Program (WHE), mirroring the WHE structure, while maintaining priority areas of work for the Region of the Americas not included in WHE (DRR, migrants , people with disabilities, indigenous populations, and others). In AFRO, the Health Action in Crisis (HAC) Program was merged with Epidemic Preparedness and Response (EPR) program to holistically address all types of health emergencies and relevant staff capacitries were mapped and and the staff re-assigned to the appropriate positions accordingly. For better coordination with key partners in the African Region, two emergecy hubs were established in Dakar (Senegal) and Nairobi (Kenya) where some of the regional staff were re-assigned. Ongoing discussions with RD EURO regarding the status of RED EURO position for which there was a plan to merge with Director of Country Support function. This has been discussed with RD and it has been decided to maintain the RED position and have contined reporting of RED to RD and EXD. WHE structure has changed at HQ with the establishment of two Divisions (preparedness and response). This change has led to some differences in the structure across Major Offices.
| Relevant functions of the Programme are replicated at country level as appropriate. | Unspecified | Completed. Relevant priority functions: WHE Team leads or focal points in countries; critical IMS/emergency management functions filled in all countries with G2 or G3 emergencies; Health Cluster Coordinators in all countries with Health Clusters; Incident Management Teams established as appropriate for new emergencies. In smaller country offices, there is however often a single person dealing with all aspects of emergency preparedness and response, partially because of funding constraints. Several regions have conducted capacity building activities on operational readiness trainings for RO and WCO staff, to ensure the relevant staff are trained on the key aspects of the Emergency Response Framework and familiar with emegrency SOPs. However, the country business model even for priority countries has not been implemented fully, due to lack of adequate and predictable tranches of funding.
| A standing interdepartmental task force at headquarters and regional office levels established to harness the broad range of expertise across WHO, particularly in research and development, policy, capacity building for preparedness, health systems strengthening, and protracted crises planning and programming. | Unspecified | Partially completed. At WHO Headquarters, various initiatives have been put in place to strengthen collaboration across divisions (WHE and non-WHE), for example the R&D Blue Print for Epidemics Steering Committee, collaboration on FCVs, etc. In EMRO, various interdepartmental mechanisms exist, including: RD's Cabinet; morning EOC meeing (pre-COVID) and daily IMST meeting (during COVID); standing collaboration and projects with HSD (e.g. Health Systems Emergency Lab), DCD (e.g. control of VPDs and arboviral diseases), IER (e.g. surveillance), NMH (e.g. NCDs, mental health), and DHP (e.g. peace as bridge to health). Further operationalization of this collaboraiton includes COVID-19 IMST is established, with daily participation of all departmental Directors and active membership of IMST by techncial staff. In April 2020, Regional Director at SEARO has extablished Empowered Groups in WHO South-East Asia Region to provide recommendations to the Executive Management in supporting Member States during Emergency Preparedness, Response & Recovery, and such other times as needed. PAHO has had an established Emergency and Disaster Taskforce with representatives from all technical and enabling entities across the organization. In AFRO an extended inter-cluster group continues to work on preparedness and response to emergencies with involvement of all the clusters in the regional office. To support specific emergencies, the inter-cluster Incident Management Teams have provided coordinated comrehensive support for the various field responses and drawn expertise from all the relevant programmes.
HR | Positions in headquarters and all regional offices and the first set of priority countries established. | 2016-07-01 | Completed. Organigrams exist for all 3 levels of the Organization. At the end of 2019, 270 of 355 (76%) of WHE position in HQ were filled and 867 of 1228 (71%) across the ROs and COs. In EMRO, the latest WHE organogram is approved by the Regional Director and currently recruitment of vacant and new WHE posts is ongoing. Critical lead functions at SEARO have been established and filled, however due to inadequate and unpredictable release of WHE AC flexible funds and administrative challanges, only 26 positions of an approved organogram of 39 positions have been filled. In the interim temporary staff and consultant mechanisms have been adopted to ensure all crticial functions are covered at the Regional office.
| Transition of existing staff into the new structure completed. | 2016-10-01 | Completed. At HQ, Polio, Emergencies & Country Collaboration was composed of two departments and a support unit 1) Operations & Cluster Management (PCM) program 2) Emergency Risk Management and Humanitarian Response ERM and 3) Polio Operations & Research. In 2016, the Polio department was transferred and a new structure was implemented. The new programme called the WHO Health Emergencies Programme was restructured into 6 distinctive departments in July 2016: Infections Hazard Management (IHM), Country Health Emergency Preparedness & IHR (CPI) Health Emergency Information & Risk Assessment (HIM), Emergency Operations (EMO), Management & Administration (MGA) and External Relations . A committee was created, managing the new job descriptions and the transferred of around 250 staff and 350 positions. Similar exercises have been completed in all regional offices.
| The Executive Director of the Programme recruited and in place. | 2016-07-01 | Completed.
| The Executive Director and Regional Directors will jointly recruit Regional Emergency Directors. | Unspecified | Completed. While DoA to Regional Directors clearly stated the joint-authority of the EXD to appoint RED and staff at P5 level and above of the Programme, this has now been removed in the 2020 DoA to Regional Directors. Some recent recruitments have been done under these new conditions. As part of filling the RED's position in AFRO, the Director's job description has been revised to reflect the changes and needs resulting from the revised organogram and responsibilities. The appointment process has been initiated and the the position is currently being occupied by an acting RED. PAHO is an independent organization with its own constitution, regulations, rules and governance structure. While PAHO serves as WHO’s regional office for the Americas (AMRO), it nevertheless maintains its own legal status and works within a separate legal framework with respect to all internal matters including those related to human resources. PAHO generally maintains alignment with WHO’s Staff Regulations and Rules, as well as its policies, but its Staff Rules, Regulations and policies are not the same as WHO’s and are approved by its own governing bodies. Moreover, from a procedural perspective, PAHO does not participate in WHO’s GSM. HR processes in PAHO are managed through the Organization’s own enterprise resource management system known as PMIS. Consequently, PAHO is not subject to the WHE HR management processes, including all related decisions concerning structure, HR plans, the creation, extension, abolition and classification/reclassification of posts, and the appointment status of staff. The director of the Emergency Preparedness and Disaster Relief department was appointed as the Regional Emergency Director at PAHO when PHE was established. (AMRO)
| In high-vulnerability, low-capacity countries, WHO offices will have dedicated staff to support Member States with capacity building in preparedness and response. | Unspecified | Completed, although in smaller country offices there is often one or few staff supporting all aspects of emergencies.
| In protracted crises, WHO will strengthen its in-country leadership, ensuring that all WHO Representatives receive the training given to Humanitarian Coordinators. | Unspecified (“over time”) | In progress.
| Health emergency information and risk assessment and for preparedness monitoring and evaluation teams functioning at HQ and in all six regional offices. | End 2016 | Completed as part of the roll-out of the programme.
HR (continued) | Staffing in place for the basic, essential functions of the emergency operations teams at HQ and in the Regional Offices for Africa and the Eastern Mediterranean. | End 2016 | Completed. The essential functions of the emergency operations teams are ensured in the Regional Offices for the Eastern Mediterranean region as reflected in the WHE organogram. Staffing gaps are curntly being addressed, but constrained by financial gaps - including as a result of US government funding withdrawal. At the end of 2019, 196 of 238 (82%) of WHE position in EMRO were filled and 278 of 473 (59%) in AFRO.
| Establish appropriately staffed emergency management teams, including Health Cluster Coordinators, in at least 10 priority countries affected by protracted crises. | End 2016 | In progress. As of June 2020, 22 out of 30 (73%) health clusters/sectors have a dedicated Health Cluster Coordinator and 16 out 30 (53%) health clusters/sectors have a dedicated Information Management Officer. See dashnoard at: https://www.who.int/health-cluster/countries/HC-dashboard-june-2020-final.pdf?ua=1. Stagnation in the number of dedicated HCCs persists due to previously cited bottlenecks including lack of funding to implement the WHE Country Business Plans and delayed recruitment process. The GHC works closely with WHE HQ-HR to develop the WHE HCC rosters and with the Standby Partnerships team to deploy suitable candidates to fill outstanding HCC gaps. The GHC continues to lobby WHE leadership at global and regional level to secure alternative sustainable funding and address recruitment bottlenecks to ensure timely and consistent HCC presence.(GHC)
| Staffing the remaining priority positions in HQ, regional offices and priority countries completed. | End 2017 | In progress. Highest priority positions have been filled. Some staffing gapos persist, constrained by funding and availability of qualified staff.
Standardizing processes | The WHO Emergency Response Framework will be revised and updated. | Unspecified | Completed. The ERF was published in 2016 and first updated in 2017 (ERF2). Valuable experience in implementing ERF2 led to a second revision process that started mid-2019. This latest revision took place with input and feedback from all regions and was completed in January 2020. Options paper for an updated ERF3 were developed in the areas of risk assessment, grading, no regrets policy, protracted crises, risk management, performance standards, and response to vaccine preventable diseases. To complete ERF3, a face to face meeting between major offices was planned for early 2020 but had to be postponed due to the COVID-19 pandemic. A virtual meeting may be considered in the second half of 2020, pending the acuteness of the competing COVID-19 response needs in the different regions, in addition to other emergency events. (TOM)
| Standard processes developed for risk assessments, event grading, and incident management. | Unspecified | Completed as part of the ERF2.
| All major infectious risks and emergencies with health consequences – including outbreaks – will be assessed and/or graded by WHO using standardized processes. | Unspecified | Completed. Since the beginning of 2020, 311 events occurring in 213 countries and territories were investigated, risks were assessed and followed up on. There are established standardized operational procedures for risk assessment and event grading that are followed by the 3 levels of the organization using the same structure for each event. Using information from risk assessments, WHO and MS are identifying priority public health risks and need for further support.
| WHO country office readiness will be assessed using a standardized format. | Unspecified | In progress. WHO guidance for business continuity planning (BCP) was published in 2018. BCP has been implemented in SEARO (completely) and is beginning in AFRO (with 3 WCOs: Nigeria, Sierra Leone, Mozambique). BCP aims to increase WHO resilience in the face of potential disruptions. It covers all WHO offices and staff. The main objectives of WHO BCP are: 1. Guarantee of safety of WHO staff, premises, and assets 2. Maintain critical WHO programmes and operations 3. Ensure WHO is able to deliver a swift and effective emergency response WHO prepared a country office readiness checklist. This checklist consolidated inputs on main capacities (coordination, safety and security, OSL capacity, HR, finance, IMST capacity, etc.) The checklist was implemented in 7 WCOs in AFRO. WHO has supported 48 WCOs to develop and upload costed "COVID-19 readiness and response plans" and supporting all WCOs to submit updated resource need requests for all WCOs on the Partners Platform.
| Performance standards will be established or updated for each process. | Unspecified | Completed. Performance standards have been established as part of the ERF and are monitored and reported against. As part of the currently ongoing ERF review, a document was drafted following consultation with all regional offices to revise ERF2 indicators to improve applicability for the differetn types of emergencies (acute infectious events, humanitarian crises, natural disasters, etc). Implementation of the revised performance standards will be part of the ERF3 process. A seperate set of performance and M&E indicators has also been developed specifically for the COVID-19 response as part of the SPRP, for both Member States and WHO.
| Standardized response planning in place, including templates and standard procedures to rapidly enable common strategic and operational plans. | Unspecified | Completed. Templates are available and have been used as part of the COVID-19 response and previous key graded emergencies.
WHO’s work in the broader humanitarian architecture | Alignment of WHO’s work in health emergencies with the humanitarian architecture and in particular with the IASC | Unspecified | Completed. WHO's work is wel aligned with the IASC now, and more importantly, IASC relies on WHO much more than it used to and has aligned its own work closely with WHO. WHO's work is also well aligned with the humanitarian -development -and increasingly Peace -nexus. Discussions with the UN Development Group (now UN Sustainable Development Group) as well as with the UN Peace Building Group take place regularly at global level, and WHO COuntry representatives take part in these discussions at country level as part of the Humanitarian Country Team discussions. WHO takes activley part in the Joint Steering Committee meetings, which bring together humanitarian and development actors. Health Cluster Coordination Guidance for Heads of WHO Country Offices as Cluster Lead Agency aims to assist WHO Heads of Office to fully understand their responsibilities and accountability as Cluster Lead Agency. The guidance was sent from Executive Director to all Heads of WHO Country Offices. The document is available in 5 official languages at the GHC website: https://www.who.int/health-cluster/capacity-building/HWCO-guidance/en/.
Financing | Full financing of the USD 494 million of core financing of the Programme for baseline staff and activities at the three levels of the Organization for 2016-2017. | Unspecified | Partically achieved. The approved budget for 2016-17 was 73% funded and that of 2018-19 was 81 % funded at the end of the biennium. Data source:PB Portal
| Full financing of the WHO Contingency Fund for Emergencies. | Unspecified | Partially achieved. Since 2016, 136 million have been mobilized. Current balance of the CFE is 25 million.
| Event-specific financing. | Unspecified | In progress. For COVID-19, 81% of the SPRP has been received or pledged as of 16 August 2020.
Risk assessment | Within 72 hours, the Programme will initiate an on-the-ground assessment when notified of a high threat pathogen (e.g. human-to-human transmission of a novel influenza virus), clusters of unexplained deaths in high-vulnerability/low-capacity settings, and other events at the discretion of the Director-General. | Unspecified | Completed. The Public Health Intelligence duty officer is monitoring the global situation 24/7 regarding high threat pathogens (e.g. human-to-human transmission of a novel influenza virus), clusters of unexplained deaths in high-vulnerability/low-capacity settings, and other events at the discretion of the Director-General. If an event is detected, there is an established cascading system for notifying senior management and requesting additional information from the Member States through the Regional Offices that engage the IHR NFP of the country and the WHO Country Office. Timeliness in event assessment has a high priority and when an event is detected by WHO that has not been notified by the Member State a verification process has been established. Within 72 hours, the Member States are obligated to reply to WHO’s request for verification or additional information.
| When feasible, the Programme will engage partner agencies with relevant expertise to assist in risk assessments. | Unspecified | Completed. When feasible, the joint FAO–OIE–WHO Global Early Warning System (GLEWS+) technical experts are engaged in risk assessment of health threats and events of potential concern at the human-animal-ecosystems interface. Each of the Tripartite agencies must continually assess the likelihood and potential impact of relevant events and - based on the assessment and if a need is identified - devise practical options to mitigate risks. Such assessments need to draw on international and local expertise in a variety of disciplines (depending on the type of event) which may include disease ecology, epidemiology, clinical aspects, case/outbreak management, socio-economics, and expertise on the specific etiological agent (including laboratory diagnostics), as well as knowledge and experience from the field. This is focusing only on zoonotic threat”.
| Risk assessments will include an analysis of the capacity and capability of the countries concerned, and of the WHO country office and region. | Unspecified | Completed. WHO risk assessment includes an analysis of the capacity and capability of the countries to detect and respond to public health events and its important part for the risk response and management activities. An effective response to an outbreak depends not only on the capacity and capability of the countries concerned, but also of the WHO country office and region, and underline the importance of increasing technical and operation support in concerned counties or region.
| The outcome of all risk assessments will be communicated to the Director-General within 24 hours of completion, with recommendations on risk mitigation, management and/or response measures as appropriate, for decisions on grade, incident management, and leadership in consultation with Regional Directors. | Unspecified | Completed The outcome of all risk assessments are shared immediately following the completion with the Director-General, the Regional Directors, incident management and leadership. The risk assessments include the recommendations on risk mitigation, management and/or response measures as appropriate, and decisions on grade. The risk assessments are based on a predefined and standardized format that follow the guidance document published already in 2012: : https://www.who.int/ihr/publications/WHO_HSE_GAR_ARO_2012_1/en/
| The outcome of all risk assessments will be shared with Member States through their National Focal Points for the International Health Regulations (2005), or other channels as appropriate, and to the United Nations Inter Agency Standing Committee and WHO Independent Oversight and Advisory Committee. | Unspecified | Completed. There is a well-established system for completion of the risk assessments and distribution. The outcome of all risk assessments is shared with Member States through their National Focal Points for the International Health Regulations (2005), through the Regional Office or the WHO Country Office. The global COVID-19 risk assessments were shared through the Regional Offices and through the IHR mechanism during Health Security Committee Meetings. The United Nations Inter Agency Standing Committee and WHO Independent Oversight and Advisory Committee receives the risk assessments through the established procedures.
Business processes | Development of emergency business rules and systems for planning. | Unspecified | Completed. The updated emergency business rules for planning have been consistently published at eManual XVII.3, detailing the guidance on OCR planning within the context of WHO General Programme of Work and Biennium Operational Planning. Emergency Planning in an integrated part of Incident Management System, which has been operating for all the emergencies since 2017.
| Development of emergency business rules and systems for human resource management. | Unspecified | Completed. The updated emergency business rules on Human Resources are published at WHO eManual XVII.8, including generic post descriptions for IMS roles and country business models, emergency roster management and selection for deployment, emergency deployment, on-site support during deployment and end of deployment, fast-track FT selection during emergencies. The roster system and deployments have been operational within IMS system for all emergencies since 2017.
| Development of emergency business rules and systems for procurement. | Unspecified | Completed. The updated emergency business rules on procurement are published at eManual XVII.9.3.4, detailing the delegation of authority for procurement during emergencies as well as the emergency procurement process. It has been applied in all emergencies since 2017.
| Development of emergency business rules and systems for finance. | Unspecified | Completed. The updated emergency business rules for Finance are published at eManual XVII.5 and XVII.6, covering grant management and reporting during emergencies, Contigency Fund for Emergencies request and reporting, cash advances in emergencies, Impreset PO, Direct Implementation and DFC process during emergencies and consultant payment during emergency deployments. The system has been operational within IMS system since 2017.
| Ensure that emergency finances are available immediately, through a minimum-burden application process to the WHO Contingency Fund for Emergencies. | Unspecified | Completed. In 2019 funding was made available within 24h for 78% of CFE request of up to $500k.CFE has proved to be a vital tool in response to emergencies and has significantly assisted in the rapid response . Replenishment of CFE remains a constant challenge and a review of options for CFE sustainability is underway
| Rapid deployment mechanisms in place for staff and consultants, both rostered and non-rostered, using new contractual modalities with appropriate insurance, duty of care and entitlements. | Unspecified | Completed. Rapid deployment mechanism is in place for all types of deployments (Duty Travel, consultants, GOARN, SBP, UNVs, etc..) in emergencies. This mechanism has been implemented and working effectively for various incidents including Ebola in DRC and global COVID19 responses. All deployees (Staff/non-staff) are eligible for emergency deployment entitlements and covered with appropriate insurance/WHO’s duty of care framework. Comprehensive SOPs have been developed in this regard and published in the emanual which can be found here https://emanual.who.int/p17/s08/Pages/XVII-8-3-Emergency-Deployment.aspx
| A continuous business improvement system in place to monitor, evaluate and improve core services, with systematic updating of standard operating procedures to reflect lessons learned. | Unspecified | Completed. A dedicated team on continuous business improvement has been in place since 2016, focusing on development and continuously updating SOPs for emergencies, as well as related training. eManual XVII has been continuously updated since 2016 with the input from emergency reviews, subject matter experts and lessons learnt.
Member State preparedness | WHO’s work in support of Member State preparedness will be aligned with the recommendations of the Review Committee on the Role of the IHR in the Ebola Outbreak and Response and the Sendai Framework for Disaster Risk Reduction 2015–2030. | Unspecified | Please see the details provided in subsequent rows 38-41
| The Programme’s work in preparedness will be structured to support application by all States Parties of the new monitoring and evaluation framework for the IHR (2005) and assessments with the new joint external evaluation tool as requested. | Unspecified | • WHO has developed and published the IHR Monitoring & Evaluation Framework to support countries in assessing preparedness levels, identifying critical capacity gaps and priority action for health security strengthening • WHO has supported countries to scale-up monitoring & evaluation of IHR capacities including achievement of the highest number of national responses to the States Parties Self-Assessment Annual Reporting (SPAR) questionnaire since 2010 which was achieved in 2019 (192/196) • WHO has also developed and launched a new web-based platform (e-SPAR) which allows online SPAR reporting, thus making the SPAR process easier for States Parties • Review of SPAR questionnaire to include additional quesstions to document experiences of countries during COVID-19 pandemic, completed with input from technical teams in HQ and RO. • JEE version 2 developed and rolled out and implemented by over 20 countries so far. • WHO has supported implementation of 113 Joint External Evaluations to date (as of October 2020)
| Support for national preparedness planning and capacity building prioritized to high-vulnerability, low-capacity countries with a focus on the most critical core capacities for early warning, incident management, risk communications and safe hospitals. | Unspecified | • WHE has supported 68 National Action Plans for Health Security (NAPHS) to date (as of August 2020) and is supporting countries to implement capacity building action to enhance health security • Technical documents have been developed in consultation with WHO ROs and partners to further support adaptation and implementation of National Action Plans for Health Security and Operational Planning measures in the context of COVID-19 lessons. The documents are currently being reviewed and finalized • The WHO benchmarks for IHR capacities was developed to facilitate the continued development of NAPHS and other emergency preparedness disease plans. To facilitate this process, WHO together with partners have developed an IT interface platform for the benchmarks, which provides direct access to guidance, tools and materials for support of capacity building action and development of draft action plans. • The WHO benchmarks for IHR capacities are used to map elements for health systems for health security, documenting progress of Member State action in health security and preparedness and many partners are using it as a reference to priortise their work plan and activities. • WHE is capturing case studies, lessons learned and best practices from COVID-19 preparedness and response action to strengthen health security. The evidence and information gathered will be used to update the WHO benchmarks for IHR capacities. • WHE continues to provide technical support to countries in making hospitals safer from emergency and disaster events and has published the 'hospital readiness for COVID-19 management checklist' to support countries in scaling up standardized hospital level care for COVID 19 including IPC • WHE is strengthening its partnerships with the International Hospitals Federation to review the existing safe hospital index based on the lessons learned from the current pandemic and will review the indicators for health facilities safety. • WHE has supported 68 National Action Plans for Health Security (NAPHS) to date (as of October 2020) and is supporting countries to implement capacity building action to enhance health security • Technical documents have been developed in consultation with WHO ROs and partners to further support adaptation and implementation of National Action Plans for Health Security and Operational Planning measures in the context of COVID-19 lessons. The documents are currently being reviewed and finalized • The WHO benchmarks for IHR capacities was developed to facilitate the continued development of NAPHS and other emergency preparedness disease plans. To facilitate this process, WHO together with partners have developed an IT interface platform for the benchmarks, which provides direct access to guidance, tools and materials for capacity building action and development of draft action plans. • The WHO benchmarks for IHR capacities are used to map elements for health systems for health security, documenting progress of Member State action in health security and preparedness and many partners are using it as a reference to priortise their work plan and activities. • WHE is capturing case studies, lessons learned and best practices from COVID-19 preparedness and response action to strengthen health security. The evidence and information gathered will be used to update the WHO benchmarks for IHR capacities. • WHE continues to provide technical support to countries in making hospitals safer from emergency and disaster events and has published the 'hospital readiness for COVID-19 management checklist' to support countries in scaling up standardized hospital level care for COVID 19 including IPC. • WHE is strengthening its partnerships with the International Hospitals Federation to review the existing safe hospital index based on the lessons learned from the current pandemic and will review the indicators for health facilities safety. • WHE has developed and published guidance and tools for Member States to plan and implement Country COVID-19 Intra-Action Reviews (IARs) which facilitate countries to conduct periodic review(s) of their national and subnational COVID-19 preparedness and response, so countries do not miss critical opportunities for learning and improvement to better respond to the COVID-19 outbreak in their countries. To date, 9 countries have implemented IARs and others are planned. • WHE is working with the environmental health program on guidance for climate resilient health facilities • WHE has supported 10 countries to map all available financial and technical resources that can be applied to emergency preparedness strengthening and IHR (2005) implementation through the WHO REMAP tool and process. This tool and process has been adapted to support countries to carry out mapping of technical and financial resources for COVID-19 preparedness and response action and WHE is providing support to countries for this in collaboration with the World Bank GFF and DEVCO • WHE has supported countries to plan and implement 136 simulation exercises and 65 after-action reviews to date (as of August 2020) in order to strengthen national, regional and global emergency preparedness. The simulation exercises and after-action reviews have supported countries to identify critical gaps and implement measures to strengthen capacities. • WHE is supporting Member States to address emergency preparedness risks and hazards at the animal-human interface including zoonotic diseases. Support includes implementation of One Health National Bridging Workshops which strengthen alignment and coordination between national human and animal health sectors for preparedness, and One Health Joint Risk Assessments which focus on one or more specific priority zoonotic disease hazards and bring together expertise from all relevant sectors. National data from Joint Risk Assessments are used to estimate risk and propose options for management and risk communication. As of 7 October 2020, 32 National Bridging Workshops have been implemented, and 21 Joint Risk Assessments have been implemented. • Through the Pandemic Influenza Preparedness (PIP) Framework, WHO received >$220 M since 2012 to implement activities that strengthen national, regional and global preparedness. Gains made include an additional 12 countries with recognized National Influenza Centres that contribute to the Global Influenza Surveillance and Response System, and 131 countries with stronger participation in global influenza surveillance including 77 that newly participated in virus sharing, virological or epidemiological data reporting. 42 countries published influenza disease burden estimates to inform disease control strategies including 29 low and middle income countries, 2 achieved WHO’s standards for having a stable, well-functioning and integrated regulatory system for medicines and vaccines, and 26 advanced their pandemic response plans. • Under the PIP Framework, WHO has signed legally binding contracts for access to the following pandemic influenza response products, to be made available when the next influenza pandemic strikes: 10% of pandemic vaccine production (approximately 8% of which will be donated); 10M treatments courses of antivirals; 25M syringes; and 250,000 diagnostic kits. Using current influenza vaccine production technologies, 10% represents about 420M vaccine doses; this could significantly increase when new technologies come online.
| Preparedness planning and capacity building will be closely integrated with the Organization’s work in health systems strengthening. | Unspecified | • WHE has coordinated closely with the Organization's health systems division to better integrate health system elements within emergency preparedness, IHR (2005) monitoring and evaluation tools, processes and measures. This includes integration of indicators and questions to capture health system considerations within the SPAR and JEE tools. WHE is also working with the health systems divisions to further enhance IHR (2005) monitoring and evaluation tools/processes in line with lessons that have already emerged from COVID-19. • WHE is working closely with health system teams to strengthen health systems for health security for preparedness, UHC and SDGs. WHE is also working with HS on PHE indicators and as well resilience. • WHE published the Multisectoral Preparedness Coordination Framework to support health system strengthening through engagement of non-traditional health stakeholders, including foreign affairs and parliaments in emergency preparedness. • WHE has published a pandemic influenza preparedness planning package, which supports WHO Member States with the necessary guidance for strengthening their national capacities, including the development and exercise of national influenza pandemic preparedness plans, to prepare for and respond to pandemic influenza. This package consists of a checklist for pandemic influenza risk management (2018), essential steps for developing or updating national influenza pandemic preparedness plans (2018) practical guide for developing and conducting simulation exercises for pandemic influenza (2018), and non-pharmaceutical public health measures to mitigate the risk and impact of epidemic and pandemic influenza (2019). • In 2019, recognizing the need for a global roadmap to strengthen global influenza research and development and national capacities, WHE launched the Global Influenza Strategy 2019-2030 with two high-level outcomes for 2030: better global tools and stronger country capacities. The strategy aims to drive high-level action towards strengthening influenza prevention, control, and preparedness as a model for broader respiratory disease preparedness. • WHE continues to monitor the global circulation of influenza, conduct on-going risk assessments and develop bi-annual seasonal influenza vaccine strain recommendations for the Northern and Southern Hemispheres. • WHE continues to enhance the Global Influenza Surveillance and Response System, including through the recognition of additional National Influenza Centres, to serve as the global platform for influenza virological and epidemiological surveillance as well as the alert system for the emergence of novel influenza viruses. GISRS has now grown to over 150 institutions in 122 Member States. These NICs form the backbone of the national laboratory diagnostic system in many countries and are the first to establish diagnostics for emerging pathogens. • WHE mobilized partners and resources to develop global guidance documents and tools, and conducted activities across several key areas of work related to laboratory and biosafety strengthening. National laboratory services capable of providing reliable results in a safe and timely manner are at the center of any outbreak detection mechanisms and disease control strategies. Activities conducted were implemented to strengthen and sustain core capacities of national laboratory systems, and accelerate countries progress towards compliance with the International Health Regulations (IHR 2005) in this critical areas. • Through the Pandemic Influenza Preparedness (PIP) Framework, WHO received >$220 M since 2012 to implement activities that strengthen national, regional and global preparedness. Gains made include an additional 12 countries with recognized National Influenza Centres that contribute to the Global Influenza Surveillance and Response System, and 131 countries with stronger participation in global influenza surveillance including 77 that newly participated in virus sharing, virological or epidemiological data reporting. 42 countries published influenza disease burden estimates to inform disease control strategies including 29 low and middle income countries, 2 achieved WHO’s standards for having a stable, well-functioning and integrated regulatory system for medicines and vaccines, and 26 advanced their pandemic response plans. • Under the PIP Framework, WHO has signed legally binding contracts for access to the following pandemic influenza response products, to be made available when the next influenza pandemic strikes: 10% of pandemic vaccine production (approximately 8% of which will be donated); 10M treatments courses of antivirals; 25M syringes; and 250,000 diagnostic kits. Using current influenza vaccine production technologies, 10% represents about 420M vaccine doses; this could significantly increase when new technologies come online.
| The Programme’s work on preparedness and disaster risk reduction will be finalized following the Health Assembly’s consideration of the report of the IHR Review Committee. | Unspecified | To better align the RC recommendations and accelerate the implementation of the Sendai framework: • WHO published the Health Emergency and Disaster Risk Management (Health EDRM) Framework and translated it into all UN languages. WHO is supporting countries to implement this framework and enhance emergency preparedness and disaster risk management. • WHO published the health EDRM glossary to harmonize the language/concept/terminology of emergency and disasters across the board. This is in line of the international definitions accepted by all the agencies. • WHO is finalizing a guidance for the countries to facilitate health sector implementation of Sendai and also to align country level reporting.
Global Health Emergency Workforce | Establishing national emergency medical teams that can deploy locally in high-vulnerability countries prioritized. | Unspecified | For the last five years, the Emergency Medical Team (EMT) Initiative continues to focus on training and capacity building of national emergency medical teams; • Over 23 500 EMT responders from national EMTs are engaged in national capacity building activities. • Over 250 national & international health responders have been trained on EMT coordination. • The EMT initiative is working with all 15 countries with the highest risk index worldwide. • There are 30 Internationally Classified EMTs globally. These teams have over 4 000 readily available EMT responders with nearly 100 other teams are in the mentorship process and receiving direct support to reach the minimum standards to achieve classification.
NB: Health Cluster information is reflected in the HR section | Secretariat of the Global Outbreak Alert and Response Network strengthened, and its advocacy work enhanced, to enhance the capacity of partners in the Response Network to systematically support WHO and Member States in alert detection, risk assessments and rapid response activities. | Unspecified | Completed. Weekly meetings (Tele & video conferences) organised, sharing of information and operational discussions. Steering committee active (including remotly due to Covid 19 constrins). Focal points are operational in the regions and regular update of the GOARN Knowledge Platform is effective. Achieved: Trainings are organized to ensure team operational cohesion (virtual “sense-making” retreats, as part of the GOARN Outbreak Response Leadership Training Programme for COVID-19 responders, virtual GOARN Orientation to International Outbreak Response training, Completed the 6-week ArcGIS Foundational Training Programme, in partneship with ESRI for insitutions working on COVID response. Launched new eModules on the social determinants, culture and well-being for contact tracers) and knowledge (The Go.Data team is currently supporting over 55 Go.Data projects worldwide, and is coordinating rollout activities in a close collaboration with the WHO regional offices.”).

## IOAC recommendations
AREA | IOAC RECOMMENDATION (REFERENCE) | Status
Structure | To share the WHE Programme roll-out plan with WHO staff in the country offices (EB140/8) | Completed as part of the 2016 roll-out of the programme.
Structure | To establish a baseline level of emergency operational and management capacity at country level by including key senior staff positions (deputy WR when the WR assumes the IM role) in biennial budgetary planning for the COs in priority countries (A70.8) | In progress. In EMRO, the baseline level of emergency operational and management capacity is established at country level by including key senior staff positions. It will be further adjusted in line with the CFR conducted for the EM COs in 2019. US government funding cuts place this recommendation at risk. Between 2017-2018 SEARO conducted 4 Operaitonal readiness workshops to build capacity within the Regional Office, and all 11 WCOs on WHO's ERF. Furthermore, as part of the WHE WHE internal roster for deployment, SEARO completed an in-depth review and shortlisted 23 staff deployable immediately. For the COVID-19 Pandemic response, in 6 of 11 WCOs either WR or Deputy WR has assumed the role of incident manager, while in the remaining 4 WCOs it is taken ip by the WHE lead and by MO-CDS in 1 WCO. CBM for EURO, for the two protracted emergencies in TUR and UKR, includes WHE Team Lead positions at P5 level. They take over the role of the IM (when needed), in support of the WRs. In AFRO WHE team leads have been filled with P5 in 5 high priority countries i.e. Ethiopia, Nigeria, South Sudan, the Democratic Republic of Congo. These staff support the WR in coordination and lead emergency preparedness and responses In PAHO WHE Team Lead positions have been filled in the one priority 1 country (Haiti) and one of two priority two countries (Guatemala). The positon in Colombia, the other priority two country will be filled by last quarter of 2020. The functions are currently being implemented on an interim basis by a senior P4 level staff. These staff members normally assume the IM or Deputy IM role as needed. Since 2016, PAHO has conducted at least one operational readiness training/meeting annually with varying participants from RO and CO, including WRs, WHE Focal Points, Administrative Officers and other technical personnel
Structure | To use IMS for acute emergencies and focus on surge of staff and partners in humanitarian crisis settings (A70/8) | In line with the ERF, all high graded emergencies have been managed through WHO’s Incident Management System to fulfil its six critical functions (Leadership, Coordination, Information and Planning, Health Operations, Operations Support & Logistics, Finance & Administration. At country level, setting up an IMS was achieved within 72 hours in 63% (100%) of events in 2017 (2018). External partners and networks - e.g. from the Global Outbreak Alert and Resposne Network, the Global Health Cluster, or the Standby Partnership arrangement - have been used where feasible and appropriate to strengthen and/or complement IMS. The relationship between Cluster and IMS has been examined by several reviews to streamline the coordination mechanism in humanitarian settings where both health cluster and incident management work side by side. The evaluation recommendations how the Health Cluster best engages with the response pillars will be incorporated in the next revision of the ERF.
Structure | To develop a standard template for DOA and adopt all three levels of the Organization (A70.8) | Completed. The updated emergency rules on Delegation of Authority is published at eManual XVII.2.3, including the operational guidance within GSM system.
Structure | To clarify and adapt reporting lines and performance management of staff deployed as surge capacity specific emergency contexts to ensure operational effectiveness (A72/6). | In progress. Staff are expected to attend on-arrival briefing which includes briefing with supervisor on reporting lines and objectives that form part of the performance evalution process. There is an ongoing intiative to ensure peformance evaluations are shared with HR Emergency team for roster management.
Structure | To make further efforts to promote Delegation of Authority, to familiarize all levels of staff with it and to empower WHO representatives and managers (EB144/8), (EB146/16) | Completed. Since 2016, face-to-face training workshops have been conducted regularly with major regional offices, mainly targeting the administrative staff and programme managers. SOPs for Emergencies is also an integral part of WR orientation every year. A standard set of training materials for SOPs for emergencies have been developed, including online training module at OpenWHO.org as a part of pre-deployment training. With the evolvement of COVID19, further development of online packages is under way.
Leadership | To improve coordination among the departments of the WHE and across the three levels (EB140/8) | In progress. Technical departments conduct annual coordination meetings with participation of 3 level staff, on thematic subjects. Coordination and close collaboration among WHE technical units and other EMRO Departments have been duly established and maintained. COVID-19 reponse reflects this progress well, with each WHE Unit and EMRO Department well represented in the IMST At SEARO there is strong inter-departmental collaboration between WHE and Health Systems and immunization teams. In the context of the current COVID-19 Pandemic, HSD, IVD, Research teams actively participate in the IMST and lead specific aspects of WHO's response. There is strong coordination between PAHO Health Emergencies, with regular coordination meetings with the unit chiefs and team leads. Additionally, between 2016 and 2019,the department has had at least one annual joint meeting with personnel across the department for perfromance review and planning. There is also ongoing inter-departmental coordination with areas outside PHE, for example, during peace time on influenza, yellow fever, other emerging infectious diseases, migrants health, climate change, indigenous populations and Disaster Risk Reduction. During disaster response, there is active participation from all relevant technical departments, according to the type of hazards. In the context of the ongoing COVID-19 pandemic, all technical departments are actively part of the Incident Management Support Team.
Leadership | To improve both internal and external communication about the WHE Programme (A70/8) | In progress.
Leadership | To accelerate implementation of the WHE at country level (EB140/8) | In progress. In EMRO, there has been good progress across made in institutionalizing WHO's work in emergencies across all main areas of intervention: prevention, preparedness, detection and response. WCO structures have evolved and have been capacitated to accommodate the emergency work - although this is now under threat, due to resource limitations. Examples of progress made: 18 Member States have completed JEEs and NAPHs; 19 MS now have functioning epidemiological surveillance for SARI & ILI and virological surveillance for influenza; 7 countries have established event-based surveillance; timely and effective response to acute emergencies (e.g. cholera in Sudan in 2019) and protracted emergencies (e.g. consultation rate in Syria within internationalk standards). In SEARO, all 11 WCOs have at least one WHE focal point, however country business has only been partially implemented due to lack of adequate and predictable WHE AC Flexible funds. In EURO, the CBM has been fully implemented in line with EURO business model, i.e. concentration of techncial capacity at HUB level to cover a group of countries. In AFRO CBM implementation has been significantly implemented by establishing all the key positions in the countries and filling some of them. However, partial implementation is due to inadequest financial resources. Review of the country business model (CBM) for priority 1, 2, and 3 countries revealed the CBM was mainly adopted to meet the needs and existing structures in the country offices. In many priority 2 and 3 countries, only one Technical Officer was planned to cover all PAHO Health Emergencies program areas (PA). By end of 2018: Increased number of staff positions for the health emergencies Program at country level (220%: from 5 to 16 positions). Due to requirement to align with PAHO's corporate as well as CO HR Plans, numerous hiring freezes and financial challenges, there are currently only four positions occupied at country level (HTI, GTM, PRY, NIC). However, PAHO has complemented the staff positions with consultants to ensure operational coverage at country office levels, particularly in the 16 health emergencies priority countries. Additionally of 38% of PHE's 76 filled staff and consultant are currently decentralized at subregional or CO level providing direct operational support to the countries
Leadership | To embed transparent and proactive communication across the Organization, for both internal and external audiences, especially with regard to the strategic vision, structure, function and deliverables of the WHE Programme (EB142) | Completed. There are weekly coordination meetings between the HQ Senior Management and Regional Emergency Directors. At least bi-annual retreats have also been organized to align strategic aspects of the programme.
Leadership | WHO’s Emergency Response Framework (ERF) should be consistently followed by staff at all levels of the Organization. (A71/5) | ERF and the emergency SOPs are consistently applied across the Organization for the management of all acute events, regardless of hazard or cause. They form the basis of WHO's risk assessments and grading processes, implementation of response activities and evaluation of performance. Standard indicators are being collected in EMS2 and used to regularly review ERF. Training programs on ERF/IMT are being available on iLearn and OpenWHO; physical training courses have been held in major offices and many suboffices. Consistency and quality of ERF implemetation is variable though, particularly when subject matter experts are expected to manage acute events because of the absence of a group/unit dedicated to acute event management and thus throrougly familar with this task.
Leadership | Transparent and documented three-level decision-making to describe any required adaptation of roles and responsibilities as outlined in the ERF. (A71/5) | Completed. All risk assessment and grading processes are three level decisions recorded in EMS2. At the grading call, the three levels will discuss the most appropriate operational setup, including roles and responsibilites of country office, regional office and HQ. The traditional roles assigned by ERF - G1 led by country office, G2 led by regional office, G3 led by HQ - have been gradually replaced by a more dynamice model where key functions are assigned to major offices according to capacity and needs. This model has been discussed as part of the ERF review and will be incorporated in more detail in ERF3.
Leadership | WHO’s leadership in the Inter-Agency Standing Committee for infectious disease events. (A71/5) | Completed. The IASC policy paper has been updated (IASC, Protocol for the Control of Infectious Disease Events. Humanitarian System-Wide Scale-Up Activation, published April 5, 2019) As the Inter-Agency Standing Committee Cluster Lead Agency for Health, WHO has led health sector coordination through 30 Health Clusters (28 national, 2 regional), targeting the health and humanitarian needs of 68 million people, in partnership with over 900 national and international partners. In collaboration with national authorities, the Inter-Agency Standing Committee, the United Nations Office for the Coordination of Humanitarian Affairs and other global partner networks, WHO is actively strengthening context-specific coordination and multisector collaboration to achieve better health outcomes. In response to the Covid-19 pandemic response, the Strategic Preparedness and Response Plan developed by WHO has subsequently informed the Covid-19 Global Humanitarian Response Plan, a joint effort by IASC agencies with a humanitarian mandate to analyse and coordinate the response to the direct public health and indirect immediate humanitarian consequences of the pandemic on the population in countries already facing other crises. Implementation builds upon existing humanitarian mechanisms and process including the Health Cluster to meet COVID specific needs through a multi-partner, multi-sectoral response to the pandemic. (HIM)
HR | To assure the high quality of the HCCs roster through adequate assessment of candidates, improved performance management of HCCs, training on field-level health cluster coordination prior to deployment, and adequate support on deployment. (A71/5), (EB146/16) | Completed. HCC roster candidates are selected through WHO's virtual interview process (SONRU platform) with candidates assessed against a set of technical and competency based questions set by the Global Health Cluster reflecting the essential requirements for Health Cluster Coordination core functions. Candidate assessement is undertake jointly by the GHC and HRT. Candidates selected for the roster must complete the Health Cluster Coordination E-learning course before commiting to an HCC contract. The GHC provides pre-deployment technical briefings. Once deployed, HCC performance management is overseen by first and second level supervisors (respectively Head of Country Office & Regional Emergency Program Manager) as per WHO HR policy. The GHC proivdes remote support to all HCCs through regular thematic webinars and individual support to enhance knowledge and appliatication of sector policy and guidance. GHC support missions are undertaken at the request of country or regional office to provide address HCC performance issues.
HR | To increase the supply of a diverse pool of competent staff to lead emergencies, further develop incident managers’ rosters and create deputy incident manager posts that are preferably filled by under-represented suitably skilled groups (A72/6). | Completed. Regions indentify and deploy competent staff to lead emergecies for extended periods. Internal and external rosters of IMs are in place. Updates from WPRO: In June 2018, names of 5 staff from WP RO and CO were submitted to HQ (that can be deployed rapidly when needed). In Nov 2019, WPRO submitted a list of currently existing WHE stafff members in the Professional category for inclusion in the WHE Global Internal Roster, with a handful that can serve/fulfil the IM function. A roster of WHE and external candidates are also in place and and continously updated to include additional new hired consultants. WHE endeavours to the provide opportunity for learning and training during actual emergency events to build the capacity of staff and their effectiveness to serve the IM role. Deputy IM posts have been created and these are filled by WHE and non-WHE staff as a means of being able to scale-up and provide support and back-fill for incident manager's as needed. Updates from AFRO - Completed. Afro completed an internal roster validation process which was approved by management in October 2019. The roster covered 63 IMS functions and had 438 deployable candidates including 26 Incident Managers. In AFRO, the management of major incidents has provided an opportunity to use the function of Deputy Incident Manager and 3 different staff members successfully played that role. Work is in progress to put in place external roster.
HR | To give high priority to its country offices in fragile States and accelerate the implementation of the WHE country business model that includes plans to increase HR capacity and staff trained in emergency response at the country level (A72/6), (EB146/16) | In progress. EURO: Completed. All CBM positions are in place. In addition to TUR and UKR, EURO has CBM positions also in other 13 vulnerable countries, for a total of 33 positions. ERUO has updated/corrected the CBM positions. WPRO: In WPRO, there is only one Priority 2 country which is the Pacific Island Countries (PIC) while there are 8 countries listed under Priority 3 countries (these are countries with WHO CO presence such as Cambodia, China, Lao PDR, Malaysia, Mongolia, Papua New Guinea, Philippines and Viet Nam). Since the transition to WHE, WPRO has adapted the Country Business Model concept applicable for the Western Pacfic Region context based on the following considerations: (1) Addressing the expectations of Members States building on past experience and lessons learnt; (2) Aligning with past staffing levels; and (3) Differing country capacities and context. From the initial 44 health security and emergencies positions in countries in 2017, additional 6 new positions under WHE were created in 2018 (3 in PIC and 1 each in PHL, PNG and SLB). These additional positions are considered core positions and funded by WHE flexible funding. There were also few projected-funded positions that were created in 2019 in PIC and LAO for a limited-time duration. EMRO: In process. While HR is indeed giving high priority to its WCOs the CBM is not fully applied in all countries. More feedback could be provided by WHE on implementation of the CBM to enable HR conduct a more precise assessment. SEARO: In process: In process - though countries like Bangladesh, sub-office at Cox's Bazar who have funds, have been able to roll out the CBM, this has not been possible across the board due to unpredictable and insufficient WHE AC flexible funding. AFRO - Completed. In the context of CBM implementation, countries in AFRO were put in 4 categories, 1 and 2 being for the most fragile countries. These countries were prioritized in the recruitment of 10 WHE senior staff such as Health Cluster Coordinators and WHE Team Leads...
HR | Recruitment in priority country offices should not be held back by the transformation agenda (A72/6) | Completed.
HR | To develop a system of performance management that includes 360-degree feedback and introduces the element of assessing how outcomes have been achieved. (A72/6) , (EB146/16) | In Process: WHO is in the process of launching an RFP to replace the present performance evaluation system and will be looking into the introduction of a 360 degree feedback and a mobile applications functionalities. In addition, the present system (ePMDS) has been amended this year to include (i) a field to link each individual Objective with the GPW13 and PB Outputs and (ii) a field to indicate the amount of time spent on each Objective. WHO aims at assessing whether the higher level objectives have been met and whether there has been deviations.
HR | To conduct annual or biennial staff culture survey and supports the Director-General’s plan to undertake a similar survey on a regular basis and pulse surveys at regular intervals (A72/6) | Completed. Cultrue/Pulse check surveys were conducted. Culture survey results are here: https://intranet.who.int/sites/transformation/culture/surveys/ Link to the pulse check survey results: https://intranet.who.int/sites/transformation/pulse.shtml
HR | To establish a promotion system that rewards high-performing staff and motivates others (A72/6). | Not started. This part refers to rewarding and motivating staff through a 'promotion system'. The policy on Recognizing Excellence recognizes staff members who have made an exceptional achievement and they are awarded certificates, medals and pins together with three days special leave. The policy does not make provision to 'promote' staff members and this has to be taken forward in the context of the UN system HLCM.
HR | To develop an action plan for implementing improvements against the outcomes of the survey, and that performance on this plan be reported within the IOAC reporting framework by WHE Programme leadership (A72/6). | Not started.
HR | To take transitional steps to ensure that the centralized corporate structure does not dilute the particular and immediate needs of emergency operations and risk mitigation. (A72/6) | Completed. The Incident Management System (IMS) as defined by the Emergency Response Framework (ERF) ensures empowerment and separation of the Incident Management Team (IMT) in the field (also, the Incident Management Support Teams at HQ and RO) from the corporate structure. The Contingency Fund for Emergencies (CFE), the no regret policy and the emergency SOPs give the required tools and resources for the IMTs and the IMSTs to respond effectivity to any immediate needs. HEO in collaboration with CRE have developed several tool, including a new section of the ERF and the eManual to make sure that risks are mitigated at the onset of the activiation of the IMS for any emergency.
HR | To accelerate the recruitment process at the country level, so that the staffing capacity is brought up to 75% of the total planned positions. (EB144/8) | In progress. 73% of the planned positions at country level were occupied as of December 2019.
HR | To strengthen technical expertise across the Organization and develop a policy for surge capacity especially as regards health operations leads, senior epidemiologists and infectious disease specialists (EB144/8). | In progress. The draft Surge Policy will be discussed at an upcoming GPG.
HR | To leverage WHE Programme’s best practices across the Organization, especially for WHO representatives, and complement corporate programmes and initiatives in staff development and learning, human resources and performance management (EB144/8). | This is with reference to WHE Programme's best practices - not relevant to the functions of the TAD Team. However, the stafff learning and development function is managed through the Global Learning and Development Committee (GLDC). A budget of $8M is available for the biennium and teh funds are allocated to global and regional projects based on priority areas of learning. the global Leadership Pathways initiative is being managed by AFRO and targets senior managers. Please see comments under line 21 above for comments on performance management
HR | To conduct HR benchmarking exercise (EB140.8) | Not started. HR benchmarking is quite vague and touches all the different HR function ranging from Recruitment and selection to retirement. In TAD, no benchmarking exercise has been conducted until now in areas of staff learning and development and performance management. However, it is worth highlighting that the JIU has produced a report on "Policies and platforms in support of learning: towards more coherence, coordination and convergence" after a survey they carried out across the UN System. They have made recommendations based on their findings: https://www.unjiu.org/sites/www.unjiu.org/files/jiu_rep_2020_2_english.pdf . The report will be submitted to the Global Learning and Development Committee (GLDC).
HR | To improve the recruitment rate: HQ 70%, RO 50%, CO35% position filled as of Dec 2016 (EB140.8 and A70.8) | Completed. HQ 76%, RO 67%, CO 73% filled as of Dec 2019.
HR | To stabilize short term contractual arrangements through long-term sustainable financing (A70.8) | In progress. Longer-term sustainable financing is critical to stabilizing contracts that are short-term due to funding constraints - while multi-year partnerships have supported the stabilization of some contracts, not all contracts have been possible to stabilize. For some contracts including those for emergencies in the field, such as the North Kivu EVD outbreak, the nature of the funding (humanitarian) meant that a stabilization of contracts was impossible. Funding with a duration of anywhere from 6-12 months, does not allow for longer term contracts, especially when the funding is received at varying times during the response. This is a real and re-occurring problem for WHE when responding to health emergencies. For HQ, fundraising to cover salary costs remains a challenge – may donors will not want to cover HQ salary costs or only in limited form through their contributions for the programme, thus making WHE over reliant on what is raised as flexible funding for staff salaries.
HR | To invest and support national staff (A70.8) | In process. The recently revised policy on NPOs who apply for international professional positions will contribute to the professional growth and career of the nations staff. Some examples of additional suport measures from AFRO, EMRO, EURO and SEARO as follows: AFRO - National staff were supported mainly through training workshops, online learning and long duratopm emergency deployments in both field and regional office. EMRO: The Country Functional Review exercise has been completed for all EMRO WCOs. In that perspective, full consideration has been given in increasing national staff capacity. HR has provided input in that respect on all organograms and currently in process of implementing those in cooperation with the WCOs. EURO: National staff receive trainings on various areas related to health emergency work. SEARO: National staff has been supported where possible for recruitments WPRO: Since the transition to WHE, there had been two successful recruitments of a national staff to an international position in the Regional Office. We continue to support the capacity-building of national staff to increase their readiness and greater chances to be selected to international positions.
HR | To expand the recruitment pool rather than limiting to internal WHO staff (A70.8) | Ongoing: External, partner rosters in place to support requests for external surge capacity. In addition for specialized functions, technical leads recommend external expertise for recruitment
HR | To deploy Admin staff at the beginning of an emergency activation and during response (A70.8) | Ongoing. Admin staff are regularly deployed at the onset of an emergency
HR | To train WR for emergency response and prioritize WRs with experience in humanitarian crisis for emergency settings (EB140.8) | In progress. In 2018 WHE developed a Learning Strategy and created a Learning and Capacity Development Team which has prioritized the development of flagship training based on the Incident Management System (IMS). The first training and table-top exercise conducted by the LCD team was in December 2018 for the WHO Heads of Country Offices in WHO HQ. Learning from the feedback and needs, the training has been further developed and defined. Over the period 2016 – 2020: A total of 236 staff have received face to face training on emergencies in pre-deployment training and Leadership in Emergencies training. A further 1450 WHO staff have completed on-line training on the Incident Management System (IMS) Tier 1 and Tier 2 hosted on OpenWHO. In 2019 the online IMS training was made mandatory for deploying staff and colleagues from partner organizations amounting into a total of 25 000 enrolment in the courses in 6 UN languages and Portuguese. Since its formation in October 2018 LCD provided training in Leadership in emergencies and IMS training workshops to 75 staff across all regions (the workshops were held in Philippines, Senegal and Jordan). The LCD is currently engaging with colleagues in AFRO, EMRO, EURO and WPRO to extend IMS and Leadership in Emergencies Training in these regions. Training will largely de delivered remotely online. This will involve the enrolment of a further 50 colleagues from Eastern Mediterranean and further cohorts from the African region. It is anticipated that this programme will be rolled out across all regions in 2020 and 2021. The programme including the face to face ocmponents will be trabsformed online through vurtual interactive classes, vurtual learning labs, webinars and virtual simulation exercises by the end of 2021 to address the challenges posed by the COVID19 pandemic, as well s to scale up the number of users worldwide.
HR | To give special considerations and incentives to staff working in emergencies at the most challenging duty stations (EB140.8 and A70.8) | In progress. We are currently working with ICSC in package of entitlements. Some examples of additional inititatives from the regions below: EURO: NA WPRO: Completed. Staff deployed to hardship duty stations are encouraged to take their leave entitelments. Staff deployed to emergencies are also availing their compensatory leave entitlements. EMRO: Completed. SEARO: Ongoing - this is being done as and when needed and requested. In the specific context of COVID-19 where many SSAs are working on the frontline conducting contact tracing and surveillance, it would be useful to have a corportate policy on incentives and insurance for SSAs. This has been currently been implemented by WCOs on a case by case basis. AFRO - Completed Staff deployed to hardship duty stations are encouraged to take their leave entitelments and also compensatory leave entitlement when applicable.
HR | To implement staff rotation policy in hardship duty stations (A70.8) , (EB146/16) | EURO: NA WPRO: Currently, Port Moresby and Honiara are D duty stations while Kiribati and FSM are C duty stations. All our duty stations are family duty stations. In addition to complying with global geographical mobility policy, WPR has its Regional Mobility scheme. Senior management reviews, on an annual basis, staff members who are reaching 5 years stay or more in the same duty station (3 yrs for PNG) and consider where they could be moved within the region or outside the region. EMRO: Completed. SEARO: Ongoing - this is being done - several WHE staff has been brought to SEARO on rotation including PAMs for IHM, and EMO from hardship duty stations. AFRO - In process Rotation in hardship duty station is implemented but not at regular intervals.
HR | To develop WHO’s own ad hoc incentives and appropriate leave policies specifically for staff working in emergencies (A70.8) | Completed. Corporate compensatory leave policies have been developed for staff on duty travel and those working in their duty stations on emergencies for extended periods of time. In addition, some duty stations also introduce compressed work schedules and time off for national staff. Some regional examples as follows: AFRO: Compensatory leave policies have been developed for staff on duty travel and those working in their duty stations on emergencies for extended periods of time. In addition AFRO has introduced time off for national staff. SEARO: Compensatory leave policies have been developed for staff on duty travel and those working in their duty stations on emergencies for extended periods of time. In additin, some duty stations have also introduced compressed work schedules and time off for national staff. WPRO: Staff deployed to emergencies for extended periods are availing their compensatory leave entitlements. In addition, a rotation schedule among IMS/IMST members are in place to prevent burnout and fatigue. Members are also constantly reminded to take some time off.
HR | To provide psychological support and protection against workplace harassment to staff working in the field (A70.8) | Ongoing. Staff Health andf Wellbeing (SHW) is regularly offering breifings to staff being deployed to regions and countries, including in emergency response settings. When alerted about specific cases, by either staff members involved or the administration, SHW staff take action to help address the situation, in collaboration with the releavnt parties at HQ or at the regional and country level.
HR | To explore flexible contractual arrangements and roster arrangements for emergencies. (EB142/8), (EB146/16) | Completed. Roster arrangements have been developed for emergencies.
HR | To examine the capacity for HR planning, recruitment and management and propose directions for improvement at the organizational level for the WHE Programme. (EB142/8) | Completed. Each Incident Management Support Team at HQ, RO and CO is capacitated with technical and administrative support required for these actions. The three-levels of the organization work together to ensure this support is available where gaps are indentified during an emergency. WPRO: Ongoing. The WPRO WHE internal roster as well as the external roster of experts are in place and continously updated. A WPRO General Service Emergency Roster is also in place and aprpoved by the RD on Oct 2019. RED with the support from WHE AAs manage this GS roster for emergency. WHE has been providing opportunity for learning during actual emergency events to build their capacity for both P and G staff support. AFRO - Completed. In AFRO, there is an agreement on the importance of the Planning Officer function, especially during emercy responses. In order to reinforce HR management efficiency and effectiveness, HR Officer position have been created and filled in high priority countries. Fast track recruitment processes and emergency SOPs are used often and correctly.
HR | To benchmark HR incentives, and appropriate R&R in emergency settings against those of peer UN agencies and development organizations, commensurate with the intensity of work. (EB142/8), (EB146/16) | Ongoing. HR incentives and R&R are monitored at the country level and recommendations made in accordance with ICSC guidelines. In addition, adjustments are made during specific response events, following consultation amongst the agencies.
HR | To complete the recruitment to fill the dedicated full time HCC and IMO posts at country level and ensure satisfactory information management and coordination (A72/6) | In progress. Since the inception of the WHE program, substantial investment has been made to secure dedicated full time HCC and IMO capacity to enhance health cluster performance. As of June 2020, 22 of 30 (73%) health clusters have a dedicated HCC and 16 of 30 (53%) health clusters have a dedicated Information Management Officer at national level, compared to 43% HCC and 39% IMO in June 2016. This improvement has been achieved through targeted activities including (1) recognition that the national level HCC post is a key function within WCO emergencies staffing structure & country business plan; pro-active recruitment process to establish global HCC network offering longer term contracts (2) strengthening strategic partnerships to secure standby capacity for both functions (3) investment in GHC Capacity Development Strategy to systematically deliver competency based training for HCCs and IMOs to enhance knowledge & skills and offer career development pathways. * (5) Joint Health Cluster Coordination and Information Management Trainings were conducted in 2016-2019 in English and French. 147 personnel were trained that were fully or partially dedicated to HC work. https://www.who.int/health-cluster/capacity-building/training-courses/en/ * - E-Learning course for Health Cluster Coordination. This 17-module course is suitable for both WHO staff and partners, including Ministry of Health focal points, who are currently or intend to be involved in partner coordination activities. Since its launch December 2019, over 24,000 people have enrolled for the course with OpenWHO (https://www.who.int/health-cluster/capacity-building/e-learning/en/). * - Simulation-exercise trainings – at the request of WHO and partners, 3 new scenario- based trainings have been developed in collaboration with WHO Regional Offices and partners. These trainings can be adapted to regional contexts and are targeted at WHO staff, national authority personnel responsible for humanitarian health action and international and local partners. Planning for 1 SIMEX to be delivered in SEARO commenced in January 2020 but has been delayed due to Covid-19. https://www.who.int/health-cluster/capacity-building/simulation-exercises/en/ - The GHC Information Management Task Team facilitated an online pilot training on Health Information Management between April and July 2020. The training consisted of 12 online thematic sessions which were regularly attended by over 25 participants. At the end of the training, participants took part in group projects revolving around the visualization and analysis of PHIS data in a training scenario. The second wave of online training started on the 3 August and similarly consists of weekly thematic courses which will last until 23 October. More than 26 participants are currently taking part of the training through two weekly classes. https://www.who.int/health-cluster/news-and-events/news/health-information-management-trainings/en/. Whilst progress on recruitment and retention of HCCs and IMO has been positively acknowledged by internal and external stakeholders it should also be noted that progress on both HCCs and IMOs has plateaued over the last 2 years. Whilst this is partly due to anticipated staff turnover, structural aspects also play a significant role including (1) changes in the country business plan model with appears less enabling of funding HCC and IMO functions resulting in increased hiring against short-term contracts linked to event based funding or use of short-term standby partner capacity (2) protracted recruitment.
Business Processes | To specialize expertise of the WHE Programme operations support and logistics team and the emergency management field experience should be leveraged within the transformation agenda and the effectiveness of operations should be maintained (A72/6). | Completed. The WHE programme operations support and logistics has transformed rapidly in the wake of the COVID-19 response. These changes have seen an expansion of the core team, the temporary restructuring of the group to sub units that cover demand, supply, logistics, operations support to the three inter-agency procurement consortiua (diagnostics, PPE and Biomed) as well as establishing a technical support network to advise on the design and construction of treatment centres. The group also accomadated an COVID-19 coordination cell, including 17 staff from WFP, 4 from UNICEF, 1 from OCHA and 5 from CHAI. So far this construct has delivered 277 Million US of supplies to 179 countries with the WHO procured cmponent accounting for over 50% of the total.
Business Processes | To carry out further efforts be to streamline the process and accelerate engagement to support critical emergency responses (A72/6). | Completed. The continuous improvement activities to streamline core services process have been ongoing since 2016. Feedback has been taken from a variety of sources, including operational review of major emergencies, subject matter experts, ongoing basis during critical emergencies. This has resulted in continuing update of eManual XVII, including templates and tools. An enhanced operational toolkit is also under development to serve as one-stop shop of emergency-related templates. (JU)
Business Processes | To implement emergency measures under FENSA across the regions. (EB142/8), (EB146/16) | In progress. New FENSA emergency processes have been rolled-out and supported by the PNA unit and a focal point in WHE HQ. Training has been made in some regional offices to familiarize with these processes and additional ones are expected. The revision of the Guide for Staff and the Guide for NSA will better articulate these requirements. An online training on emergency SOPs will also incorporate FENSA provisions.
Business Processes | To caution when operating the new business rules within the existing systems. Business processes must support the WHE Programme based on a no-regrets approach. (EB140.8) | Completed. No regrets policy has been incorporated in teh ERF. HEO in collaboration with CRE have developed a new sections that will be incorporated to the ERF and the eManual to make sure that risk management is systematically applied at the onset of activation of the Incident Management System in any new emergency. This will ensure caution when operating new business rules within the existing systems during emergency response. Now the no regret policy is fully integrated in the ERF second version and in the eManual. Its used showed great improvement for rapid deployment of the WHE response to emergencies (e.g. plague in Madagascar, diphtheria in Bangladesh, Ebola in DRC and COVID-19 response). However, many audits showed that this policy is too permissive, therefore it will be amended to include controls on its use.
Business Processes | To set up a time limited working group dedicated to addressing major issues for streamlining admin and operational systems in an emergency response (A70.8) | Not started yet. This will be addressed as part of the Business Process Optimization of the new ERP project which is planned to take place over the next two years. This will also build on the conclusions from the ongoing transformation process.
Business Processes | To implement automatic activation of the waivers for SOPs in emergencies (A70.8) | Completed. The emergency business rules on Activation are published on eManual XVII.2.2. Once the emergency grading is completed, the SOPs for emergencies are automatically activated. In addition to graded emergencies and protracted emergencies, the following situations can also activitate some SOPs such as CFE request without grading: 1) Field investigation and risk assessment undertaken by the WHO Health Emergencies Programme (WHE) in advance of a grading decision; 2) Early warning issued by relevant authorities to alert of an impending emergency, in particular for natural hazards (e.g. cyclones, drought) and societal hazards (e.g. civil unrest); 3) Suspected public health events.
Business Processes | To apply a fast track recruitment (in advance of funding if required) and shorten the recruitment process, ex Iraq 87 days (A70.8) | Completed. Fast Track Procedures for Emergencies SOP published on 26 November 2016.
Business Processes | To streamline SOP for emergency procurement: increase the expenditure limits in the DOA, apply standard waivers, systematize pre-qualified suppliers, simplify local contracts and payment processes, and fast track due diligence process. (A70.8) | Completed. A policy specific to Procurement for Emergencies was issued in 2017 and has been regularly updated since (available from eManual XVII.9.3.4). Delegation of Authority: Upon grading of an Emergency 1, 2, 3 or notification of pre-graded event, WR, IM or Technical Leader for Response are automatically granted procuremnt authority up to US$ 200k per PO (US$ 500k for catalogue items) against WHE and OCR workplans. Waivers: - Adjudication Report not required for purchases below US$25k. - Competitive bidding is not required and CRC approval before the award of the contract is not required. - When the Purchase Requisition cannot be submitted in time in GSM, the WR or the IM is authorized to send a signed emergency adjudication report and an off-line purchase requisition to Team Lead, SUP/GPL. Prequalified suppliers: WHO has a specific process to approve pre-selected supplier (manufacturers or distributors) according to the WHO Quality Assurance Policy for the procurement of essential medicines and other health products (https://www.who.int/about/finances-accountability/procurement/procurement-of-essential-medicine-policy-16-07-2018.pdf?ua=1) see Chapter 3. In addition and for the purpose of streamlining emergency procurement further, significant efforts have been made to develop Emergency Health Kits (based on LTAs signed with approved pre-selected suppliers). See https://www.who.int/emergencies/emergency-health-kits. Payments: WR or IM is authorized to approve advance payments up to US$50,000 for Grade 3 emergencies, and up to US$20,000 for Grade 1 and 2 emergencies. Due diligence process: When the Procurement Initiator possesses the relevant technical expertise, and provided the goods required are not available from the Catalogue, they may be allowed to purchase items from the product categories that normally require involvement from the Quality Assurance technical network (Medicines, biological products, medical devices, etc.).
Business Processes | To familiarize staff with the emergency SOPs through regular training of operations and administrative staff. (EB142/8) | Completed. Since 2016, face-to-face training workshops have been conducted regularly with major regional offices, mainly targeting the administrative staff and programme managers. SOPs for Emergencies is also an integral part of WR orientation every year. A standard set of training materials for SOPs for emergencies have been developed, including online training module at OpenWHO.org as a part of pre-deployment training. With the evolvement of COVID19, further development of online packages is under way.
Business Processes | To harmonize and standardize DOA and approval responsibilities in the WHO-wide resource planning system. (EB142/8) | Completed. The harmonized DOA and approval responsiblities are outlined in eManual XVII.2.3, including operating modality in GSM.
Business Processes | To strengthen its resource mobilization capacity at country level, and encourage WRs to engage effectively with in-country donor representatives. (EB142/8) | Completed. In recognition of funding decisions being informed, and increasingly decided by donors at country level, WHE has invested in strengthening RM capacity at country level. These investments include the recruitment of dedicated RM staff for priority graded country office operations – 10 priority positions were identified, and out of these 7 were filled. The WHE RM team also deployed dedicated RM staff to work with WRs for targeted responses to develop capacities for engagement of donors and through this, for resource mobilization. WHO will continue to strengthen efforts for RM at country-level to tap into funding for emergencies e.g. ECHO funding and country-based pooled funds such as CERF funding. From 2020, under the new Global RM Strategy there is focus on RM and external relations capacity building in country, particularly where the identified opportunity is greatest and for certain humanitarian donors, where considerable momentum exists such as with ECHO for which WHO has become a strategic partner (as of Jan 2020). For example an external specialist (certified ECHO trainer) has been brought on board to strengthen targeted capacities at country level for stronger and more strategic engagement with ECHO. This approach has already seen some early success.
Business processes | The IOAC encourages WHO to conduct a benchmarking analysis for the supply chain process, to establish key metrics to gauge the timeliness and effectiveness of the process, and to estimate the necessary staffing and corporate investment level. (A71/5) | Completed. Two benchmarking exercises were performed; one in 2017 and one in late 2018. Certain key recommendations from this have been taken forward. In particular, increasing the number of LTA's for supplies, increasing catalogue offerings, expanding operations in Dubai hu, expanding stockpiles and implementing a data system. All but the last have see improvements, with data being a more general issue that needs to be considered in light of future corportate ERP requirements. The expansion of the Dubai hub from 4,000 sq meters of temperature controlled storage facilities to now more than 17,000 square meters was primarily funded through approximately USD 3 million in Funding from the Kuwait grant. WHO has benefited from the expansion; increasing the availability of supplies globally, reducing response times, and saving financial resources through management and partnerships: • USD 1.4 million in medical supplies saved from expiry due to stock rotation and inventory management (dispatching items at risk of expiry to emergencies able to quickly utilize the supplies. • USD 750,000 in charter flight operations donated by the UAE to support Iran, Somalia, Ethiopia, and Lebanon. • USD 250,000 in reduced charter costs for humanitarian response provided by Emirates Sky Cargo in response to Afghanistan and Iraq - at 50% commercial rates • Additional support such as the rapid customs clearance for the export of WHO medical supplies and waiver of formal procedures can’t be quantified in terms of cost savings but have most certainly contributed in limiting the loss of human life and protecting health care workers.
Finance | To boost humanitarian donors’ confidence (EB140.8) | Completed. WHO has, since the establishment of WHE, made significant strides engaging humanitarian donors in support of WHO’s work in emergencies. CRM/EHE has developed dedicated donor profiles for WHE outlining the different donor institutions, which WHE collaborates with, or for which there is potential for collaboration based on mutual priorities. Special consideration has been given to identify and differentiate between partnerships and funding from Ministries of Health, and Ministries of Foreign Affairs, where the humanitarian funding often sits. In 2019 and 2020 WHE has established and engaged more strategically and frequently with the humanitarian attachés in GVA and in capital as well. In 2020 in the context of the COVID-19 response, CRM and WHE have proactively, and at senior level, engaged on a regular basis with the so-called G12 group, which is a group of 14 GVA based Humanitarian Attachés. In depth briefings are held on a regular basis. A number of humanitarian donors have or are considering including WHO/WHE as a strategic humanitarian partner – discussions around this have been ongoing in 2019, and continue in 2020, while ECHO confirmed that WHO in January 2020 was now officially included as one of eight strategic partners to ECHO. WHO is, thanks to WHE, increasingly viewed by donors as a critical partner on the ground in humanitarian settings – this is especially thanks to a number of strong and engaged WRs, who have set the bar high, and also a result of the health cluster coordination function, under which WHO has also proven itself an effective coordinator.
Finance | To advocate early successes in a more proactive way and present compelling economic investment cases that set out the reasons for funding the new WHE Programme (EB140.8) | Completed. WHO Investment Case, GPW13, output strategies and factsheets. Humanitarian Response Plans such as the SRP for DRC, SPRP for COVID-19, Donor Alerts. The Investment Case is to be refreshed and Emergencies will be fully reflected; it is likely that the IPPR will comment on the macroeconomic investment case for pandemic preparedness, as well as make other specific recommendations
Finance | To increase the fundraising authority of COs during emergency response, to enable COs to secure large-scale funding directly rather than through the regional offices (A70.8) | Completed. New Delegation of Authorities have been circulated to HWCOs in January 2020.
Finance | To encourages WRs to engage effectively with in-country donor representatives (EB140.8) | Completed. From 2020, under the new Global RM Strategy there is focus on RM and external relations capacity building in country. WRs receive training in donor engagement and RM on appointment as part of their induction course. CRM HQ works closely with regional colleagues, showcasing strong country teams in Strategic Dialogues with donors and is furthermore developing a Contributor Engagement Management System, with AFRO as the region featuring in the initial roll out. This will further capacitate WRs and country office staff to engage donors in a more informed and strategic manner. Finally, going forward, also it will be important for WHO to also consider opening up WR positions for candidates with non-medical degrees and ensure a more tailored training in e.g. coordination, stakeholder and partner-engagement etc.
Finance | To fund-raise at local level (WCO) with support from regional offices and headquarters (A70.8) | Completed. HQ has fielded several External Relations and Resource Mobilization surge support missions to WHO responses e.g to Idai & Kenneth cyclones in Mozambique, the Ebola response in DRC, and the Rohingya crises in Bangladesh. As part of those missions donor engagement at country level was strengthened; analyses and mapping of donor relations and funding opportunities at local level was carried out and RM plans developed; RM materials were prepared including proposals and concept notes. And, while deployed the HQ RM colleagues provided coaching and training t to colleagues in country on RM. In addition, CRM in collaboration with the ROs have provided support to ensure adequate funding is secured for its emergency operations in different countries by e.g: - Developing Resource Mobilization plans for several countries such like Yemen, Bangladesh, Ebola DRC. - Organized WHO's participation in several pledging events and conferences including UN High Level Pledging Event for e.g. Yemen, Brussels conferences on Syria, donor meetings in GVA on Iraq, Libya, and Ebola etc. - Recruited RM officers where it is most needed places such like DRC and Somalia to strengthen RM capacity at country level. - Provided RM training to the Health Cluster Coordinators in Geneva. However, the medium-term plan is based primarily on capacity building (including recruiting local leaders with the right skill set) with strategic support from HQ and regions, including via the global Contributor Engagement Management (CEM) system.
Finance | To identify trade-offs within a more limited staffing footprint, and reconsider the balance of HQ, regional office, and field staff (EB140.8) | In progress. WHE has strengthened significantly and prioritized Regional Offices and Country Offices as part of the roll-out of the programme, ensuring that flexible funding is primarily transferred out of WHO Headquarters. Additional work has been done as part of the WHO Transformation to identify functions which could be further decentralized, however delays have been faced due to the COVID-19 response.
| To recruit greater numbers of national staff with fewer international positions in COs, which would allow the WHE Programme to balance costs and stay within the overall budget(A70.8) | In progress. This has to be reviewed and addressed through the upcoming mobility policy and the new country model initiatve within the broader transformation agenda.
Finance | To come forward with clear plans for the CFE sustainability for the future (A70.8) , (EB1465/16) | In progress. Donors have demonstrated their confidence in WHO and the CFE by investing nearly US$137 million in the Fund since it was launched. The Contingency Fund for Emergencies (CFE) budget of US$ 100 million was 92% funded for 2018-2019 biennium. Standard procedures across all of WHO’s three levels – its headquarters, regional offices and country offices – ensure the CFE’s effective operation and management, sustainability, and accountability to donors. Furthermore, the CFE’s income and expenditure are included in WHO’s Financial Reports, are submitted to the World Health Assembly annually, and are subject to internal and external auditing.The External Relations team continues to mobilize resources for the CFE. In 2019, US$54 million was raised from 16 Member States, while US$83 million was released to support 23 emergencies in 22 countries. Four new donors joined the list of contributors and the first multi-year agreement for the CFE was signed with New Zealand for a period of three years.Despite the increase in funds raised, the continued drawdown of the CFE in 2019, especially for the Ebola response, left the Fund depleted at times, and therefore not available to perform its core function. As a result, the CFE is being revisited with a view to strengthen replenishment, visibility, and accountability with a view to ensure alignment with the RM strategy presented to the EB in February 2020 to better ensure adequate levels of funding at all times to the CFE. The goal is to provide WHO and its Member States with a more financially sustainable and accountable financing mechanism that continues to save lives. A road-map for how to better (re)position and replenish the CFE is being developed and will be carried out over the course of 2020 but has been somewhat delayed as RM capacities and efforts were redirected towards the COVID-19 response.
Finance | To identify additional revenue sources for the core budget of the WHE Programme, and strengthened budgeting at country level (A70.8) | In progress. Transformation was finalized end of 2019. For CRM this confirmed the creation of 4 units including a centralized Unit for Partner Engagement for Health Emergencies (EHE), but the new structure envisaged that partner engagement for health emergencies will take place across the 4 units, guided by EHE. In 2020, this has very much been the case, while the smaller EHE team leads on RM for emergencies, it is supported and backstopped by the wider team in CRM. A resource mobilization strategy was developed and presented to the EB at the 146th session held in February 2020. It provides information on the strategy for mobilizing the resources needed to deliver GPW 13, covers the period for 2019–202,3 and rests on four pillars, namely: • Established government partners: growing, diversifying or maintaining funding through regular and active engagement and policy alignment, taking a tailored approach; • Philanthropic partners: building on our most effective partnerships and seeking to grow funds from a wider range of philanthropies; • Funds, international development banks and multilaterals: maintaining funding from mature partnerships and developing funding streams from new sources and mechanisms; • Innovative financing and revenue-producing activities: exploring the potential in these areas. Individual donor profiles and engagement plans have been developed for top donor to the emergencies programme, detailing key partner institutions, budget cycles, key dates/events for engagement. The profiles also include a mapping of donor priorities against the 10 output strategies to guide more strategic engagement with donors for 2020. Strategic dialogues were held with several donors to WHO, and all included representation of the emergency programme thereby facilitating high level strategic discussions and positioning with donors. Mobilizing flexible or thematic resources is a corporate priority and decisions about how such funds are allocated between the core budgets of different programmes are taken at a senior level across the organization. (EXR)
Finance | The IOAC reiterates its recommendation that the WRs should increase their level of engagement with in-country donor representatives. (EB142/8) | In progress. See feedback on row 57 and 58. This is in progress and reflects a general corporate push within PAHO for WRs to engage with in-country donor representatives for all areas of work. For PHE, there is active engagement, particularly in COL, HTI, VEN
Finance | The IOAC encourages WHO to identify additional multi-year partnerships, to improve the predictability of the emergency response and the resilience of the WHE Programme. (A71/5) | In progress. Several multi-year partnerships were in place including with Australia, BMGF, German, the UK, the US (OFDA, USAID, CDC), New Zealand, the Netherlands, Russia – this was pre-COVID. With COVID new multi-year partnerships have been developed including with China and Kuwait.
Finance | To strengthen resource mobilization capacity at country level and to standardize across the regions WR’s financial authority to accept funds. (A71/5) | Se responses to # 1 and 6.
Finance | To urges donors to contribute in order to bring the current EVD outbreak in the Democratic Republic of the Congo under control and to contain the spread to surrounding countries (A72/6). | Completed. As of May 2019 (time of these recommendations) the WHO funding gap against its requirement in the third Strategic Response Plan (SRP) was 49%, and only a few donors had stepped up with significant funding. Whilst total funding received increased from SRP to SRP, the level of funding decreased from SRP 1 (fully funded) to SRP 2 (28% gap) and SRP 3 (49% gap). SRP 2 and SRP 3 left WHO with significant funding gaps, which were mainly filled by CFE. The SRP 4, released in July 2019, was however fully funded (USD 146 mil received) and supported by 17 donors. Overall, WHO received a total of US$ 269 million provided by 24 individual donors between Aug 2018 and June 2020 for the Ebola North Kivu response for SRP 1 to SRP4. This only includes direct funding to the Strategic Response Plans, and does not include funding provided by donors to the Contingency Fund for Emergencies (CFE) or the Regional EVD Preparedness Plan. It also does not include allocations from the CFE to the Ebola response. The Top 10 donors together provided US$ 234 mil, or 87% of all funding received. Only 3 Member States (UK, US, Germany) are in the Top 10 donors. All 3 Multilaterals (ECHO, CERF, GAVI) are in the Top 10 donors. On quality of funding, the following can be noted: - Flexibility of funding: Half of all Ebola funds were specified. Especially the Top 10 donors provided specified funding. All multilateral funding was highly specified (ECHO, CERF, GAVI). Flexibility increased with smaller contributions (Norway, Canada, Ireland, Korea, Italy, Denmark, Luxembourg, Canada). - Predictability: SRP 1 was fully funded within one month of the declaration of the outbreak, SRP 2 was fully funded within a few months. First significant gaps in funding started with release of SRP 2.1 (Dec 2018) which was almost entirely funded by CFE/internal allocations. SRP 3 was only 50% funded 5 months into the implementation period. For SRP 4, released in July 2019, it took another 5 months to be fully funded. The longer the outbreak went on, the more difficult it was to secure predictable and sustainable funding. Emergency funding mechanisms, e.g. CERF and PEF provided immediate funding, but medium to longer term epidemic financing still needs to be improved holistically.
Risk assessment | To monitor effectiveness of the ERF and EIOS (EB140.8) | In progress. WHO monitors the effectiveness of the ERF through: Collection of performance indicators for all graded responses which are recorded in vSHOC (now EMS2) and regularly evaluated. For larger events, operational reviews are conducted, which include recommendations for improving ERF. These lessons learned form the basis of discussion during the face-to-face IMS training courses and were also the starting point for the curremt ERF review. Roll out of EIOS is still ongoing and no formal evaluation has been conducted to date. Access to EIOS has so far been granted to 17 governments/national entities and 12 regional/international organizations, networks and academia.
Risk assessment | To track the ERF is properly implemented against the specific timeframes in 24hr, 72hrs, 60days (A70.8) | In progress. Performance indicators are captured in EMS for all graded emergencies as feasible. E.g in 2017 (2018), IMSTs were established at country level within 72 hrs in 63% (100%) of all G2-3 emergencies. Strategic response plans were developed with partners within 30 days in 71%, 56% and 65% of graded emergencies in 2017, 2018 and 2019 respectively. Experience over the last few years has shown that some of the time-bound indicators cannot be meaningfully applied to all types of events, particularly for acute infectious disease events (as opposed to events in humanitarian settings). As part of the ERF revision the indicators were revised to make them more applicable to all settings and it isplanned to include them in the upcoming ERF3.
Risk assessment | To inform the governments concerned of grading decisions immediately prior to their announcement (A70.8) | Completed. Between 1 January and 30 June 2020, 311 events in 213 countries and territories were investigated, followed up and their risks assessed. Of these, 92 % were infectious disease events, 5% were natural disasters related, and the remaining 3% were related to chemical, radiological or nuclear, products or food safety events. Formalized risk assessments were conducted for a total of 22 events, including 16 events in 12 countries and 6 risk assessments for the global COVID-19 pandemic. The top three events besides COVID-19 were Ebola virus disease, cholera, and yellow fever. The risk at national level was assessed as very high or high for 73% of the 22 events.
Risk assessment | To clarify roles and responsibilities between departments on leadership of investigation/response operations during the different phases of event management as well as coordination with and engagement of partners in GOARN in outbreak investigation (A70.8) | Completed. SOPs have been develop to delineate responsibilities at HQ for the management of the various event types (sudden natural, slow natural, sudden man-made, NBC accidental, NBC deliberate, high consequence pathogens) and for the transfer modalities between teams and departments when event phases change. The GOARN operational support team at HQ participates in the daily risk management and operational meetings and involves partners in outbreak investigation and control activities as feasible. This is done in a transparent manner through Requests for Assistance on the GOARN knowledge platform. GOARN Operational support team continues to conduct regular weekly operational calls with GOARN steering committee and partner instiutions. These calls serve as a forum for information exchange on ongoing events. Through GOARN alerts and GOARN Requests for assistance, partners are informed and engaged in response actvities. In 2020, until 18 August, GOARN partners submitted close to 600 offers of support, of these over 100 deployments, incuding remote support deployments were conducted.
Risk assessment | To assess the effectiveness of the EMS and update the current systems (A70.8) | In progress. EMS is going through transformation allowing the seamless management and capturing of information from signal detection, verification, risk assessment to response and information dissemination. The transformation is guided by best practices on the use of EMS and event management jointly developed between different departments in HQ and the Regional Offices. This will increase data quality, reduce redundancies in data capture and work flow and integrate with other tools and systems like the Event Information Site and the Epidemic Intelligence from Open Sources system. One of the latest improvements has been the integration of EMS data in WHO Health Emergencies Public dashboard allowing to show outbreaks WHO is currently monitoring (https://extranet.who.int/publicemergency).
IM | To adapt the IMS principles and approaches to WHO’s mission and structure, and iteratively improving and systematizing WHO’s approach over time (EB140.8) | In progress. WHO continuously reviews the implementation of IMS principles as laid down in both the ERF and the emergency SOPs. Operational reviews are regularly conducted and inform areas that require adaptation and/or improvement. Currenty, WHO works on the third edition of the ERF to incorporate the lessons learned from recent events.
IM | To build a critical mass of qualified WRs and Incident Managers through rosters and training and linkage (A70.8) | Ongoing. Qualified WRs and WR candidates are members of a global roster, that is managed by the Human Resources and Talent Management Department. Training is under development (august 2020) to guide candidates about the skills and competencies required to be a successful WR, before they apply to the global roster. Further learning and development opportunities are made available to roster members when they meet for global or Regional WR meetings. The global roster is updated every quarter.
IM | IM to have a direct line to the WHE/EXD to ensure appropriate technical and operational oversight (A70.8) | Completed. WPRO: RED has a direct line to WHE/EXD. During emergencies, the direct contact of IMs are either the Director for Emergency Operations or the designated HQ Emergency Coordinator. AFRO - Completed. There is always a direct reporting and collaboration between IM and all 3 levels of the organization.
IM | To hold the WR accountable for the performance of the IM (A70.8) | In progress. As per established process under the WHO Emergency Response Framework (ERF), HWO/WR supervises the Incident Manager directly, unless alternate arrangements are agreed by the WHE Executive Director and WHO Regional Director. In AFRO, all IM established for emregncy responses are overseen by the WRs to whom the Incident Manager directly reports maknig the WRs part of and responsible for the emergency activities. The WRs and IMs use the DOA for allocation of responsitbilities and for accountability purposes. As for the operational oversight, it is under direct supervision of the HWO/WR for the emergency operations, day-to-day monitoring of the effectiveness of the Organizational response to the emergency, and delegated authority to make technical, operational and management decisions regarding the response. Monitoring mechanisms being improved to track WHO performance at country level (e.g. standardised indicators established by Health Cluster) and corrective actions being advised to WR and WCO when objectives and targets not met. Escalation of concerns to RD occur when required, but is rarely needed. Strengthened RO support to WCOs being established, e.g. 22 Country Support Teams for COVID response; course corrections being advised as appropriate. In PAHO, all CO IM established for emeregncy response operations are overseen by the WRs to whom the Incident Manager directly reports, making the WRs part of and responsible for the emergency activities.
IM | DOA should be issued concurrent with the IM activation (A70.8) | Completed. The DOA for Emergencies is published in eManual XVII.2.3. It clearly specified "30 The delegation is valid as per the criteria to activate the SOPs for Emergencies (as listed in section XVII.2.2 of the WHO e-Manual), starting from the date of the grading decision, and ending when the grading decision is removed or ends. For Protracted Grade 1 and 2, the SOPs for Emergencies only apply during the first 12 months following the grading decision, unless otherwise extended by the EXD. " The delegation of authority for Special Emergency Procedures during a "disaster situation" is contained in the overall Delegation of Authority issued to each PAHO/WHO Representative. Under the delegation of authority, special administrative policies and procedures may be used by the head of the PAHO/WHO office or responsible officer, including the IM (PAHO/WHO E-Manual XVII.2.3 Delegation of Authority)
IM | To empower and support the WR (EB140.8) | In progress. For example in EMRO, we are strengthening techncial and operational support to WRs and WCOs. "Service-oriented" posture taken by EMRO to ensure that WRs have the resources and technical guidance required. As noted, regional office structures to support WRs and WCOs being strengthened, e.g. 22 Country Support Teams for COVID. Also, clear focal points in EMRO/EMO for all Grade 2 and Grade 3 humanitarian emergencies; this "desk function" currently being reviewed. This is on going in PAHO, led by and with very strong support from the Director and EXM. Emergency related topics have for example consistently been part of the PAHO Managers and WRs meetings. PHE also supports WRs with HR and financial resources for health emergencies, as well as tools and technical materials, such as toolkits for CO EOCs.
| To give greater authority to the IM, particularly in relation to recruitment, procurement and finance (A70.8) | Completed. The DOA for emergencies outlined in eManual XVII.2.3 granted delegations to Incident Managers in the area of recruitment, procurement and finance for acute emergencies, including development and management of workplan, approval of selection of temporary staff, consultants and deployment, approval of up to USD 500,000 for procurement of catalogue items, request reallocation of funding, etc.
IM | To provide pre-deployment orientation on WHO systems, procedures, delegation of authority and its relationship to the CO (A70.8) | Completed. IMS learning and SOPs developed. Surge capacity are expected to complete the learning opportunties as part of their placement on the rosters or, at the time of their deployment, if they are not part of the rosters. Over the reporting period 236 staff have received face-to-face Pre-Deployment Training and Incident Management System training. This figure is broken down as follows.215 risk communications and response staff received pre-deployment training (PDT) during 2016-2018. We delivered pre-deployment training in to risk communications and response staff in Amman in (2016), Nigeria (2017), Switzerland (2016 and 2017). In 2018 the we delivered a PDT in Congo. In 2019 an additional LCD worked with colleagues in the regions to train an additional 71 staff. 45 staff have received orientation on WHO systems during emergencies as part of the Leadership in Emergencies Training Programme LCD has worked with HRT to include operational staff in the Leadership Training Cohort. 26 staff from the Western Pacific region attended IMS training. 1450 staff have completed the IMS Tiers 1 and 2 on-line learning provided on OpenWHO, available in 6 UN languages and Portuguese. To date more than 10,00 people from Minstries of Health, Un partners, NGOs and others have completed the online IMS tier 1 and IMS Tier 2 courses on the www.OpenWHO platform.
IM | To engage IM on a longer-term contractual arrangement—at least 12 months instead of three-month contracts with extensions (A70.8) or released from other duties and assignments for an extended period (EB140.8) | Completed. Senior staff are released from other duties and assigned for extended periods to support events.
Partnership | Sufficient and consistent support for information management should be provided to the health cluster coordinator (A70.8) | Completed. HIM and GHC jointly co-chair the GHC Information Management Task Team, which is a group of focal points for agencies working in humanitarian information management. The IMTT has quarterly face-to-face (virtual) meetings, and works collectively to develop standards and tools (Public Health Information Services [PHIS] Standards + Toolkit) to facilitate information management within national Health Cluster. In the past 12 months, the IMTT has conducted an survey of national Health Clusters (Coordinators, Information Management Officers [IMOs] and others) to assess their greatest information management needs; and has provided guidance on estimating People in Need (PiN) of Health; has developed training materials on multiple aspects of emergency health information management; revised core health indicators; amongst others. Further, the GHC global IMO provides hands-on day-to-day support to national Health Cluster Coordinators through their Health Cluster IMOs. Efficient use of limited info management for the Health Cluster (e.g. when there is not a dedicated HC IMO) is promoted through the Integrated Information Management Unit (IIMU) concept.
Partnership | Health cluster coordination should be operationally oriented, focusing on assessment of needs and gaps, and corresponding allocation of assets and services by individual partners (A70.8) | Completed. The GHC conducts regularly a Health Cluster Partners' Capacity Survey that aims to capture information on partners' technical, operational and coordination capacities. The result of this exercise helps to more effectively identify critical gaps in health response capacity and inform future partner engagement for the Health Cluster. The latest survey was conducted across international partners in 2018 and national partners in 2019. Resuts are availble through GHC website - https://www.who.int/health-cluster/partners/current-partners/partners-capacity-survey/en/. Country Health Cluster teams were presented the results and are working with partners to best address the gaps and strenghten the response. Results have also been used to advocate for strenghtening country multi-stakeholder interventions to address identified gaps and weaknesses (such as newborn health, MHPSS, SRH & GBV in emergencies and outbreak readniess and response capacity). The GHC actively contributes to the OCHA led Humanitarian Program Cycle Working Group; Inter-Agency Information Working Group and Joint Intersectoral Analysis Group developing updated tools, methods and training materials to strengthen needs assessment and gap analysis to improve identification of people in need and funding of health cluster response actions.
Partnership | GOARN should not limit its role to deployment but should support the WHE Programme with developing the technical and operational innovation and enhanced networking (EB140.8) | In progress. WHO in collaboration with GOARN partner institutions have designed, developed and are rolling out an outbreak investigation tool called Go.Data. This tool focuses on case and contact data, including contact tracing and visualisation of chains of transmission. At present Go.Data is being rolled out globaly in support to COVID-19 response. Additonal operational research work is being conducted with GOARN areas of work, specifically research area of work.
| To continue invest in operational partnership such as GOARN and EMT (A70.8) , (EB146/16) | Completed. The EMT initiative continues to improve the timeliness and quality of health services provided by national and international Emergency Medical Teams and enhance the capacity of national health systems in leading the activation and coordination of this response in the immediate aftermath of a disaster, outbreak and/or other emergency. E.g. At the onset of the COVID-19 pandemic, the EMT network mobilized medical teams to the most affected countries as surge capcity. Additionally, in collaboration with GOARN has sent clinical experts and coordinators to affected countries to support them to manage and respond to the rising cases in countries. The GISRS (Global Influenza Surveillance and Respons System - in > 125 countries) was leveraged in March and has become the platform for sentinel surveillance of COVID-19 providing critical understanding of community transmmistion to inform country's response. In April 2020, GOARN celebrated 20 years of its existence. What started as 60 institutions strong network, is today a network of over 250 institutions which contributed to over 140 operations and response actvities
Partnership | WHO should be the technical lead for health within the IASC and play the leadership role in outbreaks(EB140.8) | Completed. WHO has established its leadership in health in the IASC and plays its leadership role in outbreaks. The GHC has produced Health Cluster Coordination Guidance for Heads of WHO Country Offices as Cluster Lead Agency which aims to assist WHO Heads of Office to fully understand their responsibilities and accountability as Cluster Lead Agency and includes the IASC protocol on system wide activation for large scale outbreaks including WHOs role. The guidance has been disseminated to Heads of WHO Country Offices by the WHE Executive Director. The document is available in 5 official languages at the GHC website: https://www.who.int/health-cluster/capacity-building/HWCO-guidance/en
Partnership | To make further efforts to proactively reach out to these partners, including humanitarian actors, and to establish long-term partnerships with key nongovernmental organizations (NGOs) for managing outbreaks. (A72/6) | Completed. The Health Cluster has over 900 partners at country level of which 65% are national & local actors; 57 of the international partners also engage strategically at global level. This is a collective force guaranteeing the response to health emergencies is more timely, effective and predictable. The GHC strategy (2017-2019 & 2020-2023) prioritizes partners' committment to prevent, prepare for, respond to and recover from public health and humanitarian emergencies including through greater outreach to multi-sectoral development actors who provide health enhancing capacity including WASH and RCCE. Several cluster partners have strengthened their collective operational readiness and response capacity for outbreaks (based on lesssons learned from recent Ebola outbreaks) including investment in national actor capacity. In response to COVID-19, a GHC Task Team was established in 2020 to strengthen the coordination and effectiveness of the Health Cluster response to the COVID-19 pandemic.
Partnership | Close collaboration of health cluster coordinators with incident managers to enable closer engagement and effective coordination (A72/6). | Completed. The relationship between Health Cluster Coordination and Incident Managers has been examined and addressed through the review of the WHE Emergency Response Framework and GHC commissioned external evaluations of the Country Health Cluster performance and coordination architecture in NE Nigeria and Mozambique (completed between September 2019 and January 2020). Both evaluations explored aspects of WHOs role as Cluster Lead Agency and adaption of Health Cluster coordination to each evolving crisis, including the interface WHO Incident Management System and other outbreak coordination platforms. The evaluation summary findings concluded that overall the Health Cluster scored 60%, or ‘average’ across all evaluation criteria, only slightly below a rating of ‘good’. The cluster is therefore fulfilling its core role of providing a well-functioning coordination platform for health response in both countries. The evaluation found that roles and responsibilities must be further clarified across WHE Incident Management System and the Health Cluster, that overall, the WHE IMS structure was found to provide a positive environment. The GHC addressed the evaluaton recommendations in the revised second edition of the Health Cluster Guide which clearly articulates the intereace between the HCC and Incident Manager roles; how the Health Cluster engages with the response pillars defined within each event specific inicdent management system. The Health Cluster Guide is the 'go-to' reference for all country Health Clusters, partners and other key stakeholders.
Partnership | To improve the quality of the HCCs roster through adequate assessment of candidates, training on field-level health cluster coordination prior to deployment, and providing adequate support on deployment to ensure satisfactory information management and coordination (A72/6). | Completed. 'HCC roster candidates are selected through WHO's virtual interview process (SONRU platform) with candidates assessed against a set of technical and competency based questions set by the Global Health Cluster reflecting the essential requirements for Health Cluster Coordination core functions. Candidate assessement is undertake jointly by the GHC and HRT. Candidates selected for the roster must complete the Health Cluster Coordination E-learning course before commiting to an HCC contract. The GHC provides pre-deployment technical briefings. Once deployed, HCC performance management is overseen by first and second level supervisors (respectively Head of Country Office & Regional Emergency Program Manager) as per WHO HR policy. The GHC proivdes remote support to all HCCs through regular thematic webinars and individual support to enhance knowledge and appliatication of sector policy and guidance. GHC support missions are undertaken at the request of country or regional office to provide address HCC performance issues.
Partnership | To establish institutional arrangements for GOARN deployment to improve accountability and ensure the safety of deployed experts (A72/6). | Completed. GOARN deployments of personnel with contractual arrangements directly with WHO are covered under the UN Security Management System. As such, they are covered by established security management systems, policies, procedures and contingencies wherever they are deployed.
Partnership | To continue engaging and working collaboratively with partners and disseminating | Completed. GHC held annual Partner Meetings and Health Cluster Forums with the respective participation of GHC partners and Health Cluster Coordinators to share good practices and lessons learned to be disseminated at the field level. https://www.who.int/health-cluster/about/structure/partner-meeting/en/ https://www.who.int/health-cluster/capacity-building/health-cluster-forum/en/ GHC created a Knowledge Bank in 2017 that provides the most up-to-date and relevant documents for humanitarian coordination and response to health emergencies . Documents include technical guidelines and guidance, tools and templates, best practices, lessons learned - available via the GHC website: https://www.who.int/health-cluster/resources/publications/en/
| best practice at the field level (EB144/8). | Completed. Various time-limited GHC Task Teams have been created to address strategic and operational issues identified by partners and HCCs producing coordination guidance, tools and best practice to enhnace cluster operations and performance - including Public Health Information Services; Remote Management; Quality Assurance for Humanitarian Health Action. The COVID-19 Task Team was created in 2020 to strenghten the coordination and effectiveness of the Health Cluster response. The primary objectives are to: 1) Collate country-level technical, operational and coordination challenges; 2) Promote and support adaptation and use of COVID-19 guidance for low capacity and humanitarian settings; 3) Support multi-sectoral action; 4) Capture and share lessons learned and good practices; 5) Advocacy to address unmet needs and operational barriers.
Partnership | To further leverage partners on the ground and develop a policy for surge capacity to authorize the release of technical expertise within the Organization at all levels (A72/6). | In progress. Draft Surge Policy will be discussed with GPG. Some regional examples below: AFRO: during emergency responses, there is greater collaboration with several partners including but not limited to CANADEM, GOARN, Africa CDC, Institut Pasteurs, EMTs, UKMed, etc.). WPRO: the region implements emergency guidance released by the WHE Programme. Deployment of partners through GOARN mechanim or Standby Partner are utilized to meet surge needs during emergencies.
Partnership | To work with partners to improve social cohesion and community engagement (A72/6). | In progress. • WHO/EPI-WIN is working with UNICEF and IFRC on community engagement • WHO/EPI-WIN has developed a new partnership with UNESCO in the area of access to information and infodemic management, with a particular focus on youth engagement • WHO/EPI-WIN is working with faith leaders and faith-based organizations for the COVID-19 response with an intention to build a sustainable relationship for health emergencies. The objective of this partnership is to o Co-develop guidance for the faith community o Provide a forum for sharing of information and best practices o Engage faith leaders as amplifiers of accurate information • WHO/EPI-WIN is working with private sector partners to co-design and build a community platform for information exchange and dissemination during epidemic events • WHO has supported 10 countries to implement Resource Mapping (REMAP) which aims to facilitate countries, donors and partners for better alignment towards addressing critical preparedness gaps by identifying all available technical and financial resources that can be applied for health security strengthening • WHO has also developed and published a Multisector Preparedness Coordination Framework which provides countries with an overview of the key elements required for overarching, all-hazard, multisectoral coordination for emergency preparedness and health security
IHR | To support countries in maintaining the level of preparedness and avoiding burnout after Ebola readiness efforts (A72/6). | Completed. WHO has provided guidance and support for integrated preparedness with the rollout of the REMAP tool for countries to identify cross cutting preparedness capacities for highest assessed threats. The REMAP tool has been adapted for COVID-19 and along with the Partners Platform tracking of actions aligned with IHR capacities, allows countries to prepare for multiple threats with cross cutting actions for better efficiencies. WHO has developed the Partners Platform, the first place where governments, UN agencies and partners can plan and coordinate together in real time for all stakeholders to see. This has created an environment of real time, fully transparent planning and implementing of readiness and response actions and tracking of resources among all actors. This coordination has been successful fully virtually for over 140 countries using the Platform.
IHR | To build national capacity and continue to work with Member States and partners to build International Health Regulations (2005) (IHR) core capacities (A72/6), (EB146/16) | In progress. • Data consolidation between COVID-19 Partners Platform and the SPH Portal to facilitate the mobilzation of financial and technical resources to ensure donor and partner coodination to address countries gaps and needs in preparedness capacities. • Through implementing the WHO Global Influenza Strategy and Pandemic Influenza Preparedness Framework (PIP), the GISRS capacity in countries on surveillance and detection, risk assessment and vaccination has been building up systematically. Such capacity is reflected in the detection of zoonotic influenza virus infection in humans and timely reporting through IHR mechanism and WHO surveilance platforms. The capacity built through influenza preparedness has been institutionized and was put into use immediately in countries in for early detection and response to the COVID-19 pandemic. • WHO has developed the Strategic Tool for Assessing Risk (STAR) to support Member States in assessing the priority risks and hazards in a country, including non biological hazards. This has allowed countries to build capacities to mitigate specific hazards, has informed preparedness and response plans, and built longer term preparedness. • WHO has been focussing on the sub-national level capacity building and is working on adapting various monitoring and evaluation tools to be used at subnational and community levels. • WHO has built capacities at the Human Animal Interface, conducting One Health National Bridging Workshops jointly with OIE, and has developed and is implementing the WHO-OIE-FAO Tripartite Operational Tool for conducting Joint Risk Assessment at the interface. Pillar 2 of the five-year global strategic plan to improve public health preparedness and response (2018-2023) highlights the need to support and further strengthen the National IHR Focal points, notably through: 1. community-of-practice related activities • The launch of the Global Knowledge Network and AFRO Regional Network of National IHR Focal Points in 2018, followed with the launch of additional regional networks in 2019, allowed NFPs to share information and experiences in implementing the IHR. • These Knowledge Networks provide platforms where NFPs discuss the challenges and successes encountered in their work. • These platforms also serve as fora for NFPs to communicate about specific aspects related to IHR implementation, facilitate peer-to-peer learning, share materials developed and other resources that may be relevant to other NFPs. 2. training initiatives to support workforce development of NFPs and IHR stakeholders: • the design and development of online courses such as the IHR Orientation Program, Public Health Preparedness for Mass Gathering Events, the Basics of One Health, Event Information Site (EIS) for NFPs, etc. • current emphasis is on the design of COVID-19 related courses, geared to Border Health / Points of Entry and in support of national Rapid Response Teams. These courses are hosted on the Health Security Learning Platform (HLSP). The health laboratory sector is a key IHR component: 1. Building the capacity and monitoring the performance of this sector is a high priority for PHE. Working with partners including FAO, OIE, US CDC and ECDC, a Global Laboratory Leadership Programme is being developed. The aim of this programme is to provide laboratory leaders with the skills necessary to ensure optimal functioning of a modern laboratory. The programme will be introduced in Pakistan in the coming months and in other countries thereafter. 2. A number of laboratory proficiency testing programmes for diseases of high public health importance have been organized and the global level and support for regional level programmes has also been provided. A large-scale global programme for diagnosis of COVID-19 at the subnational level will take place in the coming months covering over 3,000 laboratories. This will greatly assist Member States and WHO to understand the performance of the subnational laboratories where the majority of testing is taking place. The PoE and border health program is supporting countries in enhancing capacities for public health preparedness, readiness and response at points of entry- international travel and transport, by providing technical guidance, learning programs, simulation exercise tools, field technical assistance, in an effort to minimize international spread of disease and mitigate impact of outbreaks through effective application of proportionate public health measures in a risk based approach, that do not impose unwarranted restrictions on travel and trade, in a close collaboration with other UN organizations (e.g. ICAO, IMO, IOM, UN WTO) and industry associations (e.g. IATA, ACI, ICS).
IHR | To streamline the process, and support countries in developing simplified and impact-oriented NAPs which prioritize short-term goals with timelines for implementation. (EB144/8), (EB146/16) | In progress. • To date, WHO has supported the development of National Action Plan for Health Security (NAPHS) in 68 countries. • The WHO benchmarks for IHR capacities was developed to facilitate the development of NAPHS (22 countries have used the benchmarks) and some countries including Sierra-Leone and Nigeria have used the benchmarks action to prioritise their one year activities of NAPHS. To facilitate this process, WHO together with partners developed an IT interface for the benchmarks, which can generate a draft plan. • The Operational planning tool is being finalized to support the development of a simplified and impact-oriented NAPs which prioritize short-term goals with timelines for implementation. • The WHO resource mapping (REMAP) tool and process has been developed and implemented to support countries in identifying all available technical and financial resources that can be applied toward national plan development and implementaton.
IHR | To support countries in implementing corrective measures for critical areas of work identified in JEEs and after-action reviews (EB144/8). | In progress. • WHO continues to encourage and support the implementation of corrective measures by Member States following an AAR or JEE. For example, in Madagascar, the AAR following the Plague outbreak led to very specific surveillance and control measures which greatly increased the country's capacity to detect and respond to the next plague outbreak. • Reports of AARs and IARs are published and shared with technical teams and stakeholders. • WHE is developing a global strategic preparedness network to support countries bridge their specific gaps, in partnership with national public health institutes to strengthen sustainability of preparedness actions in countries. • WHE published COVID-19 tabletop exercise (SimEx) packages to support countries’ preparedness effort on the COVID-19 outbreak. Those packages include COVID-19 TTX for health facility and IPC, Point of Entry and Urban settings.
IHR | To reinforce the pool of expertise across the Organization and to allocate a core budget for supporting countries with transition activities following major events, with a view to building IHR core capacities in a more sustainable way (EB144/8). | In progress. • To ensure coordination and streamlining in strategic planning and implementation of transition efforst across the Organization, WHE is part of several working groups with colleagues working on health systems: recovery working group; joint working group for fragile, coflict affected and vulnerable settings; joint working group on UHC. • WHE and health systems colleagues have developed a way forward paper to support continued joint action between teams involved in supporting countries to enhance health security preparedness and those involved in supporting countries to strengthen integrated health services. The paper maps ongoing and evolving joint work in the context of COVID-19 and beyond within the frame of longer-term preparedness and the resilience of health systems of our Member States. • WHE is working closely with health system teams to strengthen health systems for health security for preparedness, UHC and SDGs. WHE is also working with health systems on PHE indicators and as well resilience.
IHR | WHO is mandated to assist countries in making rational decisions, deploying effective measures to prevent public health emergencies and complying with the IHR requirements. This is another issue that should be looked into as part of IOAC’s future agenda. (A71/5) | In progress. WHO, supported by partners including GISRS and other public health agencies, develops and routinely updates risk assessment and risk management recommendations on zoonotic influenza outbreaks; updates recommendations on seasonal influenza vaccines; and develops operational guidance for countries in using existing resources (influenza capacity) for surveillance of COVID-19. Operational guidelines are developed by WHO for readiness and preparedness for all emergencies which outline effective, priority interventions aligned with international strategies and IHR requirements in all public health pillars to guide countries in implementing sound, effective measures systematically. • The Secretariat has continued to implement a structured approach for monitoring States Parties’ compliance regarding additional health measures, in accordance with Article 43 of the Regulations, and has maintained a database of such measures. • In accordance with Article 43 of the IHR (2005), the Secretariat will continue to monitor systematically additional health measures in relation to public health events. The Secretariat is also exploring approaches for reporting and presenting such information to States Parties, including the details of actions by States Parties under Article 43. In order to better inform States Parties about the effectiveness of additional health measures, the Secretariat is drafting evidence-based guidelines on the effectiveness of travel measures in reducing international spread of infectious diseases. WHO has commissioned a Cochrane systematic review of evidence on the effect of travel measures during COVID-19 response. The review showed low quality of exisiting evidence, which is insufficient to inform evidence-based recommendations, but provides a basis to identify needs for future research. WHO has also provided a letter of suport for Canadian Institute for Health Research Institute to conduct extensive research in the field of additional health measures, the results of which are expected in 2021. WHO contineus to explore options to expand research in this critical field. • The Secretariat published the Guidance for Conducting a Country COVID-19 Intra-Action Review (IAR) and accompanying tools to guide countries to conduct periodic review(s) of their national and subnational COVID-19 response, so that countries do not miss critical opportunities for learning and improvement to better respond to the COVID-19 outbreak in their countries, especially as the possibility of a protracted pandemic becomes increasingly probable. This includes possible lessons-learned for implementing the IHR on the national level, e.g. through senior-level allocation of the National IHR Focal Point, monitoring of functions relevant to the IHR such as legislation, governance, financing, cross-sectoral ownership, etc.
IHR | RO should support countries to share best practice and experience with JEE and NAP (A70.8) | • WHE supported countries to integrate seasonal influenza programs and pandemic influenza planning into their NAP. • WHO has provided direct support to countries and has documented progress of national implementation of IHR Monitoring & Evaluation recommendations and NAPs missions in number of countries (Lao PDR, Sierra Leone, Sri Lanka and Tanzania). https://www.who.int/ihr/procedures/evidence-and-analytics-for-health-security/en/ . • Case studies have been collected to capture best practices, lessons learned and knowledge on the implementation of IHR capacities for health security and emergency preparedness for all hazards. • A call was issued for COVID-19 related case examples, lessons and best practices in preparedness from all countries: https://www.who.int/ihr/procedures/special-call-for-covid-19-related-case/en/ and for case studies on IHR, health security and emergency preparedness https://www.who.int/ihr/procedures/call-for-case-studies-on-international-health-regulations/en/ (SHIDDED)
IHR | JEE tool should be suitable for its purpose, including its ability to assess: (i) capacity at the community level to alert and take early action, and (ii) the way in which strengthening community engagement is being built into core IHR capacity. (EB140.8) , (EB146/16) | In progress. • A review of the current JEE process and tool will take place to address elements including assesment of capacities at sub-national levels and additional areas highlighted as critical capacities for a severe pandemic, as highlighted by COVID 19. • WHE has developed a guidance document for Urban preparedness during the COVID 19 and beyond, that would guide early action for local authorities.
IHR | Relevant community-based groups be systematically included in Joint External Evaluation processes to ensure that community-based surveillance and community early response systems are included in all evaluations (A70.8) | In progress. • Review of the current JEE process and tools to include assesment of capacities at sub-national level using lessons learnrt from COVID-19 pandemic, IAR and case studies.
Staff protection | To emphasize cost estimates for emergency responses should include budgets for staff security, protection and well-being. WHO is advised to accelerate the ongoing recruitment process for security staff at HQ and development of a corporate security strategy in alignment with the United Nations (UN) Security Management System (A72/6), (EB146/16) | in progress. 1. Inclusion of security requirements in budgets and cost estimates for emergency responses is being ensured with the engagement of security services from the onset and planning phase of all emergency response activities. 2. The recruitment of security staff at HQ and in WHO is conducted in synergy with existing resources, especially with UNDSS, and the WHO transformation guidelines. The recruitment of the Head of Global Security is in process and it is expected to be completed this year; other recruitments to follow in accordance with the implementing guidelines of the Transformation Process. 3. The development of a Corporate Security Strategy is planned to be initiated during the scheduled WHO Security Network Workshop this year and to be finalized following the assumption of a full time Head of Global Security (also towards the end of this year).
Staff protection | To clarify and simplify the various elements of the grievance and redress system to build greater staff trust in the mechanisms, and to make them more responsive. The WHE Programme senior management should ensure that effective staff welfare and protection measures are in place both in the field and at all levels of the Organization, and make them accessible and responsive (A72/6), (EB146/16) | Completed. The Organization has reformed its internal justice system to allow for the resoluton of formal grievances/appeals under strict timelines. Further, the Organization has increased resources for the informal resolution of disputes which has been effective in addressing matters before they escalate. The Organization has also invested in regular trainings for staff at all levels, including through orientation training of new staff, so that dispute resolution mechanisms are widely known.
Staff protection | To develop its framework of accountability in line with the UNSMS and enhance its crisis preparedness and capacity development for security management in emergencies (EB144/8), (EB146/16) | In progress. The current framework of accountability is essentially in the existing WHO Staff Security Policy included in the WHO Manual. This is to be updated and enhanced at the scheduled WHO Security Network Workshop in synchrony with the development of the Corporate Security Strategy.
Staff protection | To focus the provision of adequate logistics and security support (EB140.8), (EB146/16)
Staff protection | To apply a consistent and robust approach to security: Security should be funded by flexible corporate funding (A70.8) | Ongoing. Security costs are primarily covered through UNDSS, which are funded through POC (corporate funding) within SP4 budget. Response-specific security costs are included in appeals and funded through VC.
Staff protection | Security procedures and adequate measures, including medical evacuation, should be put in place for staff support and protection when delivering critical assistance to people in areas with limited infrastructure and increased security risk. (A71/5) | Ongoing. Security Risk Management at all levels are done in collaboration with the UNSMS. To ensure availability, applicability and responsiveness, the WHO Security Focal Point and the unit engages where necessary from the field level (Area and Security Cells and Management Teams) to the HQ Level through the Inter-Agency Security Management Network An interagency working group for MEDEVAC linked to COVID-19 has been established. WHO is taking the lead through its Medical Coordination Unit (MCU) in Geneva: a "control tower" to manage medevac cases across the UN system. For non-COVID related cases, standard medevac processes are in place.
Staff protection | WHO is advised to put in place a coherent strategy and investment for security as a matter of urgency. (EB142/8) | Ongoing. Security requirements are included in budget estimates at the time of PB preparation and operational planning. As security is primarily managed through UNDSS, WHO contributes its share of the cost to this entity. A Security Fund also exists to record and report security expenses. To note that the newly established position of Head of Global Security (P6) is currently being filled through a competitive process.