## Slide 1: Brainstorming and Interventions Action Plan

## Slide 2: Sample Agenda
Time | Activity | Responsible
9:00 – 11:00 | Experiences from the field | All 10 teams
 | Break | 
11:00 – 12:00 | Present and discuss draft analysis results | 
12:00 – 13:00 | Brainstorming I: Identify key causes and solutions for MOVs (three priorities per working [WG]) | Three WGs
13:00 – 14:00 | Lunch | 
14:00 – 16:00 | Brainstorming II: Action plan/chronogram of activities to reduce missed opportunities (6-12 months time-frame) | Three WGs
16:00 – 16:30 | Break | 
16:30 – 17:30 | Review of action plan Re-prioritisation by the plenary (3–5 priorities) | Three WGs

## Slide 3: Experiences from the field
Each team to identify one person to report on field experience (5 minutes per team)
  Common themes at field site
  Challenges in the field
  Comments/suggestions on assessment tools

## Slide 4: Preliminary Results for Brainstorming
(See Preliminary Analysis and Debrief Slides)

## Slide 5: Working Group Brainstorming Sessions:
Creating an action plan to reduce missed opportunities in <<<Country>>>

## Slide 6: Working Groups
Split into 2-3 working groups of ~5 participants each
  Diversity of field locations
  Mix of organizations represented (e.g. MoH, WHO, UNICEF, etc.)

## Slide 7: Expected final output from each WG
Main issues identified (prioritize 3 for each WG) | Proposed interventions (3 priority activities only) | Immediate next steps | Timeline for completion | Responsible person/ organization | Remarks on funding/ sustainability
Submit in Excel format to Assessment Coordinator (Name, email address)

## Slide 9: Brainstorming Process
Each group selects a facilitator
Group provides ideas for reducing MOVs
  Rapporteur records all ideas on a flip chart
  Encourage all ideas!
Group combines ideas on the flip chart into similar themes
Group prioritizes ideas based on potential impact and feasibility
  Determine what will be presented to the plenary by the rapporteur
  Prepare to elaborate/defend ideas

## Slide 10: Best practice brainstorming
Facilitator plays a critical role:
  Ensures everyone is clear about the focus question. Write on the flip chart to keep it visible.
  Ensures a safe zone- no personal accusations, criticism
Step 1: Creating the ideas
  Record ideas with no editing or judging
  If ideas dry up- Repeat question, how person X might solve
Step 2: Clarifying the ideas
  Clarifying understanding of all ideas. Still no criticism, analysis or decisions yet

## Slide 12: Best practice brainstorming
Step 3: Organizing ideas
  Reduce redundancies and repetition
  Categorize/condense/combine/refine
  Label the groups of ideas
Step 4: Analyse or prioritize ideas
  Assess/analyse suggested activities and compare to the original question
  Use relevant criteria for selection: financial, time, staff, urgency
  Prioritize options

## Slide 15: Impact/Feasibility Grid
B High impact Requires planning and/or persuasion Long term investment | A High impact Quick fixes
D Low impact Difficult or expensive Resistance | C Low impact Quick fixes Nice to haves
Feasibility
Impact
Low
High
Hard
Easy

## Slide 16: Factors for determining feasibility and impact
Feasibility
  What is the timeline?
  What commitment is necessary?
Funding
  Think about existing funding streams
Partner collaboration
  Explore synergies with existing work plans
  How does this fit with national immunization plans?
Potential impact
  What is the possible impact on reducing MOVs?

## Slide 17: Sample questions for brainstorming session
From the debrief presentation you just listened to and your experience during data collection, make a list of 3-5 major causes of MOVs in this <<LOCALITY>>
What are the top three priority activities in this <<LOCALITY >> for reducing MOVs?
Lay out a draft action plan (chronogram) of MOV activities for the next 6-12 months in this <<LOCALITY>> for reducing MOVs

## Slide 18: WGs Presentation
Each rapporteur presents WG’s top three priority interventions
  5 minutes presentation
  5 minutes Q&A from the group

## Slide 20: Priority Interventions
Examples

## Slide 21: Interventions to reduce MOVs
Priority Intervention 1
  Priority Intervention 1 Detail
  Priority Intervention 1 Detail
  Priority Intervention 1 Detail
Priority Intervention 2
  Priority Intervention 2 Detail
  Priority Intervention 2 Detail
  Priority Intervention 2 Detail
Priority Intervention 3
  Priority Intervention 3 Detail
  Priority Intervention 3 Detail
  Priority Intervention 3 Detail

## Slide 22: Sample action plans/chronograms
Remember to include:
Timeline
Person(s) responsible
Funding source/synergy with existing activities or work plans

## Slide 24: Gantt Chart from Chad

## Slide 26
MALAWI MoV ANNUAL IMPLEMENTATION PLAN FOR 2017 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
YEAR: 2017 |  |  |  |  | J | F | M | A | M | J | J | A | S | O | N | D | Expected Output | Resources Needed
No. | Activity | Start Month | End Month | % Compl | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  | 
1 | Train health workers in Immunization in Practice | 5 | 6 |  |  |  |  |  |  |  |  |  |  |  |  |  | 3000 HWs trained | $900,000
2 | Conduct regular district supervision | 3 | 12 |  |  |  |  |  |  |  |  |  |  |  |  |  | 87 district supervisory visits conducted yearly | $174,000
3 | Orient drama groups on immunization | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  | 5 sessions conducted | $50,000
4 | Intensify health talks | 1 | 12 |  |  |  |  |  |  |  |  |  |  |  |  |  | Health talks intensified | $0
5 | Conduct drama performances | 5 | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  | 290 drama performances conducted | $145,000
6 | Air radio slots and jingles on immunization schedule and contraindication | 1 | 12 |  |  |  |  |  |  |  |  |  |  |  |  |  | 730 radio slots aired yearly to each of the 3 radio stations | $21,900
7 | Disseminate TV slots on immunization schedule and contraindication | 1 | 12 |  |  |  |  |  |  |  |  |  |  |  |  |  | 365 TV slots aired yearly to each of the 2 TV stations | $26,500
8 | Hold radio panel discussion | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  | 2 Sessions conducted | $4,000
9 | Orient community volunteers | 11 | 11 |  |  |  |  |  |  |  |  |  |  |  |  |  | 4200 volunteers oriented | $168,000
10 | Conduct regular national supportive supervision | 3 | 12 |  |  |  |  |  |  |  |  |  |  |  |  |  | 4 supervisory visits conducted | $16,000