## NVI Checklist
Annex 4: New Vaccine Introduction Checklist
Country: |  | Country X
New Vaccine: |  | Vaccine X
Planned Introduction Date: |  | Date X
Theme | Timeline (months before intro) | Issue | Lead Agency | Activity/Action to be taken | Deadline | Status | Is Funding Available (if required) | Importance (High Medium Low)
Programme objectives/targets | 12 | Setting Short, Intermediate and Long-Term Goals: If the short, intermediate and long-term goals of the introduction have not been set to contribute to global, regional and/or national health goals, what actions need to be taken to ensure this?
Target population and delivery strategy | 10 | Establishing the Target Population: If the new vaccine is for older age groups, or for age groups outside the traditional infant target population, and the size and location of the target population has not been established, what steps need to be taken to establish this information? (Including involving actors not traditionally involved in EPI, e.g. Ministry of Education.)
| 10 | Establishing the Target Population: If target population is "new", what steps need to be taken to identify this population and to cost delivery strategy options?
| 10 | Delivery Strategy: If the introduction strategy is not the traditional one, i.e. , country-wide introduction, what steps need to be taken to ensure an optimal introduction?
| 10 | Delivery Strategy: If the identification of ways of reaching children not located at the primary vaccine delivery site has not been completed, what steps need to be taken to complete this preparation?
| 10 | If an equity analysis (gender, wealth, geography) has not been conducted, including suggested actions to mitigate any equity-related barriers to vaccine introduction that are identified, what steps need to be taken to complete this?
Policy | 10 | National Policy and Schedule Revisions: If the necessary revisions to the national immunization policy and/or national immunization schedule to include introduction of the new vaccine have not been completed, what actions need to be undertaken to complete the revisions?
Financial considerations | 12 | Non-vaccine Operational Costs: If funding to cover the non-vaccine operational costs for the introduction of the new vaccine is not available, what actions are being undertaken to secure the funds?
| 12 | GAVI Vaccine Introduction Grant (VIG): If the vaccine is provided by GAVI, and the new vaccine introduction grant (VIG) has not been received, what actions are being undertaken to secure the VIG?
| 6 | Human Resource Capacity: If there are potential HR shortages, what actions need to be undertaken to address such shortages?
Situational Analysis | 6-12 | EPI Programme Strengthening: What actions/recommendations from recent programme reviews related to the strengthening of the EPI programme need to be implemented prior to introduction of the new vaccine(s)?
| 6-12 | Immunization coverage: If immunization coverage is not achieving national targets, or is low in certain districts or provinces, or in certain geographic, economic, ethnographic populations, what plans exist for increasing coverage as part of the new vaccine introduction?
| 6-12 | Data Quality: What actions/recommendations from recent assessments of data quality need to be implemented prior to, or can be addressed through, the introduction of the new vaccine(s)?
National Coordination Mechanism | 12 | National Steering Committee: If a National Steering Committee has not been established to oversee the planning for, and implementation of, the new vaccine introduction, what action is being taken to establish such a Committee?
| 12 | Technical Sub-Committees: If Technical Sub-Committees have not been established for some of the following areas, what actions are being taken to establish them?: 1. Technical issues 2. Cold chain and logistics 3. Advocacy, communication, social mobilization 4. Monitoring & Evaluation
Vaccine procurement & distribution | 9 | Licensing of the Vaccine(s): If the selected vaccine product is not already licensed in the country, what steps need to be undertaken to complete licensure?
| 6 | Procurement of the Vaccine(s): If the vaccine is to be purchased by the country itself, and there is a local tendering process (procurement through competitive international bids), what actions need to be taken to ensure that this process does not delay the planned introduction of the new vaccine(s)?
| 3 | Customs Requirements: If there are national customs regulations that may cause delays in receiving the vaccine in the country, what actions are needed to ensure these issues do not delay the planned introduction of the new vaccine(s).
| 3 | Vaccine Arrival: If confirmation of the vaccine shipment plan has not been received, what actions need to be undertaken to confirm the date of the first arrival and subsequent shipments?
| 3 | Vaccine Transport: If the frequency of deliveries needs to be increased and there are insufficient funds to permit this, what actions need to be taken to secure funding for this activity?
Cold chain, logistics and vaccine management | 12 | Effective Vaccine Management (EVM) Assessment: What actions/recommendations from recent EVM assessment need to be implemented prior to introduction of the new vaccine(s)?
| 12 | Cold Chain Assessment: What actions/recommendations or cold ch ain rehabilitation plan resulting from a recent cold chain assessment need to be implemented prior to introduction of the new vaccine(s)?
| 9 | Vaccine Stock Management System: If a system is not in place for vaccine stock management at central and intermediary levels, e.g. stock management tool (SMT), what actions need to be taken to establish one?
| 6 | Vaccine Stock Management Tools: If the vaccine management tools have not been updated to include the new vaccine(s), what actions need to be taken to update them?
| Ongoing | Enhanced Supervision of Vaccine Management: If there are no plans in place to increase the supervision of vaccine management following introduction, what actions need to be undertaken to put such plans in place?
Waste management and injection safety | 12 | Waste management & Injection Safety: What actions/recommendations from recent waste management &/or injection safety assessments need to be implemented prior to the introduction of the new vaccine(s)?
| 12 | Waste Management: If the National policy on waste management is not being implemented at the service delivery level, what actions need to be undertaken to ensure the policy is implemented and can accommodate the new vaccine(s)?
| 12 | Injection Safety: If the National policy on injection safety is not being implemented at the service delivery level, what actions need to be undertaken to ensure the policy is implemented, including having a system in place to ensure sufficient injection equipment is always available, i.e. "bundling" of injection equipment with vaccines?
Monitoring and evaluation | 6 | Supportive Supervision: If the plans and forms for supervision do not (a) provide for increased frequency of visits in the 6 months after introduction of the new vaccine(s), and (b) include questions on how to monitor the implementation of the new vaccine, what actions need to be undertaken to incorporate such changes?
| 4 | Recording and Reporting Tools: If the revised recording and reporting tools have not been prepared and distributed to regions, districts and health facilities, what actions need to be undertaken to do so?
| 4 | Disaggregation of data: If it is not currently feasible to disaggregate data by sex, geography and wealth quintile, are there any steps that could be taken to collect this data (eg, surveys)?.
| 4 | Monitoring and Evaluation Framework: If an M&E framework for monitoring the implementation of the new vaccine has not been developed, what actions need to be undertaken to develop one?
| 4 | Risk Management Strategy: If a risk management assessment and plan, putting in place strategies to mitigate and address challenges to the introduction has not been put in place, what actions need to be undertaken to establish this?
| 2 | Post-Introduction Evaluation: If a plan for conducting a post-introduction evaluation (PIE) 6-12 months following introduction of the new vaccine(s) has not been put in place, what actions need to be undertaken to establish this.
Health worker training | 6 | Training of Health Care Workers: If a training plan for health care workers to train them in the specific requirements and attributes of the new vaccine(s) and to include sufficient time for refresher training in immunization practices has not been developed, what actions need to be undertaken to develop such a training plan?
| 6 | Training Materials: What actions need to be undertaken to ensure that training materials (introduction guideline, handbook for health workers, FAQs, fact sheets, video, posters, pre- and post knowledge tests, other) will be updated and available prior to the introduction of the new vaccine(s), including allowing provision to adapt them to the local language(s)?
Disease burden surveillance | 12-24 | Disease Burden Surveillance: If (according to WHO recommendations) establishing in-country sentinel hospital surveillance is desired to assess disease burden or evaluate the impact of the new vaccine, what actions need to be undertaken to establish such surveillance in line with the following minimum requirements? (a) establishment of baseline data on disease burden (including existing WHO estimates) (b) identification of surveillance sites (c) training of staff in surveillance sites (d) checks to maintain quality of surveillance data collected and analysis of data.
AEFI monitoring & reporting | 12 | National Capacity for AEFI Monitoring & Reporting: If national capacity to implement pharmacovigilance is not in place, what actions need to be undertaken to establish it?
| 10 | National AEFI Expert Review Committee: If there is no National AEFI Expert Review Committee able to provide technical guidance on causality assessment of AEFIs in place what actions need to be undertaken to establish such a Committee?
| 8 | Risk Communication: If no risk communication plan has been developed, what actions need to be undertaken to develop one?
Advocacy, communication & social mobilization | 12 | Involvement of Local Leaders in the Advocacy for the New Vaccine(s): If mechanisms to sensitize political and opinion leaders at national, regional, district level on the introduction and benefits of the new vaccine(s) have not been identified, what actions need to be undertaken to do so?
| 6-8 | KAPB (Knowledge, Attitudes, Practices and Behaviour) study of health workers and/or caregivers or person to be vaccinated (if older): What actions need to be undertaken to ensure that recommendations or messages from recent KAPB studies, including messages about comprehensive disease approaches, are implemented or incorporated into advocacy, communication and social mobilization activities prior to the introduction of the new vaccine(s), or if no such study has been conducted, to conduct such a study?
| 6 | Development of key messages: If other relevant departments (maternal and child health, communicable diseases) are not involved in preparing the key messages, what actions need to be undertaken to facilitate this?
| 6 | Development of IEC Materials: If IEC materials have not been developed and adapted into local languages, and plans for their distribution to service delivery level have not been made, what actions need to be undertaken to develop the messages?
| 6 | Use of Media Outlets for Social Mobilization: if the relevant media outlets have not been identified, contacted and briefed on the timing and benefits of the introduction of the new vaccine(s) what actions need to be undertaken to achieve this?
| 3 | Date for the Launch of the New Vaccine(s): If a launch date has not been set, what actions need to be undertaken to confirm this date with relevant Ministry departments and key stakeholders and to invite them to the ceremony(ies)?
| 2 | Preparations for the Launch of the New Vaccine(s): If the preparations for the launching ceremony(ies), i.e. location, invitations, media, security, protocol, etc., have not been completed, what actions need to be undertaken to prepare this activity?

## NVI Activity List & Timeline
Annex 4: New Vaccine Introduction Activity List & Timeline
Instructions: Copy from the checklist only the activities that require action.
Country: |  | Country X
New Vaccine: |  | Vaccine X
Planned Introduction Date: |  | Date X
[5 empty] | Year 1 | [11 empty] | Year 2
Theme | Lead Agency | Activity/Action to be taken | Deadline | Status | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec
Programme objectives/ targets
Target population and delivery strategy
Policy
Financial considerations
Situational Analysis
National Coordination Mechanism
Vaccine procurement & distribution
Cold chain & logistics
Waste management and injection safety
Monitoring and evaluation
Health worker training
Disease burden surveillance
AEFI monitoring & reporting
Advocacy, communication & social mobilization
Introduction of the new vaccine (Example)