## Instructions
Mass gathering (MG) after action review (AAR) trigger question database Important note – Using this database effectively This trigger question database is a resource file with an extensive list of questions organized by pillars and cross-cutting issues (please refer to the table below).
• Mass gathering AARs do not have to be comprehensive reviews or laborious processes. • It is up to individual countries/event organizers to decide whether to review only a single public health response pillar or a combination of different pillars. Countries/event organizers are also encouraged to adapt the pillars provided in this database and develop other pillars as needed to their specific context and relevant to the AAR objectives. • Countries/event organisers are also encouraged to customize the trigger questions provided and develop additional questions that are relevant to their specific event context. • AARs should be conducted in the spirit of continual collective learning across different sectors to identify gaps for improvement and sustain best practices. It is important to maintain an impartial perspective and use open-ended questions to guide the discussion. • An abbreviation tab is available for your reference. What to do before the AAR: 1. During the planning phase, AAR facilitators should first pre-select the relevant documents to review, possible indicators and trigger questions using the drop-down box next to them to filter by relevancy (i.e. “relevant”, “may be relevant” or “not relevant”). 2. During the desk review phase, in preparation for AAR, ideally collect and review the relevant documents and indicators to ensure a productive discussion for the pillar(s) selected for the review. What to do during the AAR: 1. It is important NOT TO SHOW the list of pre-selected questions to the participants during the review and AVOID using them as a Q&A session. 2. AAR facilitators should refer to and use the pre-selected questions when needed to stimulate reflections and discussions within the group, especially when conversations become less lively. 3. AAR facilitators should probe the underlying causes of the best practice and challenges identified using the root cause analysis to ensure that recommended actions can be as impactful and meaningful as possible.
Disclaimer: This database of trigger questions is not meant to be exhaustive nor cover every aspect of MG events the country/event organizers may wish to review.
Category | No. | Public health response pillar | Description
Preparedness emergency (PE) | PE.1 | Risk assessments | This pillar evaluates the effectiveness of risk assessments conducted prior to a MG event. It focuses on identifying potential threats, vulnerabilities and hazards that could impact the event's safety and security. Assessment considers factors such as the venue, crowd dynamics, environmental conditions and potential public health risks. The goal is to determine the adequacy of risk identification, risk analysis and risk mitigation strategies in place to ensure the safety of participants and the general public.
| PE.2 | Simulation exercises | This pillar assesses the effectiveness of simulation exercises conducted before a MG event. It evaluates the identification and rectification of gaps and weaknesses identified during simulations and how well they were implemented to enhance preparedness, response and coordination during the actual event.
| PE.3 | Training | The training pillar examines the adequacy and relevance of training programmes conducted across key areas in preparation for a MG event. This includes assessing the proficiency of personnel in various roles, the comprehensiveness of the training curriculum and the use of innovative training methods. Evaluation aims to determine the extent to which training contributed to the overall preparedness and response capabilities.
| PE.4 | Contingency plans | Contingency plans are crucial for addressing potential challenges during a MG event. This pillar evaluates the development, communication and implementation of contingency plans. It includes an assessment of the responsiveness of these plans to emerging scenarios, as well as their integration with overall event management and emergency response strategies.
Health sector operations (HSO) | HSO.1 | Command, control and coordination | This pillar reviews the structure and functionality of the command and control system during a MG event. It assesses the clarity of roles and responsibilities, the efficiency of communication channels and coordination among various agencies and stakeholders. The goal is to determine how well the command structure facilitated coordination and timely decision-making and effective responses.
| HSO.2 | Capacity-building | Capacity-building is essential for enhancing the skills and capabilities of individuals and organizations involved in a MG event. This pillar evaluates the initiatives taken to build and strengthen capacities, including training programmes, skill development and the establishment of partnerships. Assessment aims to identify areas for further capacity enhancement.
| HSO.3 | Emergency medical services | This pillar focuses on the provision of emergency medical services during a MG event. It assesses the readiness, accessibility and effectiveness of medical services, including first aid, ambulance services and coordination with health-care facilities. Evaluation also considers the availability of medical personnel, equipment and facilities to handle potential health emergencies. It may also review the emergency referral system already in place.
| HSO.4 | Risk communication, community engagement (RCCE) and Infodemic management (IM) | RCCE-IM evaluates the communication strategies employed to disseminate information, engage with the community, and manage misinformation or disinformation during a MG event. Assessment includes the development and implementation of communication plans, community outreach efforts and measures taken to address and counter misinformation or rumours.
| HSO.5 | Environment health surveillance | This pillar examines the monitoring and surveillance of environmental health factors during a MG event. It includes the assessment of air and water quality, sanitation facilities, waste management and other environmental aspects to ensure the well-being and safety of attendees. Evaluation aims to identify areas for improvement in environmental health planning and surveillance.
| HSO.6 | Points of entry | The points of entry pillar assesses the implementation of health measures at designated entry points, such as airports, ports and ground crossings, to prevent the spread of infectious diseases associated with a MG event. This includes the effectiveness of screening procedures, coordination with public health authorities, and the availability of isolation and quarantine facilities. Evaluation aims to ensure the robustness of measures to protect public health.
| HSO.7 | Laboratory | This pillar reviews laboratory system functioning during a MG event. It assesses the capacity to conduct timely testing, the reliability of diagnostic tools, and the sharing of relevant information and data with national and international partners. Evaluation aims to identify strengths and areas for improvement in the laboratory response to potential health threats.
| HSO.8 | Supplies/logistics | This pillar evaluates the adequacy and efficiency of the logistics arrangements made for a MG event. It includes the procurement, storage, distribution and management of essential supplies, equipment and resources required for emergency response, medical services and overall event operations. Assessment also considers the resilience of supply chains, stockpile maintenance and the ability to adapt to unforeseen challenges.
| HSO.9 | Human resources | This pillar focuses on the planning, deployment and management of human resources for a MG event. It assesses the sufficiency and appropriateness of personnel in various roles, their training and coordination of their activities. Additionally, evaluation includes an examination of the effectiveness of communication channels among team members and the adaptability of human resources to evolving situations.
| HSO.10 | Information-sharing | Information-sharing is crucial for effective decision-making and coordination for a MG event. This pillar assesses the mechanisms in place for timely exchange of relevant information among various stakeholders including government agencies, emergency responders and event organizers. Evaluation considers the accessibility, accuracy and timeliness of shared information to support coordinated responses and informed decision-making.
Cross-cutting topics | CC | Lessons identified, legacy, security, monitoring and evaluation, PHSM, data protection, public health programmes, translation, etc. | This cross-cutting topics pillar serves as a catch-all for any additional aspects or issues that may not be covered by the specific pillars but are deemed important for a comprehensive after action review. It encourages an examination of unique circumstances, emerging challenges or unexpected elements that played a role in the event.
© World Health Organization 2024. Some rights reserved. This work is available under the CC BY-NC-SA 3.0 IGO licence.

## List of Abbreviations
List of Abbreviations
AAR | After action review
ARI | Acute respiratory infection
BSL | Biosafety level
CBRN | Chemical, biological, radiological and nuclear
CBCM/FM | Community-based complaint mechanisms/feedback mechanisms
CDC | Centers for Disease Control and Prevention
CHW | Community health workers
CONOPS | Concept of operations
C3 | Command, control and communication
EBS | Event-based surveillance
EMT | Emergency Medical Team
EOC | Emergency Operation Centre
EOIS | Epidemic Intelligence from Open Sources initiative
EPRP | Emergency Preparedness and Response Plan
EWS | Early warning system
EWRS | Early warning and response system
GBV | Sexual and gender-based violence
HCW | Health care worker
HECP | Health Emergency Contingency Plan
HR | Human resources
IAR | Intra action review
ICU | Intensive care unit
IGO | Intergovernmental organization
IHR | International Health Regulations (2005)
ILI | Influenza-like illness
IMS | Incident management system
IPs | Implementing partners
IPC | Infection prevention and control
IT | Information technology
JEE | Joint external evaluation
MCC | Medical Centre Command
M&E | Monitoring and evaluation
MH | Mental health
MG | Mass gathering
MOC | Main Operation Centre
MoH | Ministry of Health
NGO | Nongovernmental organization
NHICC | National Health Incident Command Centre
PHSM | Public health and social measures
PoE | Point(s) of entry
PPE | Personal protective equipment
RCCE | Risk communication and community engagement
RCCE-IM | Risk communication, community engagement and infodemic management
RRT | Rapid response team
SARS-CoV-2 | Severe acute respiratory syndrome coronavirus 2
SARI | Severe acute respiratory infection
SimEx | Simulation exercise
SMEs | Subject matter experts
SOPs | Standard operating procedures
SPAR | State Parties Annual Reporting
TB | Tuberculosis
UN | United Nations
UNCT | United Nations Country Team
WASH | Water, sanitation and hygiene
WHO | World Health Organization
© World Health Organization 2024. Some rights reserved. This work is available under the CC BY-NC-SA 3.0 IGO licence.

## Setting for dropdown box (hidden)
Please select relevancy
Relevant
May be relevant
Not relevant

## PE1. Risk Assessments
PE1. Risk Assessments
Description: this pillar evaluates the effectiveness of risk assessments conducted prior to a MG event. It focuses on identifying potential threats, vulnerabilities and hazards that could impact the event's safety and security. Assessment considers factors such as the venue, crowd dynamics, environmental conditions and potential public health risks. The goal is to determine the adequacy of risk identification, risk analysis, risk mitigation and risk communication strategies in place to ensure the safety of event participants and the general public.
Relevant documents to review | Relevance for this AAR
Tool used for risk assessment | Please select relevancy
Previous risk assessment report in same area, similar events, previous SimEx reports, AAR reports | Please select relevancy
Event background and previous media reports related | Please select relevancy
Possible indicators | Relevance for this AAR
Reported consultation rates and patient transfer causes/day/area | Please select relevancy
Surveillance reports and screening reports (if any) | Please select relevancy
Numbers and location of medical teams, ambulances, facilities deployed (numbers of HCW deployed, numbers of EMS, numbers of beds avaliable, clinics) | Please select relevancy
Column1 | Relevance for this AAR
Has a risk assessment been conducted at all levels to allow for the identification of major risks which will be monitored during the event? if so, how did this assessment contribute to targeting priority hazards that will be monitored during the event? | Relevant
What type of health emergency preparedness and readiness activities were undertaken by the country based on the risk assessment results before the event? Was the risk assessment performed with other sectors, discussed and integrated into the event's Health Emergency Contingency Plan and SOPs? | Relevant
Was the decision-making process in responding to major incidents informed by risk assessment? Were the decisions made shared and clearly communicated to all relevant sectors? How were they communicated? | May be relevant
Were the results of the risk assessment tested through simulation exercises? | May be relevant
Did you perform a rapid risk assessment for all verified events within 24-48 hours of verification? | Not relevant
Was the risk assessment performed and discussed with other sectors? | Please select relevancy
Were the results of the risk assessment integrated and implemented into the MG event Emergency Preparedness and Response Plan (EPRP) and integrated with the national EPRP, etc.? | Please select relevancy
Were all-hazards risk assessment/profiling/registry conducted before, during and after the event? If so, when and what were the threats/hazards that were considered high risk? | Please select relevancy
Did the event attendees pose an additional risk for the host community or introduce hazards previously not reported in this setting? | Please select relevancy
What measures have been put in place to target high-risk populations, disadvantaged populations and vulnerable populations wishing to take part in a MG event? Have special safety measures been put in place for events held at night, such as including security, lighting, safe toilets, changing areas? | Please select relevancy
Are those participating in the event only from one country? If not, what were the other countries of origin of participants and spectators? Were you informed of the possible countries of origin and health profiles of MG event participants and spectators? If so, how has that information helped modify your plans? | Please select relevancy
© World Health Organization 2024. Some rights reserved. This work is available under the CC BY-NC-SA 3.0 IGO licence.
Relevant documents to review
(It is preferable to identify, collect and review these documents before discussing this pillar)
Possible indicators
(It is preferable to collect any available data before the AAR so that it can be validated and put in context during the discussion)
Trigger questions
(Please only select questions that are relevant for this AAR)

## PE2. Simulation Exercises
PE2. Simulation Exercises
Description: this pillar assesses the effectiveness of simulation exercises conducted in preparation for the MG event. It evaluates the identification and rectification of gaps and weaknesses identified during simulations and how well they were implemented to enhance preparedness, response and coordination during the actual event.
Relevant documents to review | Relevance for this AAR
Scenarios used for SimEx | Please select relevancy
SimEx and after action review reports | Please select relevancy
EPRP and contingency plan documents | Please select relevancy
Possible indicators | Relevance for this AAR
% tested processes out of all event management-related processes | Please select relevancy
% stakeholders involved in SimEx out of total stakeholders for the event | Please select relevancy
% process and/or plan changes based on SimEx results | Please select relevancy
Column1 | Relevance for this AAR
What type of simulation exercises have been conducted before the MG event? What were the objectives? | Relevant
How have the results of the simulation exercises been used to strengthen/modify policies, plans and/or SOPs before the MG event? Were the results communicated widely across relevant stakeholders and senior government leadership? | May be relevant
How have the results of the simulation exercises been used to strengthen interventions at points of entry? | Not relevant
Were all the most relevant multisectoral stakeholders involved in the SimEx? If not, why? | Please select relevancy
Were targeted simulation exercises provided for specific stakeholders from various sectors? If yes, can you explain which stakeholders and why? | Please select relevancy
Was the SimEx performed as as ad hoc exercise or part of a wider national programme of interconnected and increasingly complex exercises? If not, why? | Please select relevancy
Were the lessons identified from the SimEx well documented and implemented in the MG event? | Please select relevancy
© World Health Organization 2024. Some rights reserved. This work is available under the CC BY-NC-SA 3.0 IGO licence.
Relevant documents to review
(It is preferable to identify, collect and review these documents before discussing this pillar)
Possible indicators
(It is preferable to collect any available data before the AAR so that it can be validated and put in context during the discussion)
Trigger questions
(Please only select questions that are relevant for this AAR)

## PE3. Training
PE3. Training
Description: the training pillar examines the adequacy and relevance of training programmes conducted in preparation for the MG event. This includes assessing the proficiency of personnel in various roles, comprehensiveness of the training curriculum and use of innovative training methods. Evaluation aims to determine the extent to which training contributed to overall preparedness and response capabilities.
Relevant documents to review | Relevance for this AAR
Event medical services plan document | Please select relevancy
Model of healthcare system | Please select relevancy
Previous event reports include RA, SimEx and/or AAR reports | Please select relevancy
Possible indicators | Relevance for this AAR
% HCWs trained on priority skills | Please select relevancy
% health facilies with trained staff | Please select relevancy
Column1 | Relevance for this AAR
Did you identify a strategy to develop a training programme for MG event staff and volunteers ahead of the event? What type of training needs were identified? | Relevant
Was there a training programme for MG event staff and volunteers including those working in the command/coordination centres? | May be relevant
Was there a training programme for MG event staff and volunteers integrating information from different sectors (e.g security and health aspects)? | Not relevant
Were the emergency medical teams trained on dealing with unusual events such as mass casualties, stampede, etc? | Please select relevancy
Which main hazards were the Rapid Response Teams, if applicable, or Emergency Response Teams trained to deal with? | Please select relevancy
How was the event workforce trained and equipped to detect and respond to a public health event or emergency? | Please select relevancy
© World Health Organization 2024. Some rights reserved. This work is available under the CC BY-NC-SA 3.0 IGO licence.
Relevant documents to review
(It is preferable to identify, collect and review these before the discussion for this pillar)
Trigger questions
(Please only select questions that are relevant for this AAR)
Possible indicators
(It is preferable to collect any available data before the AAR so that it can be validated and put in context during the discussion)
Trigger questions
(Please only select questions that are relevant for this AAR)

## PE4. Contingency Plans
PE4. Contingency Plans
Description: contingency plans are crucial for addressing potential challenges during a MG event. This pillar evaluates the development, communication and implementation of contingency plans. It includes an assessment of the responsiveness of these plans to emerging scenarios, as well as their integration with overall event management and emergency response strategies.
Relevant documents to review | Relevance for this AAR
National Emergency Preparedness and Response Plan (EPRP) | Please select relevancy
Risk profile of the MG event area | Please select relevancy
Risk assessment report for the MG event and/or similar events | Please select relevancy
Possible indicators | Relevance for this AAR
% contingency plans developed for identified risks | Please select relevancy
Column1 | Relevance for this AAR
Were health and non-health stakeholders (in both private and public sectors as well as event organizers) involved in MG event planning from the early planning phase? | Relevant
Was a joint intersectoral contingency response plan developed and implemented for the MG event? | May be relevant
Were a MG event health emergency contingency plan (HECP) and SOPs developed? What were the key challenges? | Not relevant
Did the MoPH consult other sectors in the development of the HECP and SOPs? Who were the key stakeholders involved in the process? | Please select relevancy
Were MG event-related documents disseminated effectively to all stakeholders? How? | Please select relevancy
Which mechanism ensured that all stakeholders were aware of the content of the HECP and SOPs including stakeholder training and exercises? | Please select relevancy
Did the HECP and SOPs clearly outline the roles and responsibilities of all involved sectors including decision-makers and spokespersons? Were there any challenges? If yes, what were they? What was done to solve problems? Were the SOPs updated as a result? | Please select relevancy
Was there an existing formal intersectoral memorandum/agreement to identify roles and responsibilities of these stakeholders in relation to the event? | Please select relevancy
How did you manage the alignment/integration of different MG event-related documents developed by different sectors? Which sectors were involved? | Please select relevancy
Were specific contingency plans (e.g. mitigation, crowd management, CBRN protection, event/venue-specific operations plans) developed? If so, were those plans approved, communicated and tested? Did the plan include the surge capacity issue? | Please select relevancy
Did contingency plans include RCCE activities on when, where and how to seek health services at the MG event? | Please select relevancy
What was the estimated timeline from the onset of event preparedness set-up/establishment of working group or similar forum until the event? | Please select relevancy
© World Health Organization 2024. Some rights reserved. This work is available under the CC BY-NC-SA 3.0 IGO licence.
Relevant documents to review
(It is preferable to identify, collect and review these documents before discussing this pillar)
Possible indicators
(It is preferable to collect any available data before the AAR so that it can be validated and put in context during the discussion)
Trigger questions
(Please only select questions that are relevant for this AAR)

## HSO1. Command, Control & Coord
HSO1. Command, Control and Coordination
Description: this pillar reviews the structure and functionality of the command and control system established for the MG event. It assesses the clarity of roles and responsibilities, the efficiency of communication channels, and coordination among various agencies and stakeholders. The goal is to determine how well the command structure facilitates timely decision-making and effective responses.
Relevant documents to review | Relevance for this AAR
Legal document setting out stakeholder mandates | Please select relevancy
Existing health strategies, task allocation within the health sector, and previous SimEx and after action review reports | Please select relevancy
Data governance document | Please select relevancy
Possible indicators | Relevance for this AAR
Please select relevancy
Please select relevancy
Please select relevancy
Column1 | Relevance for this AAR
Did the Health Incident Command and Control Centre have a clear mandate, terms of reference and SOPs before the MG event? | Relevant
Were personnel in charge of the Health Incident Command and Control Centre properly trained and exercised? | May be relevant
How were coordination and communication between MoH and other non-health ministries and stakeholders (in both public and private sectors) managed at different levels during the MG event, including at the field operational level? | Not relevant
How effective was the information flow? How were roles and responsibilities defined and updated? How was accountability ensured and how well did coordination and communication work? | Please select relevancy
How did routine practice/emergency operation coordination develop during the MG event between different departments in MoH and other non-health ministries and sectors? | Please select relevancy
What type of challenges were encountered before, during and after operational coordination of the MG event? What was the nature of the challenges (e.g lack of communication, planning, identification of roles and responsibilities, etc)? Also, were any SOPs updated as a result? | Please select relevancy
Was there an existing formal intersectoral memorandum/agreement to identify roles and responsibilities in relation to the MG event between health and non-health sectors? Please list all existing reference documents and specify relevant stakeholders. | Please select relevancy
Were Health Incident Command Centre roles and functions comprehensive enough to play a leading part in coordinating surveillance and public health emergencies (all hazards) with other non-health sectors (in both public and private sectors) during the event? | Please select relevancy
Which currently existing coordination mechanisms were adapted by MoH and other stakeholders/sectors ahead of the MG event and which new coordination systems and SOPs were instituted for the event? How well did this work? Is it planned to use newly adapted coordination mechanisms and SOPs during the upcoming events? | Please select relevancy
How was the coordination of response activities done at different administrative levels (national, regional and local)/event venues and sites during the event? Highlight any good practices, challenges and lessons learned. | Please select relevancy
Was the process for decision-making inclusive and transparent? Was it based on the risk assessment? Was the rationale for decisions shared and clearly communicated with all sectors, event participants and the general public? | Please select relevancy
How were coordination mechanisms for allocation of internal/intersectoral resources (e.g. human, financial and supplies) established and were they an adequate response to a health emergency at different event-related locations and venues (e.g. points of entry, transportation hubs, stadiums, fan zones, etc.)? | Please select relevancy
Were intersectoral coordination mechanisms for management of the rapid response teams, if applicable (e.g. fire, police, emergency medical teams, CBRN protection, etc.) an effective response to an acute event at different event-related locations and venues (e.g. points of entry, transportation hubs, stadiums, fan zones, etc.)? | Please select relevancy
Was a mechanism established for MoPH coordination with public health authorities in the countries of origin of participants/international teams? How was this helpful for decision-making? | Please select relevancy
Were you able to reach public health authorities in the countries of origin before participants/international teams arrived in [country], when in [country], and after their departure from [country]? Did you encounter challenges? | Please select relevancy
Were incident management/command systems established for command, communication and control during the MG event at the central level? Describe the structure. Who leads the IMS? Was there a dedicated site for operationalizing the IMS? | Please select relevancy
Did the different command and control centres (tournament centre, medical centre, operation centre, etc.) have a clear mandate, terms of reference, SOPs before the event? | Please select relevancy
How were the different centres (tournament centre, medical centre, operation centre, etc.) activated and operationalized during the event? | Please select relevancy
How was coordination between the private health/public health sector managed? What were the key challenges and lessons learned? Any SOPs and plans updated? | Please select relevancy
Was a system established for monitoring and detecting signals of potential concern established at any of the command centres? If so, how was reporting and information-sharing achieved between the different command/operation centres? | Please select relevancy
Was there any major incident during the MG event? If yes, how was coordination with different stakeholders in both health and non-health sectors managed this major incident? | Please select relevancy
For major incident planning, were any challenges identified in intersectoral coordination before, during and after the event? Was this discussed, documented and SOPs updated? | Please select relevancy
What health emergency preparedness and readiness activities were undertaken by the host country based on risk assessment results before the MG event? Was the risk assessment performed with other sectors, discussed and integrated? | Please select relevancy
Were coordination mechanisms for allocation of internal/intersectoral resources (e.g. human, financial and supplies) established and adequate to respond to major incidents (e.g. points of entry, transportation hubs, stadiums, fan zones, etc.)? | Please select relevancy
Was there a mechanism for coordinating public health authorities in the different countries of event participants joining from different countries? Did you encounter challenges? Will you use this coordination mechanism for the MG event? | Please select relevancy
What type of challenges were encountered in coordination with international partners (e.g. UN agencies, NGOs)? Should specific actions be implemented before the MG event? | Please select relevancy
How did the coordination mechanisms at points of entry work? | Please select relevancy
Have medical regulations in communication with the care hospitals been upheld? | Please select relevancy
Has case management been provided at event venues and sites as well as in reference hospitals? What does it comprise, if any? | Please select relevancy
How has coordination been safeguarded with other sectors, including the private sector, when implementing infection prevention and control measures in health facilities, event venues and communities, as well as WASH activities? | Please select relevancy
How was coordination achieved with non-health sectors and partners when managing cases and deaths? | Please select relevancy
Was a mechanism for coordination and data-sharing with other partners/stakeholders developed and tested for a MG event? If so, please describe it. | Please select relevancy
How did event-related coordination for routine practice/emergency operations take place between different departments in MoH and other non-health ministries and sectors? What challenges were encountered during operational coordination? What was their nature (e.g. lack of communication, planning, identification of roles and responsibilities, etc.)? Were any SOPs updated as a result? | Please select relevancy
Were any challenges identified in intersectoral coordination before, during or after the MG event? Were these challenges discussed and documented, and SOPs updated accordingly? | Please select relevancy
Were there sufficient resources (human, material and financial) for multisectoral coordination at all levels? | Please select relevancy
How were administrative and financial management procedures taken into account to ensure effective and efficient management of human, material and financial resources allocated to medical coverage of the event? | Please select relevancy
Has the level of implementation of the medical coverage plan at each site been assessed? | Please select relevancy
Did public and private health sectors and partners have a coordination mechanism for surveillance and data-sharing for routine and ad hoc practice? Was it operational for the event? Was it effective? | Please select relevancy
© World Health Organization 2024. Some rights reserved. This work is available under the CC BY-NC-SA 3.0 IGO licence.
Relevant documents to review
(It is preferable to identify, collect and review these documents before discussing this pillar)
Possible indicators
(It is preferable to collect any available data before the AAR so that it can be validated and put in context during the discussion)
Trigger questions
(Please only select questions that are relevant for this AAR)

## HSO2. Capacity Building
HSO2. Capacity-building
Description: capacity-building is essential for enhancing the skills and capabilities of individuals and stakeholder involved in the MG event. This pillar evaluates the initiatives taken to build and strengthen capacities, including training programmes, skill development and the establishment of partnerships. Assessment aims to identify areas for further capacity enhancement.
Relevant documents to review | Relevance for this AAR
Previous event reports including risk assessments, SimEx, AAR reports | Please select relevancy
Please select relevancy
Please select relevancy
Possible indicators | Relevance for this AAR
Please select relevancy
Please select relevancy
Please select relevancy
Column1 | Relevance for this AAR
Was there any initial MG event-related capacity-building regarding hotline operators, telemedicine, electronic medical record system and the interventions of mobile units? | Relevant
Were needs assessments for capacity-building conducted? If so, what were the critical areas identified? How were these addressed? | May be relevant
If yes, how did this initial capacity-building contribute to the quality of mobile unit interventions during the event? | Not relevant
Was there any initial capacity-building related to mass casualty incident management prior to the event? | Please select relevancy
If yes, how did this initial capacity-building contribute to the quality of case management during the event? | Please select relevancy
Has there been any HR capacity-building regarding the collection, routing, transport and processing of lab samples in the run-up to the event? | Please select relevancy
What were the major challenges encountered during this multisectoral coordination and collaboration? | Please select relevancy
Were volunteers recruited to support the event? Did they all participate? If not, did contigency plans work when they failed to show up? | Please select relevancy
© World Health Organization 2024. Some rights reserved. This work is available under the CC BY-NC-SA 3.0 IGO licence.
Relevant documents to review
(It is preferable to identify, collect and review these documents before discussing this pillar)
Possible indicators
(It is preferable to collect any available data before the AAR so that it can be validated and put in context during the discussion)
Trigger questions
(Please only select questions that are relevant for this AAR)

## HSO3.Emergency Medical Services
HSO3. Emergency medical services
Description: this pillar focuses on the provision of emergency medical services during the MG event. It assesses the readiness, accessibility and effectiveness of medical services, including first aid, ambulance services and coordination with health-care facilities. Evaluation also considers the availability of medical personnel, equipment and facilities to handle potential health emergencies.
Relevant documents to review | Relevance for this AAR
Previous event reports include RA, SimEx, AAR reports | Please select relevancy
Event planning document | Please select relevancy
Layout and crowd management plan | Please select relevancy
Possible indicators | Relevance for this AAR
Access to medical team in 5 min | Please select relevancy
Time to reach hospital | Please select relevancy
% on-site versus total management | Please select relevancy
Column1 | Relevance for this AAR
Were pre-hospital services provided during the MG event? If so, by whom? For example, what type of resources were involved for pre-hospital event medical services and first air services? | Relevant
What types of medical services were provided within stadiums and by whom? | May be relevant
How was the emergency medical team (EMT) command centre established and activated during the MG event? | Not relevant
Was it clear who should receive reports/be informed in an emergency? What were the communication channels? Was there a hotline to faciliate this communication? | Please select relevancy
Have SOPs been developed to respond to all-hazard public health emergencies? | Please select relevancy
How were response activities to major incidents implemented by different sectors during the MG event? Highlight any good practices, challenges and lessons learned. | Please select relevancy
What type of mechanisms, including supply chains, have been put in place to liaise between testing centres (e.g. during COVID-19) and health-care centres? | Please select relevancy
What type of mechanisms have been put in place to liaise between event venues/sites and other emergency (surgical) treatment centres? What type of difficulties were encountered? | Please select relevancy
How was psychological support (first psychological aid) provided by specialists via established event hotlines? | Please select relevancy
How was the link between mobile units and medical regulations (SOPs and protocols) coordinated for patient transfers? Was there a SOPs for patient referrals including designated referral facilities? | Please select relevancy
How was medical and psychological support for patients and accident victims during the event funded? Was it free for event target groups, e.g. participants, staff, volunteers, spectators and the general public? | Please select relevancy
What type of infection prevention and control (IPC) measures were taken to protect health workers, patients (in hospitals and mobile units) and event participants? Have these measures proved sufficient? | Please select relevancy
Had the full range of stipulated coverage (medical teams, ambulances, infirmaries, hand washing and disinfection devices, sanitation facilities, etc.) already been put in place? | Please select relevancy
What type of policies or measures have been set up for vulnerable individuals or individuals/event participants with special needs (i.e. people at a higher risk of severe disease)? | Please select relevancy
If applicable, were there overlaps or duplications of functions and roles between rapid response teams (RRTs) from different sectors during the event? For what reasons? Who planned and coordinated RRT needs? Were additional planning/risk assessments identified to better synchronize resources and capacities allocated by different sectors? | Please select relevancy
Was the time lapse between RRT detection and response adequate? Were any challenges encountered ? If so, what actions were taken (increased HR, greater financial resources and supplies, dispatching capacity, etc.)? | Please select relevancy
How was the RRT composed? Who was responsible for its activation? | Please select relevancy
Was there a mechanism to ensure availability and accessibility of PPE and other requisite material for RRTs? | Please select relevancy
What type of main hazards were RRTs particularly well trained to anticipate? | Please select relevancy
Was there a roster for RRT members? How many personnel for each area of work? | Please select relevancy
© World Health Organization 2024. Some rights reserved. This work is available under the CC BY-NC-SA 3.0 IGO licence.
Relevant documents to review
(It is preferable to identify, collect and review these documents before discussing this pillar)
Possible indicators
(It is preferable to collect any available data before the AAR so that it can be validated and put in context during the discussion)

## HSO4. RCCE-IM
HSO4. Risk communication, community engagement and infodemic management (RCCE-IM)
Description: RCCE-IM evaluates the risk communication strategies employed to disseminate information, engage with the community, and manage misinformation and disinformation relating to the MG event. Assessment includes the development and implementation of risk communication plans, community outreach efforts, and measures taken to address and counter misinformation, disinformation or rumours.
Relevant documents to review | Relevance for this AAR
Previous event reports include RA, SimEx, AAR reports | Please select relevancy
National RCCE-IM plan | Please select relevancy
Please select relevancy
Possible indicators | Relevance for this AAR
Please select relevancy
Please select relevancy
Please select relevancy
Column1 | Relevance for this AAR
Was a risk communication, community engagement and infodemic management (RCCE-IM) strategy established for the event and streamlined with the national RCCE-IM strategy? | Relevant
Did you consider using surveillance data to support the development of a comprehensive RCCE-IM event strategy ? Did you consider data protection and privacy? | May be relevant
Was the capacity to develop and implement an RCCE-IM strategy for the event (HR, funds, area-specific technical tools, etc.) adequate? If not, for what reason? | Not relevant
How was the RCCE-IM strategy coordinated among sectors (e.g. working groups, task forces) before, during and after the event and with event hosts? Which key actors were leading RCCE-IM strategy implementation and response at local, regional and national levels? | Please select relevancy
Were an RCCE-IM plan and SOPs activated for the event, and when? What were the triggers to activate the RCCE-IM plan? Did you modify the plan during/after the event? What rationale was used to modify it? Which stakeholders were involved and impacted? Were these RCCE-IM activities prolonged after the event was over? How do you plan to implement this strategy in readiness for future events? | Please select relevancy
Have any elements of the risk communication strategy proved to be unnecessary or inadequate? | Please select relevancy
Did your existing RCCE-IM plans consider MG aspects such as venue admittance requirements, applied public health and social measures (PHSM), contact tracing and quarantine, infection prevention and control (IPC) measures, a mandatory testing and vaccination event policy (if applicable), as well as reach all event target groups? | Please select relevancy
Did you arrange media (including social media) monitoring activities to inform decision-making, and implement PHSM and the risk communication strategy? Did you assess the impact of the misinformation, disinformation and rumours on the event? | Please select relevancy
What type of online and offline formative research and listening systems were operational to detect international and national behavioural and social trends, including rumours, misinformation and disinformation? | Please select relevancy
Did the MG risk assessment consider the RCCE-IM domain? What key gaps/achievements were identified? | Please select relevancy
Was an existing formal intersectoral memorandum/agreement in place that identified roles and responsibilities in relation to the event between health and non-health sectors? Please list all existing reference documents and specify relevant stakeholders. | Please select relevancy
Were health and non-health actors (in both private and public sectors) involved in event planning from the early planning phase? | Please select relevancy
How were RCCE-IM data shared between health and non-heath sectors to inform decision-making and guide adjustments during the event? How effective was it? Did it improve intersectoral coordination? How can stakeholders feedback mechanisms be improved? | Please select relevancy
Were risk communications messages developed and disseminated during the MG event? Who was the authority sharing public health messages with the general public and event participants? Were there challenges clearing RCCE messages that needed to be addressed? | Please select relevancy
Which RCCE-IM building efforts were already in place before the event as part of event planning and preparations or based on risk assessment results? Did you identify areas for further improvement ahead of the event? | Please select relevancy
How were rumours, disinformation and misinformation identified, and what type of measures were taken to counter them? | Please select relevancy
Did you establish a platform and SOPs for online social listening and monitoring of public perceptions as well as rumours and early infodemic spread for the MG event? How did it function during event? Did you consider a platform and SOPs to counter rumours, misinformation, disinformation and early infodemic spread? | Please select relevancy
How effective were existing or newly developed community feedback mechanisms and how can they be improved? | Please select relevancy
Which process was applied to segment target audiences (e.g. based on geographical, epidemiological, occupational, behavioural or socio-economic context and risk, individual adherence to PHSM, individual and community risk perception)? | Please select relevancy
How did you reach different target audiences for the event? After the event did you identify additional audience groups that should be included, engaged and/or targeted with more event-related RCCE-IM messages and activities? | Please select relevancy
Did the national and event-based RCCE-IM strategy consider vulnerable and at-risk communities? How might engagement of these groups be improved? Would the developed RCCE-IM strategy strengthen the MG legacy? | Please select relevancy
Which process was applied to develop, test, approve, disseminate and evaluate the RCCE-IM messages for each target audience group? Were sectors other than health involved in this process (security, law enforcement, etc.)? Is there a need to update health messages for the upcoming events? | Please select relevancy
Which processes were already in place for selecting trusted communication channels and opinion influencers for each event target audience? | Please select relevancy
What type of coordination mechanism(s) for national and international media and social media were used for the event? Were there any channels or influencers that have not yet been fully used or engaged? | Please select relevancy
Did you identify additional national/international communication channels for further strengthening of RCCE-IM ahead of the event? | Please select relevancy
How did the event RCCE-IM strategy consider different languages, cultures, behaviours, educational levels, age groups, gender, disability, etc., in relation to the event target audience? | Please select relevancy
Which processes and indicators were already in place to monitor and evaluate effectiveness of the RCCE-IM strategy at the national level? How effective was this for the MG event? Did all response partners generally have a good understanding of strengths, challenges and adjustments needed to increase RCCE-IM impact? How could this be enhanced ? | Please select relevancy
Was capacity sufficient to support the response and implement the RCCE-IM plan for the event (HR, funding, technical tools, etc.)? | Please select relevancy
Was an existing online and offline social listening and feedback system used for the MG event? How were social and behavioural data used to feed into the response of RCCE and other pillars? | Please select relevancy
Which country-level public communication outputs were developed for the event? What type of challenges emerged for public communication and how did you overcome them? | Please select relevancy
Were there clear, streamlined SOPs/procedures for clearance of messages and materials for public communication? | Please select relevancy
Which authority shared public health messages with the general public and MG event participants? Were there challenges that need to be addressed? Was the risk communication public health message sharing process coordinated with other partners through their platforms? | Please select relevancy
Was the public information available in accessible formats, including appropriate language and culture, different levels of education, technological literacy, accessibility (e.g. for people who are sight-/hearing-impaired), etc.? | Please select relevancy
How was the RCCE-IM plan shared and coordinated among different sectors before, during and after the event? Which key actors participated in RCCE-IM plan implementation and response at local and national levels? | Please select relevancy
Which process was applied to segment target audiences? Were vulnerable and highly at-risk audiences taken into consideration? How were all identified audiences reached? | Please select relevancy
What type of coordination mechanism(s) with national and international media and social media were used for the event? What type of challenges emerged in this process? | Please select relevancy
Were indicators for regular RCCE-IM monitoring and evaluation efforts defined for the plan? How were results used to adjust RCCE-IM activities during the event? Was any RCCE-IM assessment done? | Please select relevancy
Have communication messages reached the target audience groups effectively most in need? If not, why not? | Please select relevancy
Did media monitoring provide added value in the monitoring of health and non-health events around the event? | Please select relevancy
Has community feedback been used to update risk communication messages and processes? | Please select relevancy
Did community, political and religious leaders contribute to the adoption of good practices (vaccination, compliance with barrier measures) during the MG event? | Please select relevancy
How has existing community trust influenced the effectiveness of public communication in addressing and managing emerging concerns? Additionally, how has this communication further developed or affected the trust relationship over time? | Please select relevancy
Have travel health leaflets or other information materials been developed and distributed among event attendees regarding what to do in case of any unusual public health event? | Please select relevancy
© World Health Organization 2024. Some rights reserved. This work is available under the CC BY-NC-SA 3.0 IGO licence.
Relevant documents to review
(It is preferable to identify, collect and review these documents before discussing this pillar)
Possible indicators
(It is preferable to collect any available data before the AAR so that it can be validated and put in context during the discussion)
Trigger questions
(Please only select questions that are relevant for this AAR)

## HSO5. Environment Health Surv
HSO5. Environment health surveillance
Description: this pillar examines the monitoring and surveillance of environmental health factors during the mass gathering event. It includes the assessment of air and water quality, sanitation facilities, waste management and other environmental aspects to ensure the well-being and safety of event attendees. Evaluation aims to identify areas for improvement in environmental health planning and surveillance.
Relevant documents to review | Relevance for this AAR
Meteorology reports | Please select relevancy
Previous event reports include RA, SimEx, AAR reports | Please select relevancy
Please select relevancy
Possible indicators | Relevance for this AAR
% participants covered by the surveillance system | Please select relevancy
time to verify alert and start reponse | Please select relevancy
Column1 | Relevance for this AAR
Has a system for monitoring and detecting public health/all-hazards threats been established at national and local levels and at MG event venues? | Relevant
What were the overall strengths and weaknesses of coordination of the MG event and any incidents that took place during it? | May be relevant
How was the event-based surveillance (EBS) system coordinated? Were data collected at a central site (e.g. Emergency Operations Centre (EOC) or public health intelligence hub) to facilitate data-sharing and a coordinated response? | Not relevant
Has event based-surveillance been adapted to capture priority events during the mass gathering? if yes, how (i.e. list new sources, reporting mechanism, verification methodology, coordination mechanism, communication pathway, response coordination, risk assessment, monitoring and evaluation (M&E) indicators)? | Please select relevancy
Was the list of notifiable diseases and definitions of cases/syndromes for the expected priority diseases and events up to date and reviewed before the MG event? With whom was it shared and how? | Please select relevancy
Have thresholds been predefined for priority diseases and signals? | Please select relevancy
How were detected signals verified? And what is the timeframe for verification? | Please select relevancy
Have you maintained a list of subject matter experts (SMEs)/networks specializing in particular disease areas who could be called up to assist with signal verification? | Please select relevancy
Which process was applied for EBS data analysis and reporting to the national Health Incident Command Centre? And for making general decisions on the event and event operations, and adjusting public health and social measures (PHSM), etc.? | Please select relevancy
Were there regional or bilateral arrangements with countries participating in the MG event to share/report surveillance or events data? | Please select relevancy
Did the national Health Incident Command Centre consider using Rapid Response Teams (RRT) and/or other sectors (including Ministry of Defence, Ministry of Internal Affairs, etc.) to support contact-tracing efforts in case of lack of capacity? How was communication across each of these sectors coordinated? | Please select relevancy
What type of mechanisms were put in place for alert management and triage of cases? | Please select relevancy
How were cases managed in isolation/quarantine and at health-care sites? | Please select relevancy
How were deaths managed during the event? | Please select relevancy
Have the epidemiological data collected been analysed and used to respond to a possible intervention at an event? | Please select relevancy
Has the Early Warning and Response System (EWRS) been strengthened? What improvements were made, and why? | Please select relevancy
How have partners and other sectors contributed to surveillance activities? | Please select relevancy
How have surveillance activities been adapted or strengthened during the event (e.g. HR, permanance system at call centres, overloading of call lines, etc.)? | Please select relevancy
Were there any weaknesses or gaps in the collection, storage, transmission or analysis of monitoring data during the event? | Please select relevancy
Did surveillance of diseases targeted for the MG event continue after it? If yes, for how long? | Please select relevancy
Were the national surveillance system and platform(s) tailored and reinforced, as well as event-based surveillance (EBS) and EWRS mechanisms activated for the MG event? If yes, identify any key challenges and improvements made. How was this used for decision-making? Were any mechanisms, e.g. reporting templates, needing to be tested, revised and updated ahead of future events? | Please select relevancy
What type of plans have been developed and/or updated to detect, report and respond to cases of infectious diseases, to conduct contact-tracing and follow-up, and quarantine confirmed cases in order to guide the response to the MG event? | Please select relevancy
What type of plans have been developed and/or updated to detect, report and respond to public health events (all-hazards) in order to guide the response to the MG event? | Please select relevancy
How did stakeholders support the establishment of national surveillance case definitions for diseases, reporting protocols/mechanisms and SOPs for enhanced EWRS/EBS prior to, during and after the event? | Please select relevancy
Did the Ministry of Public Health or Ministry of Health Incident Command Centre have any mechanisms in place on how to reach public health authorities or other stakeholders in the country of origin of participants/international teams before their arrival or after their departure? Did authorities encounter any challenges or identify good practices? | Please select relevancy
Did the public and private health sectors have a coordination mechanism for surveillance and data-sharing for routine and ad hoc practice? Was it operational for the MG event? | Please select relevancy
How did partners, event organizers, private and public health sector, and other non-health stakeholders contribute to the surveillance mechanism and EWRS for the event? What was included in the surveillance? How was information shared with partners and other sectors? How was the EBS system coordinated? | Please select relevancy
What type of surveillance activities were undertaken by the host country based on risk assessment results obtained before the event? Will authorities perform a dynamic risk assessment to inform decisions on the surveillance system ahead of future events? | Please select relevancy
Was the risk assessment performed and discussed with other sectors, and were its results integrated and implemented into the event surveillance plan, national surveillance and response plan, etc.? What type of activities were identified that could increase the level of operational coordination for existing systems and sectors? | Please select relevancy
Were available surveillance data analysed to establish the EBS before the event? Were relevant authorities able to access this data? What type of data was used to detect disease cases/outbreaks among different event target groups (teams, officials, service providers, event staff, spectators, participants, the general public)? | Please select relevancy
Did public health authorities or other event stakeholders apply International Health Regulations (IHR, 2005) mechanisms for coordinating and reporting purposes with the countries of origin of event target groups? | Please select relevancy
Were SOPs already in place to guide surveillance? Please list priority diseases and public health events (all-hazards) (CBRN protection, deliberate events, environmental health, etc.) under monitoring. | Please select relevancy
Were there sufficient resources (human/financial/material) to undertake surveillance and early warning in case of an outbreak and/or public health event (all-hazards) during the event? | Please select relevancy
Did the public health authorities establish a specific testing and screening programme (e.g. COVID-19, yellow fever, etc.) for participants/international teams at points of entry (PoE) in coordination with event organizers? | Please select relevancy
What type of surveillance data or other information was useful or lacking to guide response decisions (e.g. adjusting public health and social measures, imposing and lifting travel restrictions, restricting access to event venues, determining event venue capacity)? | Please select relevancy
Which surveillance systems before and during the event (e.g. sentinel or event-based surveillance system (EBS), Epidemic Intelligence from Open Sources (EOIS) initiative) were used to monitor trends or detect disease cases and clusters (e.g. ILI/SARI surveillance, ARI surveillance systems via GISRS or other platform, event-based surveillance)? | Please select relevancy
Was local/national laboratory capacity adequate for routine EBS operations and considered adequate in case of ad hoc emergency needs? Was the network of reference laboratories part of a national surveillance system? Were both lab and surveillance data linked together? | Please select relevancy
What type of strategies were set up to integrate data from multiple sources (e.g. surveillance, laboratories, intelligence, media, etc.) into situation reports for decision-makers and to support an all-hazards approach to risk assessment and mitigation after the event? | Please select relevancy
Value for money: were the surveillance systems cost-effective? Were there more cost-effective options for future events and routine post-event surveillance activities? (Consider performing a budget analysis of costs associated with establishing surveillance systems, staffing costs, etc.) | Please select relevancy
How were these surveillance systems able to contribute to routine/post-event monitoring, evaluation and learning? | Please select relevancy
Was the (daily) event situation report developed, shared with partners and confirmed by stakeholders as useful? | Please select relevancy
Which interorganizational/interstakeholder collaborative mechanisms worked well for surveillance? | Please select relevancy
© World Health Organization 2024. Some rights reserved. This work is available under the CC BY-NC-SA 3.0 IGO licence.
Relevant documents to review
(It is preferable to identify, collect and review these documents before discussing this pillar)
Possible indicators
(It is preferable to collect any available data before the AAR so that it can be validated and put in context during the discussion)
Trigger questions
(Please only select questions that are relevant for this AAR)

## HSO6. Points of Entry
HSO6. Points of Entry
Description: the points of entry pillar assesses the implementation of health measures at points of entry such as airports, ports and ground crossings to prevent the spread of infectious diseases during the MG event. This includes the effectiveness of screening procedures, coordination with public health authorities, and the availability of isolation and quarantine facilities. Evaluation aims to ensure the robustness of measures to protect public health.
Relevant documents to review | Relevance for this AAR
Previous event reports include RA, SimEx, AAR reports | Please select relevancy
Please select relevancy
Please select relevancy
Possible indicators | Relevance for this AAR
Please select relevancy
Please select relevancy
Please select relevancy
Column1 | Relevance for this AAR
Were any public health measures implemented at points of entry (PoEs) during the MG event? Please describe them and specify if there were any particular measures that targeted the general public, and all or a specific target group of participants to the MG. | Relevant
Did the public health authorities establish a specific screening programme (e.g. COVID-19, yellow fever, etc.) for participants/international teams at PoE, in coordination with event organizers? Was it effectively communicated to international travellers? | May be relevant
What types of preparedness activities (availability of contingency plans and SOPs, enhanced surveillance, management and transfer of suspected cases, etc.) have been carried out at PoE (airport, port and ground crossings)? | Not relevant
© World Health Organization 2024. Some rights reserved. This work is available under the CC BY-NC-SA 3.0 IGO licence.
Relevant documents to review
(It is preferable to identify, collect and review these documents before discussing this pillar)
Possible indicators
(It is preferable to collect any available data before the AAR so that it can be validated and put in context during the discussion)
Trigger questions
(Please only select questions that are relevant for this AAR)

## HSO7. Laboratory
HSO7. Laboratory
Description: this pillar reviews laboratory system functioning during the MG event. It assesses the capacity to conduct timely testing, the reliability of diagnostic tools, and the sharing of relevant information and data with national and international partners. Evaluation aims to identify strengths and areas for improvement in the laboratory response to potential health threats.
Relevant documents to review | Relevance for this AAR
Previous event reports include RA, SimEx, AAR reports | Please select relevancy
Please select relevancy
Please select relevancy
Possible indicators | Relevance for this AAR
Please select relevancy
Please select relevancy
Please select relevancy
Column1 | Relevance for this AAR
Was the local/national laboratory capacity adequate for routine EBS operations and considered adequate in case of ad hoc emergency needs? Was the network of reference laboratories part of a national surveillance system? Were lab and surveillance data linked together? | Relevant
Did the national laboratory system have any formal agreements with international reference laboratories? How could you increase capacities on an ad hoc basis in preparation for events? | May be relevant
Which procedures were used for information-sharing and decision-making between laboratories (including animal health laboratories), public health units, epidemiologists and public servants? | Not relevant
How did collaboration, coordination and information-sharing proceed with other laboratories in the health sector (e.g. national network laboratory) and internationally? | Please select relevancy
How was information from the laboratories managed? | Please select relevancy
What type of operational difficulties emerged in the laboratory system for collecting, routing, transport and analysing samples? | Please select relevancy
Did the analytical capacity of laboratories change before and during the MG event? | Please select relevancy
How was the laboratory system able to deal with simultaneous emergencies potentially emerging during the event? | Please select relevancy
© World Health Organization 2024. Some rights reserved. This work is available under the CC BY-NC-SA 3.0 IGO licence.
Relevant documents to review
(It is preferable to identify, collect and review these documents before discussing this pillar)
Possible indicators
(It is preferable to collect any available data before the AAR so that it can be validated and put in context during the discussion)
Trigger questions
(Please only select questions that are relevant for this AAR)

## HSO8. Supplies Logistics
HSO8. Supplies/logistics
Description: this pillar evaluates the adequacy and efficiency of logistics arrangements made for a MG event. It includes the procurement, storage, distribution and management of essential supplies, equipment and resources required for an emergency response, medical services and overall event operations. Assessment also considers the resilience of supply chains, stockpile maintenance and the ability to adapt to unforeseen challenges.
Relevant documents to review | Relevance for this AAR
Previous event reports include RA, SimEx, AAR reports | Please select relevancy
Please select relevancy
Please select relevancy
Possible indicators | Relevance for this AAR
Please select relevancy
Please select relevancy
Please select relevancy
Column1 | Relevance for this AAR
Was an estimate made of needed supplies, medications and equipment and a stockpile secured? Did you have a clear understanding how the supply chain works? | Relevant
Was there a mechanism to ensure the availability and accessibility of personal protective equipment (PPE) and other required material for rapid response teams (RRTs)? | May be relevant
Were equipment, materials and resources for case management and personal protection available? | Not relevant
Were there enough mobile units to adequately provide pre-hospital health services? | Please select relevancy
Have event reference hospital and evacuation routes been identified and sufficiently equipped? | Please select relevancy
Were there sufficient resources to protect personnel from infection (e.g. personal protective equipment (PPE)) and for waste disposal and decontamination? | Please select relevancy
Were there sufficient resources to protect different event target groups (e.g. handwashing devices, masks, etc.)? | Please select relevancy
How was waste managed in health-care facilities, mobile units, laboratories, screening stations, vaccination stations and event venues? | Please select relevancy
Was an estimate made of needed supplies, medications and equipment and a stockpile secured for acute public health emergencies relating to all-hazard event preparedness and response? | Please select relevancy
What scope of health services was provided at official event venues for event target groups and communities, and by whom? | Please select relevancy
How were supply chains (of inputs and medicines) managed ? | Please select relevancy
Did the repositioning of critical equipment result in a timely and effective response? | Please select relevancy
Were there sufficient resources (human, material and financial) to provide logistics support during the MG event? Did you know the focal point/procedure to request extra supplies? | Please select relevancy
Have other partners or sectors been involved in provision of logistics services? If yes, what role(s) did they play and how were they coordinated and managed? | Please select relevancy
How did the emergency purchasing system work (if applicable)? Who was able to authorize emergency funding? | Please select relevancy
© World Health Organization 2024. Some rights reserved. This work is available under the CC BY-NC-SA 3.0 IGO licence.
Relevant documents to review
(It is preferable to identify, collect and review these documents before discussing this pillar)
Possible indicators
(It is preferable to collect any available data before the AAR so that it can be validated and put in context during the discussion)
Trigger questions
(Please only select questions that are relevant for this AAR)

## HSO9. Human Resources
HSO9. Human resources
Description: this pillar focuses on the planning, deployment and management of human resources for a MG event. It assesses the sufficiency and appropriateness of personnel in various roles, their training and coordination of their activities. Additionally, evaluation includes an examination of the effectiveness of communication channels among team members and the adaptability of human resources to evolving situations.
Relevant documents to review | Relevance for this AAR
Previous event reports include RA, SimEx, AAR reports | Please select relevancy
Please select relevancy
Please select relevancy
Possible indicators | Relevance for this AAR
Please select relevancy
Please select relevancy
Please select relevancy
Column1 | Relevance for this AAR
Were there sufficient resources (human, material and financial) to carry out monitoring and early warning activities? | Relevant
Were there sufficient resources (human, material and financial) for collecting, routing, transporting and processing samples? | May be relevant
Were there sufficient resources (human, material and financial) to provide systematic support for medical transfer of patients? | Not relevant
Was there task-sharing for functions and roles between front-line responders in different sectors during the event? Were there areas where this created unnecessary overlap or confusion? | Please select relevancy
© World Health Organization 2024. Some rights reserved. This work is available under the CC BY-NC-SA 3.0 IGO licence.
Relevant documents to review
(It is preferable to identify, collect and review these documents before discussing this pillar)
Possible indicators
(It is preferable to collect any available data before the AAR so that it can be validated and put in context during the discussion)
Trigger questions
(Please only select questions that are relevant for this AAR)

## HSO10. Information-sharing
HSO10. Information-sharing
Description: information-sharing is crucial for effective decision-making and coordination during a MG event. This pillar assesses the mechanisms in place for timely exchange of relevant information among various stakeholders including government agencies, emergency responders and event organizers. Evaluation considers the accessibility, accuracy and timeliness of shared information to support coordinated responses and informed decision-making.
Relevant documents to review | Relevance for this AAR
Previous event reports include RA, SimEx, AAR reports | Please select relevancy
Please select relevancy
Please select relevancy
Possible indicators | Relevance for this AAR
Please select relevancy
Please select relevancy
Please select relevancy
Column1 | Relevance for this AAR
Were available plans and guidance materials for the MG public health event response discussed, agreed and shared with relevant multisectoral stakeholders involved in event planning and delivery (e.g. public health emergency contingency plans, guidelines, SOPs, isolation/quarantine, RCCE material)? How effectively were they used? | Relevant
Which mechanism was used for rapid information-sharing with government officials and stakeholders for decision-making in case of public health events? Were any back-up mechanisms available in case of IT systems collapse? | May be relevant
If you needed information from other sectors, was it easily available and accessible? Were there any challenges accessing information you needed? If yes, what were they? How were challanges overcome? | Not relevant
How was information from different stakeholders involved in the event collected and managed (i.e. compilation and dissemination of reports, interconnection with other sectors, access to information, confidentiality, clearance levels, security, etc.). Were there any challenges? Were standard operating procedures (SOPs) updated accordingly? | Please select relevancy
Did the public and private health sectors and partners have a coordination mechanism for surveillance and data-sharing for routine and ad hoc practice? Was it operational for the event? How did they contribute? | Please select relevancy
Was a mechanism developed for coordination and data-sharing with other partners/stakeholders? If yes, please describe it. | Please select relevancy
How was data and information-sharing established and what were the main challenges? | Please select relevancy
Was information on the health profiles of event participants available before the event? If so, how did that information help to modify the event contingency plans? | Please select relevancy
How was personal and confidential data from event target groups protected when sharing among different sectors? Were there any challenges? Were any SoPs updated accordingly? | Please select relevancy
How was information shared during the event? What information products have been developed? And at what rate? | Please select relevancy
How did initial capacity-building contribute to implementation of information management during the MG event ? | Please select relevancy
What were the major challenges and lessons learned from multisectoral collaboration and coordination relating to the MG event? | Please select relevancy
© World Health Organization 2024. Some rights reserved. This work is available under the CC BY-NC-SA 3.0 IGO licence.
Relevant documents to review
(It is preferable to identify, collect and review these documents before discussing this pillar)
Possible indicators
(It is preferable to collect any available data before the AAR so that it can be validated and put in context during the discussion)
Trigger questions
(Please only select questions that are relevant for this AAR)

## CC1. Lessons Identified&Legacy
CC1. Lessons learned and legacy
This cross-cutting topics pillar (CC1-CC7) serves as a catch-all for any additional aspects or issues that may not be covered by the specific pillars but are deemed important for a comprehensive after action review. It encourages an examination of unique circumstances, emerging challenges or unexpected elements that played a role in the event.
Relevant documents to review | Relevance for this AAR
Previous event reports include RA, SimEx, AAR reports | Please select relevancy
Key performance indicators for event management | Please select relevancy
Possible indicators | Relevance for this AAR
Please select relevancy
Please select relevancy
Please select relevancy
Column1 | Relevance for this AAR
What were the main lessons learned from event preparation and delivery that can be used for future MGs? | Relevant
What were the major lessons identified, areas of improvement and success stories during the entire event? | May be relevant
Were plans already in place to sustain this legacy? If yes, what are they? Please describe the research agenda, if any. | Not relevant
How were MG legacy planned activities achieved? | Please select relevancy
© World Health Organization 2024. Some rights reserved. This work is available under the CC BY-NC-SA 3.0 IGO licence.
Relevant documents to review
(It is preferable to identify, collect and review these documents before discussing this pillar)
Possible indicators
(It is preferable to collect any available data before the AAR so that it can be validated and put in context during the discussion)
Trigger questions
(Please only select questions that are relevant for this AAR)

## CC2. Security
CC2. Security
This cross-cutting topics pillar (CC1-CC7) serves as a catch-all for any additional aspects or issues that may not be covered by the specific pillars but are deemed important for a comprehensive after action review. It encourages an examination of unique circumstances, emerging challenges or unexpected elements that played a role in the event.
Relevant documents to review | Relevance for this AAR
Previous event reports include RA, SimEx, AAR reports | Please select relevancy
Please select relevancy
Please select relevancy
Possible indicators | Relevance for this AAR
Please select relevancy
Please select relevancy
Please select relevancy
Column1 | Relevance for this AAR
How has security contributed to successful health coverage of the MG event? | Relevant
How did security collaborate with other actors in its mission to ensure order and information-sharing during the MG event? | May be relevant
To what extent did security allow smooth access to official event venues (e.g. stadium, fan zones and fan camps, VIP zones, restrooms, hotels, etc.)? Were any special procedures established for different event target groups? | Not relevant
Have the staff in charge of security been trained in health risk mitigation as a prelude to event coverage? | Please select relevancy
How did initial capacity-building contribute to the implementation of security-related interventions during the event? | Please select relevancy
Were there sufficient resources to ensure the safety of different event target groups (e.g. athletes, officials, spectators, etc.) during the event? Were any modern AI technologies used to ensure security? | Please select relevancy
How was security integrated in the IMS, both physical and IT/cyber security? Was it sufficient? Were there back-up plans in case of a breach? | Please select relevancy
What were the major safety challenges during the event (e.g. health- and safety-related, cyber criminality, human resources, crowd control, spectator or participant security, etc.)? How were they surmounted? | Please select relevancy
© World Health Organization 2024. Some rights reserved. This work is available under the CC BY-NC-SA 3.0 IGO licence.
Relevant documents to review
(It is preferable to identify, collect and review these documents before discussing this pillar)
Possible indicators
(It is preferable to collect any available data before the AAR so that it can be validated and put in context during the discussion)
Trigger questions
(Please only select questions that are relevant for this AAR)

## CC3. Monitoring and Evaluation
CC3. Monitoring and evaluation (M&E)
This cross-cutting topics pillar (CC1-CC7) serves as a catch-all for any additional aspects or issues that may not be covered by the specific pillars but are deemed important for a comprehensive after action review. It encourages an examination of unique circumstances, emerging challenges or unexpected elements that played a role in the event.
Relevant documents to review | Relevance for this AAR
Previous event reports include RA, SimEx, AAR reports | Please select relevancy
Please select relevancy
Please select relevancy
Possible indicators | Relevance for this AAR
Please select relevancy
Please select relevancy
Please select relevancy
Column1 | Relevance for this AAR
Was a monitoring strategy already in place? What type of methods were used (e.g. debriefs, surveys, after action review)? Which sectors were involved? | Relevant
Were M&E activities implemented for different interventions and if yes, how? | May be relevant
Were monitoring and data collection tools available, adapted and/or revised and tested for the MG event? Have event personnel/HR been trained in their use? | Not relevant
© World Health Organization 2024. Some rights reserved. This work is available under the CC BY-NC-SA 3.0 IGO licence.
Relevant documents to review
(It is preferable to identify, collect and review these before the discussion for this pillar)
Possible indicators
(It is preferable to collect any available data before the AAR so that it can be validated and put in context during the discussion)
Trigger questions
(Please only select questions that are relevant for this AAR)

## CC4. PHSM
CC4. Public health and social measures (PHSM)
This cross-cutting topics pillar (CC1-CC7) serves as a catch-all for any additional aspects or issues that may not be covered by the specific pillars but are deemed important for a comprehensive after action review. It encourages an examination of unique circumstances, emerging challenges or unexpected elements that played a role in the event.
Relevant documents to review | Relevance for this AAR
Previous event reports include RA, SimEx, AAR reports | Please select relevancy
Please select relevancy
Please select relevancy
Possible indicators | Relevance for this AAR
% personal protective equipment (PPE) deployed | Please select relevancy
Please select relevancy
Please select relevancy
Column1 | Relevance for this AAR
Did other sectors encounter challenges in implementing public health and social measures (PHSM) developed by the Ministry of Public Health (MoPH) in preparation for this event? If so, what were they? And how where they surmounted? | Relevant
Did you identify specific training and educational needs for other sectors focusing on public health aspects of the MG event? | May be relevant
Did you identify supply needs for other sectors to follow and control established PHSM? | Not relevant
© World Health Organization 2024. Some rights reserved. This work is available under the CC BY-NC-SA 3.0 IGO licence.
Relevant documents to review
(It is preferable to identify, collect and review these documents before discussing this pillar)
Possible indicators
(It is preferable to collect any available data before the AAR so that it can be validated and put in context during the discussion)
Trigger questions
(Please only select questions that are relevant for this AAR)

## CC5. Data Protection
CC5. Data protection
This cross-cutting topics pillar (CC1-CC7) serves as a catch-all for any additional aspects or issues that may not be covered by the specific pillars but are deemed important for a comprehensive after action review. It encourages an examination of unique circumstances, emerging challenges or unexpected elements that played a role in the event.
Relevant documents to review | Relevance for this AAR
National data governance policy | Please select relevancy
Guidelines for medical data sharing | Please select relevancy
Previous event reports include RA, SimEx, AAR reports | Please select relevancy
Possible indicators | Relevance for this AAR
Please select relevancy
Please select relevancy
Please select relevancy
Column1 | Relevance for this AAR
How was personal and confidential data from event target groups protected when sharing among different sectors? | Relevant
Were there any challenges? If yes, how were they tackled? Were any SoPs updated accordingly? | Not relevant
© World Health Organization 2024. Some rights reserved. This work is available under the CC BY-NC-SA 3.0 IGO licence.
Relevant documents to review
(It is preferable to identify, collect and review these documents before discussing this pillar)
Possible indicators
(It is preferable to collect any available data before the AAR so that it can be validated and put in context during the discussion)
Trigger questions
(Please only select questions that are relevant for this AAR)

## CC6. Public health programmes
CC6. Public health programmes
This cross-cutting topics pillar (CC1-CC7) serves as a catch-all for any additional aspects or issues that may not be covered by the specific pillars but are deemed important for a comprehensive after action review. It encourages an examination of unique circumstances, emerging challenges or unexpected elements that played a role in the event.
Relevant documents to review | Relevance for this AAR
Previous event reports include RA, SimEx, AAR reports | Please select relevancy
National public health strategy | Please select relevancy
Please select relevancy
Possible indicators | Relevance for this AAR
Please select relevancy
Please select relevancy
Please select relevancy
Column1 | Relevance for this AAR
Did you identify any specific public health programmes or interventions to protect the local community and expected international participants attending the MG event (e.g. safe food and water, vaccination)? If yes, how were these implemented? | Relevant
What type of challenges were encountered when implementing public health programmes before the MG event? How can these challenges be overcome for future implementation and to achieve best practice? | Not relevant
© World Health Organization 2024. Some rights reserved. This work is available under the CC BY-NC-SA 3.0 IGO licence.
Relevant documents to review
(It is preferable to identify, collect and review these documents before discussing this pillar)
Possible indicators
(It is preferable to collect any available data before the AAR so that it can be validated and put in context during the discussion)
Trigger questions
(Please only select questions that are relevant for this AAR)

## CC7. Translation
CC7. Translation/interpretation services
This cross-cutting topics pillar (CC1-CC7) serves as a catch-all for any additional aspects or issues that may not be covered by the specific pillars but are deemed important for a comprehensive after action review. It encourages an examination of unique circumstances, emerging challenges or unexpected elements that played a role in the event.
Relevant documents to review | Relevance for this AAR
Risk Communication and Community Engagement and Infodemic Management (RCCE-IM) plan | Please select relevancy
Previous event reports include RA, SimEx, AAR reports | Please select relevancy
Possible indicators | Relevance for this AAR
Please select relevancy
Please select relevancy
Please select relevancy
Column1 | Relevance for this AAR
How did you manage to align different MG event-related documents which had been developed in different languages (national and international), notably emergency plans? | Relevant
Were translation services adequate for international participants seeking medical care in the MG event health care facilities? How was this accomplished, i.e. using human or AI-based services? How could this be improved? | May be relevant
Did the translated documents reach the target audience? If not, why not? Are there specific plans in place for their distribution to the target audience? | Not relevant
© World Health Organization 2024. Some rights reserved. This work is available under the CC BY-NC-SA 3.0 IGO licence.
Relevant documents to review
(It is preferable to identify, collect and review these documents before discussing this pillar)
Possible indicators
(It is preferable to collect any available data before the AAR so that it can be validated and put in context during the discussion)
Trigger questions
(Please only select questions that are relevant for this AAR)