## Slide 1: GLAAS Process
Module 2
GLAAS 2018/2019 cycle
Notes: This module offers a proposed process to follow in the implementation of GLAAS. However the process itself is flexible and countries are invited to adapt the process as required to suit their needs.

## Slide 2: Overview
This module will give an overview of the proposed process for implementing GLAAS at country level
This module provides a list of documents to submit alongside the survey form. Data collection will be until December 15th, 2018
Notes: This module offers a proposed process to follow in the implementation of GLAAS. However the process itself is flexible and countries are invited to adapt the process as required to suit their needs.
It is important to include all stakeholders and encourage high-level involvement early on in the GLAAS process.

## Slide 3: Suggested GLAAS process
Deciding to participate
Introductory meetings
Pre-data collection
Data collection
Data validation
Submitting documents
Reporting & data use
1
2
3
4
5
6
7

## Slide 4: Introductory meetings
Deciding to participate
Introductory meetings
Pre-data collection
Data collection
Data validation
Submitting documents
Reporting & data use
Meetings with key stakeholders and government representatives to introduce and advocate for GLAAS
1
2
3
4
5
6
7
Notes: Other steps in this phase could include:
Meeting with regional WHO office or regional facilitators
Other sensitisation meetings with key stakeholders

## Slide 5: Deciding to participate
Deciding to participate
Introductory meetings
Pre-data collection
Data collection
Data validation
Submitting documents
Reporting & data use
Decision by government to participate in GLAAS
If yes:
Identify a national focal person
Identify resource needs from WHO and outline brief work plan
1
2
3
4
5
6
7
Notes: After the government decides to participate, a National Focal Person (preferably from within a lead ministry or department) should be chosen to be the main coordinator of GLAAS or the national focal point.
The National Focal point will then work with relevant stakeholders to identify resource and budget needs and outline a brief work plan supporting these to submit to WHO. Seed funding will be available to support participation in GLAAS.

## Slide 6: Pre Data-Collection Phase
Deciding to participate
Introductory meetings
Pre-data collection
Data collection
Data validation
Submitting documents
Reporting & data use
Identify key stakeholders including:
  WASH line ministries
  National Statistics Office
  Ministry of Finance
  Ministry of Health
  Ministry of Education
  Drinking-water and wastewater regulators
  Ministry of Water Resources or equivalent
  In-country development partners (e.g. donors, NGOs, etc.)
  Private sector
  Other focal points of national, regional, or global monitoring initiatives
1
2
3
4
5
6
7
Notes: Other steps could include:
Formation of a national multi stakeholder working group
Sector mapping exercise to identify sector governance, key donors, major activities, budgets, implementers, key dates etc.)
Working group and government identifies key areas of mutual interest in the GLAAS survey
To identify other focal points:
It is recommended that GLAAS focal points reach out to the focal points of other national, regional or global monitoring initiatives particularly for the inception workshop or discussions (e.g. SWA, African Ministers’ Council on Water (AMCOW), Protocol on Water and Health, Water Supply and Sanitation Collaborative Council (WSSCC), Sustainable Sanitation Alliance (SuSanA), Integrated monitoring initiative for SDG 6, Integrated Water Resources Management monitoring initiative) to ensure alignment and coordination. Contact information for some of these country focal points is available from the WHO regional office and the GLAAS team at glaas@who.int.

## Slide 7: Pre data-collection phase
Deciding to participate
Introductory meetings
Pre-data collection
Data collection
Data validation
Submitting documents
Reporting & data use
Gather copies of any relevant sector documents, policies, and plans
Host an inception meeting or workshop to present GLAAS to government and key stakeholders
1
2
3
4
5
6
7
Notes: Other steps could include:
Formation of a national multi stakeholder working group
Sector mapping exercise to identify sector governance, key donors, major activities, budgets, implementers, key dates etc.)
Working group and government identifies key areas of mutual interest in the GLAAS survey

## Slide 8: Data collection phase
Deciding to participate
Introductory meetings
Pre-data collection
Data collection
Data validation
Submitting documents
Reporting & data use
1
2
3
4
5
6
7
National focal point coordinates responses to GLAAS survey from various stakeholders
Ongoing meetings and discussions among stakeholders to complete individual sections of survey
Notes: National Focal Point coordinates response to GLAAS survey with support from key stakeholders, working groups, and Regional focal point (i.e. WHO Regional Office focal point)
Other steps could include:
- Regional focal point (WHO Regional Office contact point or IRC/AguaConsult in Africa Region) act as main contact point for questions on survey

## Slide 9: Data presentation and validation
Deciding to participate
Introductory meetings
Pre-data collection
Data collection
Data validation
Submitting documents
Reporting & data use
1
2
3
4
5
6
7
Quality assurance and review of results
Findings are presented at multi-stakeholder national workshop
The government reviews the data and signs off on the results before submission
Notes: Findings from the GLAAS survey are presented back at a multi-stakeholder national workshop for a decision to be made about how GLAAS findings will be actioned. More information or clarification from the National Focal point may be required for data quality.
Other steps could include:
A nominated person at WHO HQ can provide quality assurance at the country or regional level

## Slide 10: Submission of GLAAS country survey documents
Deciding to participate
Introductory meetings
Pre-data collection
Data collection
Data validation
Submitting documents
Reporting & data use
1
2
3
4
5
6
7
National focal point submits documents including:
    Survey form
    Survey annex
    Country feedback form
    Data collection process form
    Consent form (if applicable)
Documents should be submitted to the WHO regional office and GLAAS at glaas@who.int by December 15th, 2018
Notes: After reviewing the data and GLAAS results, government signs off on data or discusses any issues with the GLAAS team and/or the National Focal Point, plus provides any feedback through country feedback form – information used by the GLAAS to improve the process and the data collection processes form.

## Slide 11: Reporting and data use
Deciding to participate
Introductory meetings
Pre-data collection
Data collection
Data validation
Submitting documents
Reporting & data use
1
2
3
4
5
6
7
Country data and GLAAS report published online
Production of Country Highlights with GLAAS and national focal point
Planning for national use of GLAAS data
Feedback to GLAAS from national focal point on process and suggested improvements
Notes: Results are reviewed by the GLAAS team at WHO headquarters and regional offices, as well as partners at regional and subregional levels (e.g. IRC) that are supporting the implementation and facilitation of the GLAAS survey. After the data has been analysed, the final GLAAS report and accompanying data will be published online. Country highlights are produced by the GLAAS team with support from the National Focal Point and published. To help improve subsequent GLAAS cycles, the National Focal Point and/or working group evaluates the process and provides feedback to the GLAAS team.

## Slide 12: Botswana
Example of Good Practices in the GLAAS Process:

## Slide 13: Botswana: GLAAS Process in 2016/2017
In 2016, Botswana gave formal notice of participation in GLAAS to the WHO regional office and GLAAS
A national focal point was identified and established at the Ministry of Land Management, Water and Sanitation (LMWS), which was the lead ministry throughout the GLAAS process
The national focal point assembled and worked with a focal point team from the Department of Water Affairs to coordinate the GLAAS process
Five relevant ministries and two organizations were identified as key stakeholders to contribute to GLAAS data collection

## Slide 14: Botswana: GLAAS Process in 2016/2017
A data collection workshop was organized and these ministries and organizations were in attendance. Although the Ministry of Finance was not present, they were able to provide data to the national focal point
Once all data was collected, a data validation workshop was held. The members in attendance considered themselves Botswana’s WASH team.
The GLAAS process highlighted that clear leadership in the WASH sector and contributed to reorganization of the WASH sector in Botswana.

## Slide 15: Thank you!
For additional information or assistance please contact: glaas@who.int